AM804001: Project Management

Assessment 1: Case Study

| Study block 2 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Date issued |  |  |  |  |  |  |  |  |
| Due date |  |  |  |  | Time |  |  |  |
| Delivery: |  | Submit to Turnitin via Moodle before deadline |  |  |  |  |  |  |
| Weighting |  | 30% |  |  |  |  |  |  |
| Marks out of |  | 20 |  |  |  |  |  |  |
| Instructions |  | Complete this cover sheet and attach to you your assignment. - This assignment must be your own work. - Collusion, copying or plagiarism may result in disciplinary action. - We advise that you keep a copy of this assignment. - Word limit is 2000 Refer to following website for reference related resources: http://www.cite.auckland.ac.nz/index.php?p=quickcite |  |  |  |  |  |  |
|  |  | We confirm that: This is an original assessment and is entirely my own work. Where ideas, tables, diagrams etc. of other writers have been used, we have acknowledged the source in every case. This assignment has not been, nor will be, submitted as assessed work for any other academic course. |  |  |  |  |  |  |
| Student’s Name |  |  | ID No |  |  | Signature |  |  |
| Date |  |  |  | Cohort Number |  |  |  | 1 |

CONTENTS

1.	Introduction	3

2.	Project Management Methodologies (Project title)	3

2.1 WATERFALL	3

2.2 EXTREME PROGRAMMING METHODOLOGY (XP)	3

2.3 RAPID APPLICATION DEVELOPMENT (RAD)	3

3.	Critical evaluation of chosen methodology …	3

4. MAORI INCLUSION IN THE PROJECT	3

4.	References	4

# Introduction

For the purpose of this report, the case study chosen is ….

This project requires ….

In the current COVID-19 situation ….

In order to carry out this project, three methodologies have been suggested to go ahead with the...

Out of these, .. is considered the most appropriate methodology to undertake the project.

# Project Management Methodologies (Project title)

## 2.1 WATERFALL

For the development of …

## 2.2 EXTREME PROGRAMMING METHODOLOGY (XP)

Being an agile methodology…

## 2.3 RAPID APPLICATION DEVELOPMENT (RAD)

The use of RAD as a methodology

# Critical evaluation of chosen methodology …

To choose a methodology for the …. project,

# 4. MAORI INCLUSION IN THE PROJECT

# References

Agarwal, R., Prasad, J., Tanniru, M., & Lynch, J. (2000). Risks of rapid application development. Communications of the ACM.

Berger, H., & Beynon-Davies, P. (2009). The utility of rapid application development in large-scale, complex projects. Information Systems Journal, 19(6), 549-570.

Beynon-Davies, P., Canre, C., Mackay, H., & Tudhope, D. (1999). Rapid application development (RAD): an empirical review. European Journal of Information Systems, 8(3), 211-223.

Coleman, G., & Verbruggen, R. (1998). A quality software process for rapid application development. Software Quality Journal, 7(2), 107-122.

Erickson, J., Lyytinen, K., & Siau, K. (2005). Agile modeling, agile software development, and extreme programming: the state of research. Journal of Database Management (JDM), 16(4), 88-100.

Farrell, A. (2008). Selecting a software development methodology based on organizational characteristics.

Geambasu, C. V., Jianu, I., Jianu, I., & Gavrila, A. (2011). Influence factors for the choice of a software development methodology. Accounting and Management Information Systems, 10(4), 479-494.

Hazzan, O., & Dubinsky, Y. (2003). Teaching a software development methodology: the case of extreme programming. In Proceedings 16th Conference on Software Engineering Education and Training, (pp. 176-184).

Hirschberg, M. A. (1998). Rapid application development (rad): a brief overview. Software Tech News, 2(1), 1-7.

Layman, L., Williams, L., Damian, D., & Bures, H. (2006). Essential communication practices for Extreme Programming in a global software development team. Information and software technology, 48(9), 781-794.

Lindstrom, L., & Jeffries, R. (2004). Extreme programming and agile software development methodologies. Information systems management, 21(3), 41-52.

Maori, D. M. (1994). Maori health perspectives.

McCormick, M. (2012). Waterfall vs. Agile methodology.

Mitchell, S. M., & Seaman, C. B. (2009). A comparison of software cost, duration, and quality for waterfall vs. iterative and incremental development: A systematic review. In 2009 3rd International Symposium on Empirical Software Engineering and Measurement, (pp. 511-515).

Newkirk, J., & Martin, R. C. (2000). Extreme programming in practice. In Addendum to the 2000 proceedings of the conference on Object-oriented programming, systems, languages, and applications (Addendum), (pp. 25-26).

Peterson, K., Wohlin, C., & Baca, D. (2009). The waterfall model in large-scale development. In International Conference on Product-Focused Software Process Improvement, (pp. 386-400). Berlin.

Robb, M., Harmsworth, G. R., & Awatere, S. (2015). Māori values and perspectives to inform collaborative processes and planning for freshwater management. Landcare Research.

Salo, O., & Abrahamsson, P. (2008). Agile methods in European embedded software development organisations: a survey on the actual use and usefulness of Extreme Programming and Scrum. IET software, 2(1), 58-64.

# VR Learning Platform for Healthcare Training

## 1. Introduction

Virtual Reality (VR) technology is revolutionizing healthcare training by providing immersive and interactive learning experiences. Otago Polytechnic aims to implement a VR platform for its Nursing and Healthcare programs, enabling students to simulate real-life medical procedures in a controlled environment. This report explores the key aspects of the VR Learning Platform project, including its scope, technological requirements, integration with the existing Learning Management System (LMS), cultural considerations, risk management, and training strategies.

## 2. Project Scope and Objectives

The primary objective of the VR Learning Platform is to enhance the educational experience of nursing and healthcare students by providing a simulated hospital environment. Key features include:

• Immersive 3D environments for realistic training.

• Multi-user collaboration for team-based learning.

• Role-playing capabilities for interactive scenarios.

• Integrated feedback system for performance assessment.

• Seamless integration with Otago Polytechnic’s LMS.

• Culturally responsive healthcare practices following Iwi/Māori frameworks.

## 3. Technology Implementation

The successful implementation of the VR Learning Platform requires robust hardware and software components. High-quality VR headsets, motion controllers, and haptic feedback devices will be used to ensure an immersive experience. The software solution will be developed using game engines like Unity or Unreal Engine, with AI integration for adaptive learning.

## 4. Integration with LMS and Cultural Responsiveness

To ensure a seamless learning experience, the VR platform must integrate with Otago Polytechnic’s existing LMS, allowing lecturers to track student progress. Additionally, culturally responsive healthcare practices must be embedded in the simulations, incorporating traditional Māori healing principles and ethics.

## 5. Risk Management and User Training

A comprehensive risk management strategy will address potential technological failures, cybersecurity concerns, and user resistance. Training programs for both students and lecturers will be developed to ensure smooth adoption of the platform.

## 6. Challenges and Proposed Solutions

Implementing a VR-based learning platform presents challenges such as high costs, technological limitations, and resistance to change. To mitigate these, funding opportunities will be explored, hardware requirements optimized, and continuous user support provided.

## 7. Conclusion and Recommendations

The VR Learning Platform has the potential to transform healthcare education at Otago Polytechnic. By leveraging immersive VR experiences, students can develop critical skills in a risk-free environment. It is recommended that pilot programs be launched to gather feedback before full-scale implementation.