AM804001: Project Management

Assessment 2: Case Study – Project Management Plan

| Study block 1 |  | 2023 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Date issued |  |  |  |  |  |  |  |  |
| Due date |  |  |  |  | Time |  |  |  |
| Delivery: |  | Submit to Turnitin via Moodle before deadline |  |  |  |  |  |  |
| Weighting |  | 70% |  |  |  |  |  |  |
| Marks out of |  | 100 |  |  |  |  |  |  |
| Instructions |  | Complete this cover sheet and attach to you your assignment. - This assignment must be your own work. - Collusion, copying or plagiarism may result in disciplinary action. - We advise that you keep a copy of this assignment. - Word limit is 3000-3500 words Refer to following website for reference related resources: http://www.cite.auckland.ac.nz/index.php?p=quickcite |  |  |  |  |  |  |
|  |  | We confirm that: This is an original assessment and is entirely my own work. Where ideas, tables, diagrams etc. of other writers have been used, we have acknowledged the source in every case. This assignment has not been, nor will be, submitted as assessed work for any other academic course. |  |  |  |  |  |  |
| Student’s Name |  |  | ID No |  |  | Signature |  |  |
| Date |  |  |  | Cohort Number |  |  |  |  |

Table of Contents

Executive Summary	2

## Executive Summary

| Project name | OPAIC Virtual Reality Learning Platform for Healthcare Training (OPAIC-MedVR) |
| --- | --- |
| Project Type | Software product development – Healthcare Virtual Reality Learning Platform |
| Project Goals | Develop VR platform that simulates real-world healthcare scenarios such as patient diagnosis and emergency response within virtual hospital environment. Implement multi-user capabilities and feedback system to allow lecturers to assess student performance during simulations. Create user training and support for student and lecturers on how to use OPAIC-MedVR. |
| Project Deliverables | Tangible deliverables: -VR homepage and navigation integrated within OPAIC LMS. -Single-sign on using existing student and lecturer accounts. -Multiplayer mode for students and observer mode for lecturers. -Role-playing scenarios for students. -User training manual on how to use OPAIC MedVR. -Feedback feature for lecturers. -User training for students and lecturers. -Maori values and design integration into homepage and VR. -VR Hospital Rooms: -Emergency Room -Intensive Care Unit -Medical Ward -Operating Room -Maternity Care -Behavioural and Mental Room -Family Room -Neonatal Intensive Care Unit -Github repository of source code -Jira artifacts Intangible deliverables: -Good User Experience for students and lecturers. -No bugs and no errors during usage. -The VR is responsive and fast for students and lecturers. -Available 24/7 at 99.95% uptime. -The students’ and lecturer’s data are secure and protected. -The VR has scalability feature which handles increasing number of users without affecting performance. -The code is efficient and well documented. -The code is easy to maintain for future updates. -The code has been tested for errors to ensure standards. -Good logging for monitoring. -Availability of VR for students and lecturers everywhere with Internet. |
| Project Methodology | Agile - Scrum |
| Project Budget | Phase; Estimated Cost, NZD. Sprint 0; $107,793.00. Sprint 1; $39,866.40. Sprint 2; $74,037.60. Sprint 3; $51,256.80. Sprint 4; $74,995.20. Sprint 5; $34,171.20. Sprint 6 Sprint 7 Sprint 8 Sprint 9 Sprint 10; $34,171.20 $34,171.20 $34,171.20 $34,171.20 $74,995.20. Total Cost for Project:; $593,800.20. |
| Project Schedule | Start Date: 12 March 2025 Estimated Completion Date: 22 July 2025 Estimated Duration: 95 Working days |
| Milestones | Date; Milestones. 12 March 2025 25 March 2025; Project start Preparation for Sprint 1 done.. 14 April 2025; Completion of UI/UX flows.. 14 April 2025; Completion of Emergency Room. 25 April 2025 29 April 2025 29 April 2025 29 April 2025 8 May 2025 12 May 2025 21 May 2025 29 May 2025 6 June 2025 16 June 2025 24 June 2025 2 July 2025 10 July 2025 15 July 2025 18 July 2025 22 July 2025; Completion of Deployment to Test Environment Completion of lecturer dashboard Completion of LMS integration Completion of multi-user capabilities Completion of User Training and lecture to students and lecturers Completion of Intensive Care Unit Deployment to production Completion of Medical Ward Completion of Operating Room Completion of Maternity Care Completion of Behavioral and Mental Health Room Completion of Family Room Completion of Neonatal Intensive Care Unit (NICU) Completion of Manual and User Training to Students and Lecturers Deploy to Production Project Closure. |
| Risks | - Tasks might take more time to complete as the tasks are assigned to interns. - The buffer did not consider sick leaves and absences of employees.. - Students or lecturers may be hesitant and avoid using the new VR. - Malfunctions of hardware and software - VR simulations might not reflect the Maori practices.. |

2. Background and Purpose

The VR Learning Platform for Healthcare Training is an innovative project aimed at enhancing the educational experience for Nursing and Healthcare students at Otago Polytechnic. The platform will leverage virtual reality (VR) technology to simulate real-world medical procedures, enabling students to practice and refine their skills in a safe, immersive environment. The platform will feature multi-user capabilities, allowing students to collaborate in real-time, and will integrate with the Polytechnic's existing Learning Management System (LMS). Additionally, the platform will incorporate culturally responsive healthcare practices rooted in Iwi/Māori health frameworks and traditions.

The project will be managed using the Scrum methodology, ensuring flexibility, iterative development, and continuous stakeholder feedback. The key deliverables include the development of immersive 3D environments, role-playing simulations, an integrated feedback system, and user training programs for both students and lecturers. The project will also address potential risks, such as technology malfunctions and user resistance, through a comprehensive risk management plan.

The estimated budget for the project is NZD 250,000, with a projected completion timeline of 12 months. The project will be executed in six sprints, each focusing on specific deliverables, culminating in the final release of the VR platform.

2. Background and Purpose

Otago Polytechnic is committed to providing high-quality, career-focused education to its students. The Nursing and Healthcare programs are among the most popular, with a strong emphasis on practical, hands-on training. However, the COVID-19 pandemic has highlighted the need for innovative, flexible learning solutions that can adapt to changing circumstances, such as lockdowns and social distancing measures.

The VR Learning Platform for Healthcare Training aims to address these challenges by providing students with a virtual environment where they can practice medical procedures, collaborate with peers, and receive real-time feedback from lecturers. The platform will also incorporate culturally responsive healthcare practices, ensuring that students are equipped to provide care that is sensitive to the needs of diverse populations, particularly Māori communities.

The purpose of this project is to create a state-of-the-art VR platform that enhances the learning experience for Nursing and Healthcare students, improves their practical skills, and prepares them for real-world healthcare scenarios. The platform will also support lecturers in delivering high-quality education, even in remote or hybrid learning environments.

3. Project Scope

The project scope is defined as a statement by writing the context, main inputs and outputs and main functions of the system to be developed. Project scope defines all tasks, activities, resources, timelines, decisions, and project boundaries that must be done to meet project goals and deliverables. The project scope statement (PSS) is prepared for the customer to illustrate the purpose of developing the project and plan of all activities needed to accomplish the project. The PSS warrants that all stakeholders are benefited to understand the project (Althiyabi & Qureshi, 2021).

It is explained by Amjad et al. (2017) that scope can be referred to all work and processes involved in delivery of the required value product. Defining the project scope can be considered as building the foundation for the project and understanding by all parties of what will be delivered by the project. Fageha and Aibinu (2013) stress the importance of defining the project scope at the very beginning, considering all stakeholders’ requirements and needs. All stakeholders input and early project definition helps to understand the stakeholders’ needs and determine all the work required to be performed to minimise changes during the project completion. However, as it is explained by Amjad et al. (2017) that software product development may have flexible and complex nature that requires agile scope definition. Therefore, five level planning is applied to manage the flexibility of scope definition in agile, from the product vision planning creating big picture to more specific product road map and planning on the release, iteration and day level. In Scrum the project scope is approached by defining the product vision and the product backlog (Schwaber, 2004).

3.1 Objectives

It is explained by Pichler (2021) that the project goal is the outcome based and it is important what outcomes the project delivers to the stakeholders.  Software development projects objectives move from the feature based towards the value based with the shift from the importance of the features to the importance of the value the project can deliver (Pichler, 2021).

Pedroso and Oliveira (2013) add that the software development project objectives relates to the value it creates for the stakeholders and to the customers satisfaction. The main software product development project goal is delivering value to the client and stakeholders focusing on the purpose that the project aims to fulfil (Scrum.org, 2021).

The Otago Polytechnic (OP) online Veterinary nursing course project’s goal can be seen in creating the possibility for the students and tutors to continue the education process in the Covid time and to create the online learning experience that is as close as possible to the real life conditions. This project objective is to develop online Veterinary nursing course for Otago Polytechnic (OP) that should provide the possibility for OP Students to gain knowledge and  the veterinary learning experience through online simulation gaming. With the software product, as a result of this project, OP students should be able to perform online simulations of diagnostic, treatment and administrative activities for domestic and farm animals. The software should allow to have secured individual and group access to online training, class projects and database with training archive. Students and tutors should be able to communicate via real time chat and video conferencing.

3.2 Deliverables

Bryde and & Joby (2007) explain the deliverables as the project’s end product that also can be named as measurable results that can be classified as tangible results and intangible results. Jaber et al. (2018) highlights that accurate definition and description of the project deliverables in terms of stakeholders requirements can help with accurate work identification and planning and create the product vision. The deliverables in terms of outputs could be tangible objects created as the project result (product, report and document) or new state that the project created (Jaber et al., 2018). In case of software product development with Scrum the tangible objects could be the main software functions and features, while the intangibles explain how the operations will be different for the stakeholders’ after software installation and usage (Schwaber, 2004).  The tangible and intangible deliverables for the OP online Veterinary nursing course project are listed below. Online simulation learning modules are based on the OP NZ Diploma in Veterinary, level 6 (OP Vet Nursing, 2021).

Tangible deliverables:

-Homepage with login, navigation and all features information.

-Security package (access security, network security, students’ personal information defence).

-Shared access for group simulation training and project work for multiple students and one lecturer.

-Past learning repository (learning history database and storage).

-Communication Suite that includes real time chat and video conferencing.

-Online simulation games for Veterinary nursing course for domestic and farm animals (for 8 learning courses):

- Course 1-Veterinary Nursing Professional Practice

- Course 2-Nursing Process, Disease Pathology, and Life Support

- Course 3-Nutrition, Therapy, Wound Care and Bandaging

- Course 4-Clinical Skills1

- Course 5-Surgery, Anesthesia, and Pharmacology

- Course 6-Imaging, Diagnostics and Dentistry

- Course 7-Clinical Skills2

- Course 8-Veterinary Nursing Services

-Special page with guide to Maori/Iwi practices.

-Online training for OP employees on using the online veterinary learning course.

-User guide within the software package and user documentation.

Intangible deliverables:

-Possibility for the students and OP to continue the learning process without interruptions during the lockdowns and Covid restrictions.

-Possibility for Offshore students to study Veterinary nursing course.

-Through participation simulations and the real nursing practices the students will gain practical experience requited for real work practice and work placement training.

-Increasing students’ satisfaction and work preparedness level.

3.3 Milestones

A milestone is explained by McAbee (2021) as a significant event within the projects’ life that helps in measuring the project’s progress compared with the final point. Within the software development project the agile milestone defined as a moment that displays the important stage in development (Wrike, 2021). For example, it could be when the major deliverable is completed (McAbee, 2021), or when the design is approved (Wrike, 2021).

In the agile development the milestones could be used to measure the performance and check if the project is on track. Within agile approach and scrum process the development lifecycle is separated on iterations, and as the sprints result in delivering of completed element of functionality the scrum team may to have the milestones connected with the end of the sprints (Wrike, 2021).

The milestones for the OP online Veterinary nursing course project are listed below.

| Phase | Milestones | Date |
| --- | --- | --- |
| Foundation phase | Project start | 7 September 2021 |
|  | Foundation Phase completed | 17 September 2021 |
|  | Homepage with login, navigation, security, and database -Done | 1 October 2021 |
| Development | Approval of game characters and Guide to Maori/Iwi practices page by OP and Maori Board | 13 October 2021 |
|  | Game page, online repository page, Maori/Iwi page, Game characters - Done | 15 October 2021 |
|  | Communication suite done | 22 October 2021 |
|  | Online user guide Done | 28 October 2021 |
|  | Release 1 -of Veterinary nursing simulation game with Couse1 | 29 October 2021 |
|  | Release 2 -of Veterinary nursing simulation game Couses 1-4 | 12 November 2021 |
|  | Release 3 -of Veterinary nursing simulation game Couses 1-6 | 26 November 2021 |
|  | Final Release 4 -of Veterinary nursing simulation game Couses 1-8 | 10 December 2021 |
| Closure | Project completed and closed | 16 December 2021 |

3.4 Technical requirements

For the project success the technical requirements to software product needs to be defined in details and they create a formal agreement between the customer and the developer describing specific characteristics for the product to meet (Altexsoft, 2021).   Technical requirements to the software products are divided into functional and nonfunctional and within Scrum Project the functional and nonfunctional requirements that product needs to meet are specified in the Product Backlog (Schwaber, 2004). It is very complex and difficult task to consider in full both types of requirements, thus it requires high level of technical knowledge from the product owner and project team, and collaborative work with stakeholders (Chen et al., 2013).

Functional requirements describe the functionality and determine what product need to do, what features and functions the product can perform (Chen et al., 2013). Non-functional requirements determine how the product performs, describing the system’s properties and responsible for the system’s quality (Altexsoft, 2021). For example, the non-functional requirements relate to performance, response time, security, reliability and availability, compatibility and maintainability (Singhera & Shah, 2006).

3.4.1 Functional requirements

The examples of some of the OP online Veterinary nursing course project functional requirements are listed below:

- Access on main page with login and password window.

- Main page should have the navigation to Courses pages, game page, learning depository page, Maori/Iwi page

- Storage of students’ personal data should meet general data protection requirements standards.

- The teacher can access and get connected to different group game sessions.

- Students should be able to have individual and group access simultaneously to the simulation game sessions.

- The lecturer and students should be able to communicate within the game session and out of the game session through chat and video conference options.

- Video conferencing and chat should be access through game page and main page.

- The average time a student takes to go through the simulation course should be similar to the time required to go through the course materials in the class.

- Simulation game content meets the NZQA Course content requirement of New Zealand Diploma in Veterinary Nursing ( Level6) provided by OP.

- The simulation game content and Maori/Iwi page content meets the Maori Counsel requirements to ethics and values.

3.4.2 Non-functional requirements

Non-functional requirements examples related to the OP online Veterinary nursing course project explained by Altexsoft (2021) can be seen below:

-Security requirements are focused on protecting the system from malware attacks and unauthorised access to the data and the system.

OP online Vet project requirements: 1) the permissions to access to students data, learning history and game sessions can be changed only by the OP IT administrator. 2) With the attempt to access the system by the user from the different device the system should request user verification through the access code to be sent via email or text message.

-Response time indicates the system’s response on different user activities;

OP project requirements: 1) Main page loading time: 2 seconds max, 2) Simulation gaming reaction recommended - 0.1 second, Max time - 1 second. Reaction time more than 3 seconds – Not accepted. As stated by Altexsoft (2021) this parameter is critical for product quality as the user lose attention completely after 10 seconds.

- Compatibility determines how the product interacts with other systems and what the minimum user equipment requirements are;

OP Online Couse User soft and hardware requirements: Operation system: Windows 8.1+, Mac OSX 10.13+, Processor: 1,8GHZ dual core min, 2GHz dual core recommended, RAM 2 GM min, 4 GB recommended, Disc Space 5GB min., display resolution min 1366x768.

-Availability OP Online Couse: 24/7/365

-Reliability OP online Course: 85%. It means that the course has 85% probability that the course system will not have any failures per month.

-Maintainability OP online course: 75%. It means that the course has 75 percent probability that the failures will be fixed during 24 hours.

-Usability requirements address the problems of difficulty/simplicity of using the product.

OP online course min usability requirements: 1) Support all functions to be performed by Mouse and Keyboard. 2) All visual information can be seen by colour blinded people.

-Scalability OP Online course: 1) should allow scalability up to 500 active users simultaneously. 2) Learning repository storage should allow 5 years learning experience data storage.

3.5 Project Exclusions

Project exclusions are explained by Kohrel (2013) as anything that goes beyond the project boundaries and in terms of the project planning and customer relations it could be any possible stakeholder expectations that are not included in the project scope.  It is also noted by Boogaard (2020) that it is important for the project success to stipulate what is not included to avoid any future misunderstanding between the stakeholders and project managers.

The following exclusions are considered for current project:

- The project does not include developing the mobile application and include only the web version for desktop computers.

- The costs and purchasing of any software licensing required for the online course functioning are not included in the project scope and the budget.

- The project does not include purchasing and costs for online learning depository storage capacity and regular content storage costs.

- The project does not include developing the Veterinary nursing course materials.

3.6 Project Limitations

The project limitations are defined by Boogaard (2020) as any limiting factors or boundaries that can have effect and slow down the project and the project team has to work within; These limits can come from the areas or budget, time and resources, including the human resources and pre defining the limitations can help to have understanding what factors may constrain the project completion.

The following limitations are considered for current project:

-The OP Online course will be based on and integrated with the Moodle learning management services capabilities and the course functionality may be limited by the Moodle software capabilities.

- Based on the fact the Moodle LMS is free open code software and has potential higher risk to be affected by the hackers and viruses/malware developers it can limit the project’s developers team efforts to provide efficient security defence.

- The author of this project plan does not have practical online software development experience result of the project planning is limited with the information obtained from open academic sources.

-There is no information in the case study about the project timeframe and planned project start date and required finish dates, therefore the planning was done without considering the holiday periods, while the holiday periods may have considerable effect on the project completion time and cost.

-The project is limited with the human resources available in New Zealand due to the border restrictions and have constrains to hire required specialists from overseas.

4. Project Assumptions

Project assumptions are considered by Kohrel (2013) as the elements on the planning that are just believed to be true. Boogaard (2020) explains the assumptions as the project factors that are just considered to be real and definite and considered to become true without having real practical confirmation or proof. The assumptions are important element that the adds clarity to the project planning, however the future is unpredictable and in case the assumption proves to be false it turns to become a risk for the project, therefore it is important to define the assumptions and consider them in identifying the risks and minimising possible impacts on the project results (Boogaard, 2020).

The following assumptions are considered for current project:

-The project plan is done on the assumption that OP will contract the professional software development company and the project plan is created from the software development company view.

-It is assumed the OP will provide the Online veterinary simulation course materials with documented requirements prior to the beginning of the project.

-The plan and the budgeting are created on the assumption that the software development company has in their possession all equipment and software required for developing software product and ensuring uninterrupted work by their employees, therefore the budgeting is considering the human resources costs only as main costs of the software project.

-The project planning and budgeting is done assuming the software development company has the teams of required specialists employed permanently and full time, therefore there is no need to hire new IT specialists at the beginning of the project.

-The project budgeting assuming the employees’ pay level to stay constant during the project period and does not consider any employees pay raises.

- The planning assumes that the course will be based and integrated with Moodle LMS and OP has all valid licences and registrations to use Moodle LMS, MS 365 suite and MS Teams suite, MS SQL Server.

- The project planning is done on the assumption that project team representative may represent OP communicating with stakeholders like NZQA and Maori Council proving and presenting information about the simulation course, however obtaining final documented approvals of the course content is the OP responsibility.

-The project scheduling is based on the assumption of the project team and OP representatives are available working during normal 40 hour week from Monday to Friday and do not consider possible holidays and breaks or work overtime.

5. Methodology

The methodology chosen for OP online Veterinary nursing course project is Scrum. It is proven to be efficient agile framework to work with complex problems and combining possibility to create the software products of the highest value and ensuring high level of project team creativity and productivity (Scrum.org, 2021). Scrum supports agile values and provides the process control through the strict following of simple sets of practices and rules with specific Scrum Events, Artifacts and Roles (Zenkit, 2018). The heart of Scum is in iteration called Sprint, which is a fixed time iteration comprising full software development cycle process resulting in the pieces of done product functionality and all the workflow is built around sprints with fixed scum sprint events (planning, review, retrospective) and a daily scrum that allow to adjust the planning according to the changes in the process or requirements (Schwaber, 2004).

All the project requirements prioritised for work are presented in the Product Backlog and the requirements from Product backlog are transferred into the Sprint’s backlog for the sprit planning in the form of tasks for performing (Zenkit, 2018). There is no project manager in Scrum and there are only three roles of Product Owner, Scrum Master, and Team member where all managerial responsibilities are split between them (Schwaber, 2004).  The Product Backlog and all the stakeholders relations are managed by the Product Owner who provides the direction for other project members what needs to be created, while how to develop the software product and what exactly to do the team decide themselves (West, 2018). The Scrum Master is responsible for felicitating the Scrum process to flow and making sure all impediments for team work are removed (West, 2018).

5.1 Justification

There are several reasons why Scrum was chosen for OP Veterinary course online simulations game project. It is noticed from Otago Polytechnic (2021) that delivering high quality educational products is the top priority for OP. Scrum meets that requirement as efficient agile framework for creating the software products of the highest value and ensuring high level of project team creativity and productivity (Scrum.org, 2021). There are multiple stakeholders involved in this OP project like Otago Polytechnic lecturers, administration, Nursing course team leader and head of veterinary department, students, NZQA and Maori stakeholders who create the requirement for the use of methodology suitable for considering multiple stakeholder expectations. Having Product Owner as a special role working as stakeholder representative and making sure all stakeholder requirements are translated to the team with the software product that meets the stakeholder expectations delivered makes Scrum the stakeholder focused methodology (Schwaber, 2004).  Thus, it meets the OP project requirements to consider multiple stakeholder expectations.

It can be seen from the cases study that OP online simulation nursing course can be considered to be a complex software product with multiple functions and complex structure with requirements for simulations of all parts of veterinary nursing process applicable to different types of animals. Moreover, it has the requirements for communication suit and the learning history to be built in the product. In addition, according to OP Vet Nursing (2021) the programme consist of eight different courses and creating the simulations for them requires creative approach and design work. Scrum is focused on developing complex software products were design and creativity are important (Scrum.org, 2021). Thus, it is considered to be the nest to suit the OP project requirements.

It is revealed by West (2018) that very often the customers can not realise what they exactly want from the software product until they see it and try to use it, while Scrum delivering the pieces of working, tested and maintainable product at the end of the sprint helps to solve that problem. This Scrum attribute is considered very valuable to OP project as OP team and students can see working parts of the course and simulation game early. Moreover Scrum allows producing different releases starting from minimum viable product so OP team and students can start using for product form the first course and provide the feedback that can be considered in the next releases and the next Veterinary Nursing programme parts.

6. Project Risks and Risk Management Plan

A Project risk is explained by Carnone and Tippett (2004) as a probable event or situation that, if happens in the future, has some impact on the project objectives and more often it has negative effect. The risk probability cannot be measured on scale and subjective judgement is used to estimate the probability with the term of likelihood. The project risk has attributes of likelihood and impact where the impact estimated value multiplied by likelihood value creates the risk score that shows the importance of the risk for the project results and the risks with the higher scores need to be addressed first and have more attention to be paid (Carbone & Tippett, 2004).

The following project risks with the likelihood and impact values scaled from min.1 to max. 5 and mitigation actions that are considered for current project are listed in the table below:

| Risk | Likelihood | Impact | Risk Score | Mitigation actions |
| --- | --- | --- | --- | --- |
| Employees leave the company for better job opportunity due to very high demand and skill shortage of IT specialists in NZ | High 5 | High 5 | High 25 | 1)Subcontract employees or functional team from the other software development companies. 2) Outsource the development activities to other software development company 3) Check if other team members are able to cover the missing employee before his replacement. |
| Employees ask for pay rise during the project due to average salary increase on IT market | Medium 3 | Low 2 | Low 6 | 1)Discuss with OP in advance possibility of pay rises due to current IT market 2) Discuss the budget increase with OP |
| Delay in approval of simulation source content, game characters and Guide to Maori/Iwi practices page | Medium 3 | Medium 3 | Medium 9 | 1)Switch to designing and developing other software functionality and course parts while waiting the approval. 2)Continue development as planned and then make corrections later according to authorities instructions |
| New lockdown or increase in alert levels with restrictions on personal communication and travel | High 5 | Low 2 | Medium 10 | 1)Check and test the remote work possibilities for all employees in advance before the project start. 2) Make sure all employees have required equipment and online access to work remotely |
| OP does not have all software licenses or they are expiring soon, and/or OP IT infrastructure cannot support new online course. | Low 2 | High 4 | Medium 8 | 1)Check the OP IT infrastructure and all software licensees and availability with OP in advance. 2)Test OP IT infrastructure at early stage of designing and perform upgrade where necessary |

7. Project Organisation

It is explained by Hughes (2019) that Project Organisation describes the project human infrastructure and determines the project roles and responsibilities of each project member that helps to improve coordination between the employees and completion of the project’s activities.

The work process, decision making and employees’ responsibilities that are important for the project success are defined by project organisation and at the project planning it is important to create the structure where any overlaps, conflict possibilities or lack of capabilities are minimised and employees know what are expectations of them and what they can and need to do (Hughes, 2019).

For understanding the Scrum project organisation is it claimed that all parties are divided on the people directly involved and working in the Scrum Project and people who are interested in the project and who may be only the spectators. The spectators or interested people like any company managers, sponsor, clients, and stakeholder’s representatives do not have direct authority for the project work. The managerial responsibilities are shared between the Scrum Master, Products Owner and the Team, who are the one directly involved in the project execution (Schwaber, 2004).  There is no project manager in Scrum project and this position is filled with Scrum Master, however Scrum master is responsible to manage only the Scrum Process and make sure that everyone strictly follows the Scrum rules and make sure the team is left alone and focused and doing its work. Product owner communicating with stakeholders responsible for delivering the value and with prioritising the product backlog gives the direction for the team what needs be done. The major difference of Scrum frrm other practices that the team is self-manageable and responsible for managing the development process and the team selecting and planning the fork in each Sprint (Schwaber, 2004).

For the OP Veterinary nursing simulation game project, in terms of reporting the results and value creating chain it can be accepted that the Team reports to Scrum Master, Scum Master to the Product Owner and Product Owner to the OP.

The OP project human infrastructure with Scrum process application can be seen in the below table.

| Name | Functional Role | Scrum Role | Responsibilities | Reporting |
| --- | --- | --- | --- | --- |
| Olga Suvorova | Product Owner | Product Owner | Define and Prioritise Product backlog, Stakeholder relationships, Ensures that the most value delivered for OP as early as possible. | OP |
| Ken Schwaber | Scrum Master | Scrum Master | Facilitating Scrum process, ensures everyone follows Scrum rules, ensures the team can work without impediments | Product Owner |
| Albina Petrova | Business Analyst | Team | Designs feature. Defines features and product functionality, document detailed requirements from stakeholders’ requirements provided by Product owner | Scrum Master |
| Bliss NG | UX/UI Designer 1 | Team | Designs usability. Defines and maintains the usability of the interface | Scrum Master |
| Pablo Picasso | UI/UX Designer 2 | Team | Design the interface. Creates the look and feel of the interface | Scrum Master |
| Tove Jansson | Animation Designer | Team | Created images, visual effects, animation for the simulation game | Scrum Master |
| Findus | QA Analyst 1 | Team | Tests the software product and validates that the quality is adequate | Scrum Master |
| Petson | QA Analyst 2 | Team | Tests the software product and validates that the quality is adequate | Scrum Master |
| Jagdeep Singh | Developer1 | Team | Builds the software product ( coding) and performs unit testing for quality | Scrum Master |
| Ivan | Developer2 | Team | Builds the software product ( coding) and performs unit testing for quality | Scrum Master |
| Elena | Developer3 | Team | Builds the software product ( coding) and performs unit testing for quality | Scrum Master |
| Manaia Mahuta | Maori interpreter | Team | Translation and checking all information on Te Reo in the Maori pages and course | Scrum Master |
| Grant Tomson | OP Vet Nursing Lecturer |  |  | OP |
| Warren Buffet | OP Head of Veterinary department |  | Main external Stakeholders | OP |
| Mary Cooper | OP Veterinary Nursing Program Leader |  |  | OP |
| Chris Hopkins | OP Student Rep |  |  | OP |

8. Communications with Stakeholders

8.1 Stakeholders identification.

The stakeholders are defined by Ranangen (2017) as the groups of people or just individuals who can have the influence and can create the impact on the company as well as be affected by the activities directed for achieving project objectives. The project operation requires communication and collaboration with wide range of stakeholders and it is very important for successful project operation to identify the external and internal stakeholders who can have significant effect on the project activities and have the communication planning (Ranangen, 2017).

There are multiple external stakeholders involved in this OP project like Otago Polytechnic veterinary nursing lecturers, administration, nursing course team leader and head of veterinary department, students, NZQA and Maori Council. Internal project stakeholders are presented by Product Owner, Scrum Master and Team.

8.2 Communication plan

The major communication channel in Scrum project is the set of regular Scrum meetings like sprint planning, sprint review, sprint retrospective, daily scrum that make the process of stakeholders’ communications structured and transparent (Schwaber, 2004).

The communication plan for OP online Veterinary nursing simulation course based on the Scrum structure can be seen below.

| Stakeholders | Communication channel | Frequency and dates | Purpose |
| --- | --- | --- | --- |
| OP Representatives, Product Owner (PO), Scum Master (SM) | Meeting face to face | Once, at foundation phase. Planned date 07/09/21. | Discuss and document OP expectations and requirement to the project. |
| OP Representatives, Product owner, Business analyst | Meetings , face to face, via MS Teams, email , telephone | Foundation phase, planned dates 8-9/09/21 | Collect user stories, detailed clarification of user requirements, detailed documenting requirements |
| OP Representatives, Product owner | Email communication, telephone | On demand, starting from 14/09/21 | Agreements, approvals, product requirements clarification, change requests invoicing and invoices approvals |
| Product Owner, Scum Master and Team | Meeting , face to face | Foundation phase, planned date 13/09/21 | PO presents Product backlog to team, break down of all requirements by sprints, make the sprints planning, estimate number of sprints for project. |
| Product Owner, Scum Master and Team | Sprint planning meeting face to face | Every 2 weeks, beginning of every sprint. Planned dates: sprint1 20/09/21, sprint2 04/10/21 sprint3 18/10/21 sprint4 01/11/21 sprint5 15/11/21 sprint6 29/11/21 Duration 4 hours | PO Presents next in priority requirements, team choose requirements and make tasks planning for sprint, create sprint backlog, PO presents to team and SM any change requests. |
| Scum Master and Team | Daily Scrum meeting face to face or via MS Teams | Every working day morning, beginning of the day, duration 15 min. | Synchronize work of all team members, check and discuss wat was done previous day, planning of work for the day, discuss any impediments to work progress |
| OP Representatives, Product Owner, Scum Master and Team | Sprint Review meeting face to face, and/or via MS Teams | Every 2 weeks, end of every sprint. Planned dates: sprint1 01/10/21, sprint2 15/10/21 sprint3 29/10/21 sprint4 12/11/21 sprint5 26/11/21 sprint6 10/12/21 Duration 4 hours | Team presents to OP stakeholders and PO what was developed and the results of sprint work. Receive from OP reps feedback, proposals or new requirements what needs to be done. |
| Product owner and Scum Master | Email communication, telephone, chats, face to face | On demand, starting from beginning of project | Discuss work progress, approvals, product requirements clarification, change requests. |
| Product Owner, Scum Master and Team | Sprint Retrospective meeting face to face, and/or via MS Teams | Every 2 weeks, end of every sprint after sprint review. Planned dates: sprint1 01/10/21, sprint2 15/10/21 sprint3 29/10/21 sprint4 12/11/21 sprint5 26/11/21 sprint6 10/12/21 Duration 3 hours | Analyse sprint results, revise process to make it efficient and enjoyable. |
| OP Representatives, Product Owner, Scum Master and Team | Sprint Review meeting face to face, and/or via MS Teams | Every 2 weeks, end of every sprint. Planned dates: sprint1 01/10/21, sprint2 15/10/21 sprint3 29/10/21 sprint4 12/11/21 sprint5 26/11/21 sprint6 10/12/21 Duration 4 hours | Team presents to OP stakeholders and PO what was developed and the results of sprint work. Receive from OP reps feedback, proposals or new requirements what needs to be done. |
| OP Representatives, NZQA rep, Maori Council rep, Product Owner, | Presentations, face to face, or/and via MS Teams | Planned dates 11-12/10/21 | Presentations of simulation game characters and example of game and Maori page content. To receive feedback and approval from all external stakeholders. |
| OP Representatives including OP Student reps, Product Owner | Meeting face to face, or/and MS Teams | Twice during sprint 3, Planned dates 21/10/21 and 28/10/21 | Practical testing of Cource1 beta version with students ad lecturers, Online training of OP employees using Course1 |
| OP Representatives including OP IT reps, Product owner, Business Analyst, Dev1, QA1 | face to face, via MS Teams, email , telephone | At the foundation phase, planned dates 08-13/09/21 And during closure phase, planned dates 13-15/12/21 | Check existing OP IT infrastructure and software; collect systems access info for development. Handover software code, documentation |
| OP Representatives, Product Owner , Scum Master | Meeting face to face | Closure phase, planned date 13/12/21 | Final product reviews to unsure all deliverables are met. |

9. Change management plan

It is explained by Highsmith and Cockburn (2001) that the projects often have clear vision and objectives, however specific requirements may be evolving in time as the clients and developers are exploring unknown and creating new products, thus the  changes appearing on the way require responding to change and keeping the project vision and objectives in place. Software development projects are known to have high levels of complexity and changing requirements, so agile methodologies empirical approach welcoming change and helps to manage changes efficiently (Highsmith & Cockburn, 2001). Application of Scrum processes allows managing high level of complexity and changes, and turning the chaotic changes to the order while keeping the efficient developing process (Schwaber, 2004).  With the vision to develop high quality product for Otago Polytechnic and possible high number of change requests from the stakeholders the requests will need to go through the Scrum process.

The requests and proposals related to the process and current sprint development that are coming from the development team are discussed by the team on a daily scrum and if they do not require any change in the scope can be implemented immediately. All change requests from all stakeholders need to go through the following process:

1) Receiving Change request.

The Change request from all OP project stakeholders needs to be sent in written form to the Product Owner and Product Owner registers it.

2) Evaluation and approval.

The Product Owner is the person responsible for approval of change request and placing it into Product backlog.  The Products Owner with Scrum Master will assess the effect of the requested change on the project. The requests that are below the change tolerance level for the project will be considered small, then approved by Product Owner and placed to Product Backlog. The change tolerance level shows the effect on changing the budget, time, deliverables, and will need to be set up in special agreement between the software Development Company and OP. This level is shows the effect on changing the budget, time, deliverables and recommended to be not more than 10 percent. If the estimated impact is more them the change tolerance level the Product Owner will send to OP stakeholders the report with estimated consequences and changes to the budget, time and other important parameters. If OP stakeholders do not approve additional consequences caused by the propose change then the change request is considered to be refused. However, if OP stakeholders approve the change consequences the change request returns back to the Product Owner, who makes corrections to the budget and planning and place the change requirements to the Products backlog

3) Implementation

During the next Sprint planning meeting the Team can pick the new change requirements form the Product Backlog and choose it for the implementation in the next sprint or the following sprints. The Product Owner can not interfere in the development process during the current Sprint and request to implement the change request immediately. The change requirements can be picked up only by the Team and on the Sprint planning meeting. The Scrum Master is responsible to control that this process is followed by all project members. This procedure will help to avoid chaos and distraction of development team from current sprint tasks.

10. Budget

A project budget is the total projected costs needed to complete a project over a defined period of time. It’s used to estimate what the costs of the project will be for every phase of the project. Creating a project budget is a critical part of the project planning process. The project budget will include such things as labor costs, material procurement costs and operating costs. But it’s not a static document. Your project budget will be reviewed and revived throughout the project, hopefully with the help of project budgeting software (Bridges, 2023b).

The cost is named by Kwon and Kang (2019) as a critical parameter for the project success and requires accurate planning. For the project planning purposes it is required to create the projects’ budget that shows the estimate of funds that are expected to be required to completed the project and the budgets are based on expected resources costs (Kwon & Kang, 2019).  The top-down or analogous estimate can be used by managers to obtain rough estimate of the project costs based on the costs of previous similar projects when it is required to provide  rough project budget to the sponsors (Goodrich, 2015). In software development with Scrum the manager can use the parameter of average cost of Scrum team per sprint and after estimation on required number for sprints can make the rough estimate for the project cost for all sprints (Dolfing, 2015). Bottom-up parametric estimating that calculates the detailed costs per unit of each activity and the time required for completion each activity considered to be more accurate technique (Goodrich, 2015).  Therefore, bottom-up parametric estimating and will be applied for the OP online Veterinary nursing simulation course project.

The budgeting for OP online Veterinary nursing simulation course project is created on the assumption that the software development company has in their possession all equipment and software required for developing software product and ensuring uninterrupted work by their employees, therefore for the planning purposes the budgeting is considering the human resources costs only as main costs of the software project. In the Scrum project the Product Owner is responsible for budgeting as the person responsible for prioritising the product backlog, deliverables and allocating the resources (Dolfing, 2015).

The pay rates for the team employees were estimated based on the information sourced from SEEK (2021) as the source of most recent information what the employers are ready to offer for IT specialists in current market situation. The average annual salary from ten most recent job advertisements with the pay range per occupation was divided by standard 52 working weeks per year and 40 hours per week to calculate the hourly rate.

The Work Breakdown Structure for the OP project created in MS Project was utilised for the bottom up cost estimate. In the MS Project, the required human resources and time required to complete each activity were assigned to each activity. For each activity the cost of employee per hour was multiplied by the number if required hours and the costs of all employees involved in the activity were summarised in order to receive the human resource cost per activity. Then the costs of all activities per the project phase were summarised in order to receive the phase activity cost. The project phases for the budgeting were identified as foundation, closure and 6 sprints. The information with hourly pay rates for the employees involved in the project and the project’s budget with the costs per phase and total project cost estimate can be seen in two tables below.

Human resource pay rate per hour table:

| ID | Role | Group | Standard Pay Rate |
| --- | --- | --- | --- |
| 1 | Product Owner | Product | $70.00/h |
| 2 | Scrum Master | Scrum Master | $70.00/h |
| 3 | Business Analyst | Team | $65.00/h |
| 4 | UX/UI Designer 1 | Team | $55.00/h |
| 5 | UI/UX Designer 2 | Team | $55.00/h |
| 6 | Animation Designer | Team | $55.00/h |
| 7 | QA Analyst 1 | Team | $55.00/h |
| 8 | QA Analyst 2 | Team | $55.00/h |
| 9 | Developer1 | Team | $65.00/h |
| 10 | Developer2 | Team | $65.00/h |
| 11 | Developer3 | Team | $65.00/h |
| 12 | OP Lecturer | OP | $0.00/h |
| 13 | OP HOD | OP | $0.00/h |
| 14 | OP Program Leader | OP | $0.00/h |
| 15 | OP Student Rep | OP | $0.00/h |
| 16 | Maori interpreter | External | $45.00/h |

The OP project Budget table:

| Phase | Date to complete | Estimated Cost, NZD |
| --- | --- | --- |
| Foundation | 17 September 2021 | $14,720.00 |
| Sprint 1: Homepage with login, navigation, security, and database -Done | 1 October 2021 | $17,740.20 |
| Sprint 2: Game page, online repository page, Maori/Iwi page, Game characters - Done | 15 October 2021 | $19,010.00 |
| Sprint 3: Release 1 -of Veterinary nursing simulation game with Couse1 | 29 October 2021 | $19,204.80 |
| Sprint 4: Release 2 -of Veterinary nursing simulation game Courses 1-4 | 12 November 2021 | $22,017.80 |
| Sprint 5: Release 3 -of Veterinary nursing simulation game Courses 1-6 | 26 November 2021 | $20,681.40 |
| Sprint 6: Final Release 4 -of Veterinary nursing simulation game Courses 1-8 | 10 December 2021 | $19,037.40 |
| Closure | 16 December 2021 | $2,380.00 |
| Total Cost for Project: |  | $134,791.60 |

11. Quality Control and Audit

- Quality Control

Quality control (QC) is a process through which a business seeks to ensure that product quality is maintained or improved. QC requires the company to create an environment where management and employees strive for perfection. This is done by training personnel, creating benchmarks for product quality, and testing products to check for statistically significant variations (Hayes, 2024).

QC in Scrum, on the other hand, centres around detection-focused activities. It involves verifying that the deliverables meet the predefined standards and requirements. QC activities occur at various stages of the development process, with the primary goal of identifying and fixing defects. Here are some key aspects of QC in Scrum (Hartnack, 2023):

- Testing and validation - QC encompasses various testing practices, including functional testing, integration testing, regression testing, and user acceptance testing. These tests are designed to verify that the product meets the desired functionality and quality standards.

- Defect identification and management - QC involves actively searching for defects, tracking them, and collaborating with the development team to resolve issues promptly.

- Review processes - Peer reviews, code reviews, and design reviews are part of QC efforts to ensure that the developed product aligns with the established quality criteria.

External control is more nuanced and evidenced in the activities that relate to the external environment that have an impact on risk management and control implementation within an organization. An example of external control would be an activity taken by an external entity to promote control effectiveness within an organization.  Basically, the decision an external entity makes would impact an organization (Edwards, 2023). In the case of OPAIC-VR LMS, as part of pre-production preparation for deployment to production, external entities such as NZQA(Barker, 2018) and Maori Council will do external control to check for quality and that it complies with school’s standards.

- Audit

The audit is designed to determine the status of work performed on a project to ensure it complies with the statement of work, such as the scope, time and budget of the project, along with the maturity of the project management process. During audit the project scope, schedule, quality, cost, resources, and risks are checked to make sure it is still following the project plan (Bridges, 2023a). However in agile teams, the process sometimes deviates to address certain issues, which is expected as stated in the Agile Manifesto, “Individuals and interactions over processes and tools” (Beck et al., 2001). The auditor should communicate with Product Owner and Scrum master to ensure that agile practices were followed (Nair, 2019). In OPAIC-VR LMS, the auditor should check the artifacts created during sprint planning, review and retrospective, as well as product backlogs.

12. Project Closure

Agile project closure is a pivotal phase that ensures the project concludes smoothly while capturing valuable insights for future endeavors. Unlike traditional methodologies, Agile project closure is iterative and aligned with the Agile principles (Sengupta, 2023). To ensure the successful transfer of ownership from the Agile team to the operations team, the following items below are done to make sure we tie up any loose ends (Cosgrove & Hubbard, 2020).

- The scrum boards(Jira) should be archived, and documentation should be organized.

- Meetings with the operations team to walk them through the current project status, any key user stories in the backlog, and how all the information is organized. This is where the Agile team conducts knowledge sharing for the operations team to have a feel of how the systems works end to end. This is also where the needed access controls are given to the operations team. In OPAIC-VR LMS’s case, knowledge sharing is conducted with the OP IT department to discuss how OPAIC-VR LMS operates.

- The project is handed from the Agile team to the operations team. This is where project resources such as artifacts, source code repositories are given to the operations team. In OPAIC-VR LMS, the user training manual is also handed to the operations team.

- The final review of the project should include a meeting with the stakeholders to review the final scope that was complete, the budget, and the schedule.

- A final retrospective should be completed as a team to document on lessons learned, identify process improvements.

13. References:

Althiyabi, T., & Qureshi, R. (2021). Predefined project scope changes and its causes for project success. International Journal of Software Engineering & Applications (IJSEA), 12(2/3).

Barker, A. (2018). The work of the New Zealand Qualifications Authority. In International developments in assuring quality in higher education (pp. 82–89). Routledge.

Beck, K., Cohn, M., Jeffries, R., Anderson, D., Beedle, M., Boehm, B., Combemale, B., Highsmith, J., Hunt, A., Kern, P., Larman, C., Martin, R., Mellor, S., Schwaber, K., Sutherland, J., & Thomas, D. (2001). The Agile Manifesto. Agile Alliance. http://agilemanifesto.org/

Bridges, J. (2023a). How to Do a Project Audit: A Quick Guide. ProjectManager.Com. https://www.projectmanager.com/training/project-management-audit

Bridges, J. (2023b). How to Make a Project Budget: Project Budgeting Basics (Templates Included). ProjectManager.Com. https://www.projectmanager.com/training/create-and-manage-project-budget

Cosgrove, E., & Hubbard, K. (2020). Agile closing out project. Action Engineering Blog. https://www.action-engineering.com/blog/agile-closing-out-project/

Edwards, J. (2023). A Basic Overview of Internal and External Controls. LinkedIn. https://www.linkedin.com/pulse/basic-overview-internal-external-controls-dr-jeffrey

Hartnack, T. (2023). Quality Assurance vs. Quality Control in Scrum. LinkedIn. https://www.linkedin.com/pulse/quality-assurance-vs-control-scrum-tim-hartnack#:~:text=Quality%20Control%20(QC)%20in%20Scrum&text=It%20involves%20verifying%20that%20the,of%20identifying%20and%20fixing%20defects.

Hayes, A. (2024). Quality Control: What It Is, How It Works, and QC Careers. Investopedia. https://www.investopedia.com/terms/q/quality-control.asp

Nair, B. (2019). Auditing Agile Projects & Agile Auditing- A primer. LinkedIn. https://www.linkedin.com/pulse/auditing-agile-projects-auditing-primer-biju-nair

Sengupta, S. (2023). Project closure strategy for agile project. Medium. https://medium.com/@mailme.senguptasudipta/project-closure-strategy-for-agile-project-0744c8440a86

HR Manager - $58 per hour

https://www.glassdoor.co.nz/job-listing/hr-manager-foster-moore-JV_IC3525162_KO0,10_KE11,23.htm?jl=1009673518619&cs=1_ec9b4ff3&s=58&t=SR&pos=102&src=GD_JOB_AD&guid=00000195b27bb2459b30eef8ec034985&jobListingId=1009673518619&ea=1&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp7nckhgqnl800-1d963c8dbd503581&cb=1742456206940&ctt=1742456254121

Engineering Manager – 53$ per hour

https://www.glassdoor.co.nz/job-listing/ict-project-manager-techwise-solutions-JV_IC3525162_KO0,19_KE20,38.htm?jl=1009652037968&cs=1_b6da3e24&s=58&t=SR&pos=104&src=GD_JOB_AD&guid=00000195b27ff695b5f85de7264cd50c&jobListingId=1009652037968&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp7vtnigoog804-582d7553ed486054&cb=1742456485931&ctt=1742456494351

Senior Platforms Engineer - $56 per hour

https://www.glassdoor.co.nz/job-listing/senior-devops-engineer-fiserv-JV_IC3525162_KO0,22_KE23,29.htm?jl=1009678594918&cs=1_74fa5c4f&s=58&t=SR&pos=102&src=GD_JOB_AD&guid=00000195b28109a394510563b18d3c45&jobListingId=1009678594918&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp822fq2afp000-bb82b31d9c399180&cb=1742456556303&ctt=1742456627109

Risk Management Specialist – $28 per hour

https://www.glassdoor.co.nz/job-listing/product-development-specialist-hub-services-iag-new-zealand-JV_IC3525162_KO0,43_KE44,59.htm?jl=1009662255445&cs=1_4ef51041&s=58&t=SR&pos=102&src=GD_JOB_AD&guid=00000195b283066fa760d46250f5cb8e&jobListingId=1009662255445&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp861lui0ht800-3a847457d00276f3&cb=1742456686571&ctt=1742456707752

Cultural Consultant - $42 per hour

https://www.glassdoor.co.nz/job-listing/work-winning-consultant-aurecon-group-JV_IC3525162_KO0,23_KE24,37.htm?jl=1009561005629&cs=1_448e59b4&s=58&t=SR&pos=101&src=GD_JOB_AD&guid=00000195b285d69893ad4e1c0af95b38&jobListingId=1009561005629&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp8blnd222o000-75b1809a532fc97c&cb=1742456870868&ctt=1742456884958

Senior Product Owner - $52 per hour

https://www.glassdoor.co.nz/job-listing/product-owner-data-ai-products-asurequality-JV_IC3525162_KO0,30_KE31,43.htm?jl=1009672349495&cs=1_08ef0467&s=58&t=SR&pos=104&src=GD_JOB_AD&guid=00000195b28b54b9befd8a203fdf0cc2&jobListingId=1009672349495&ea=1&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp8ml8ajdr1800-79507115f3c44640&cb=1742457230884&ctt=1742457239278

Senior VR Developer - $50 per hour

https://www.seek.co.nz/job/82471580?type=promoted&ref=search-standalone&origin=cardTitle#sol=077b2a7917309a47ff35c3d0496275e95285e244

Intermediate Full Stack Software Engineer - $42 per hour

https://www.seek.co.nz/job/82849836?type=standard&ref=search-standalone&origin=cardTitle#sol=53a3ba07959345fb41a290d083913c4e82117932

Associate Full Stack Software Engineer – $32 per hour

https://www.glassdoor.co.nz/Salary/Aderant-Associate-Software-Engineer-Salaries-E37370_D_KO8,35.htm

Senior QA Engineer - $37 per hour

https://www.glassdoor.co.nz/job-listing/senior-qa-engineer-payment-product-binance-JV_IC3525162_KO0,34_KE35,42.htm?jl=1009335940342&src=GD_JOB_AD&uido=65FC4472BDEC32AAD12883C19DB458B2&ao=1136043&jrtk=5-pdx1-0-1impacp24gqnl800-2c32325891c848b1&cs=1_12244bb7&s=58&t=SR&pos=102&guid=00000195b2a663e695acf38a3d7b45b8&jobListingId=1009335940342&ea=1&vt=w&cb=1742459004143&ctt=1742459011545

Senior VR Designer/Content Developer - $37 per hour

https://www.glassdoor.co.nz/job-listing/game-director-lead-game-designer-tencent-JV_IC3525162_KO0,32_KE33,40.htm?jl=1009649781596&cs=1_3e9eaa24&s=343&t=SR-JOBS-HR&pos=102&src=GD_JOB_AD&guid=00000195b2a948ee89ebfea76a296686&uido=65FC4472BDEC32AAD12883C19DB458B2&jobListingId=1009649781596&ao=1136043&vt=w&jrtk=5-pdx1-0-1impaij15gqmt800-af997ef44ac85d47&cb=1742459194620&ctt=1742459202771

Trainer - $38 per hour

https://www.seek.co.nz/job/82815772?type=standard&ref=search-standalone&origin=cardTitle#sol=84016d139461aca38e6d722bb3f7f84abd331b3e

Developer Intern - $25 per hour

https://www.sjs.co.nz/job-details/21526/mechatronics-rnd-engineer-intern-casualpartfull-time-cbd/

Laptops - $1300 x 20 = $26000

https://www.dell.com/en-nz/shop/dell-laptops/inspiron-15-laptop/spd/inspiron-15-3520-laptop/oin3520100901mnzh?ref=variantstack

VR hardware - $650 x 12 = $7800

https://www.pbtech.co.nz/product/MVRMTA0024/META-Quest-3s-128GB-Mixed-Reality-Headset-with-2x?qr=GShopping&gad_source=1&gclid=Cj0KCQjw-e6-BhDmARIsAOxxlxVaWUoXJIuyEoiQJ3eRXoX368WtnsJzZHLHL6e3mIZI5g8FZ-UVGZwaAntYEALw_wcB

Azure Subscription - $432 per month

https://azure.microsoft.com/en-us/pricing/calculator/?ef_id=_k_Cj0KCQjw-e6-BhDmARIsAOxxlxX14GT6Xgk_PIpmy9nZve2RbTFsrkhuQPFPnsWSuwNOKvzvVE6FhBAaAhw8EALw_wcB_k_&OCID=AIDcmmp3m06wb2_SEM__k_Cj0KCQjw-e6-BhDmARIsAOxxlxX14GT6Xgk_PIpmy9nZve2RbTFsrkhuQPFPnsWSuwNOKvzvVE6FhBAaAhw8EALw_wcB_k_&gad_source=1&gclid=Cj0KCQjw-e6-BhDmARIsAOxxlxX14GT6Xgk_PIpmy9nZve2RbTFsrkhuQPFPnsWSuwNOKvzvVE6FhBAaAhw8EALw_wcB

VR Software Licenses - $10000 one time

https://clutch.co/developers/virtual-reality/pricing

Github - $4 x 20 = $80 per month

https://github.com/pricing

Jira - $8.6 x 20 = $172 per month