AM804001: Project Management

Assessment 2: Case Study – Project Management Plan

| Study block 1 |  | 2023 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Date issued |  |  |  |  |  |  |  |  |
| Due date |  |  |  |  | Time |  |  |  |
| Delivery: |  | Submit to Turnitin via Moodle before deadline |  |  |  |  |  |  |
| Weighting |  | 70% |  |  |  |  |  |  |
| Marks out of |  | 100 |  |  |  |  |  |  |
| Instructions |  | Complete this cover sheet and attach to you your assignment. - This assignment must be your own work. - Collusion, copying or plagiarism may result in disciplinary action. - We advise that you keep a copy of this assignment. - Word limit is 3000-3500 words Refer to following website for reference related resources: http://www.cite.auckland.ac.nz/index.php?p=quickcite |  |  |  |  |  |  |
|  |  | We confirm that: This is an original assessment and is entirely my own work. Where ideas, tables, diagrams etc. of other writers have been used, we have acknowledged the source in every case. This assignment has not been, nor will be, submitted as assessed work for any other academic course. |  |  |  |  |  |  |
| Student’s Name |  |  | ID No |  |  | Signature |  |  |
| Date |  |  |  | Cohort Number |  |  |  |  |

Table of Contents

Executive Summary	2

## Executive Summary

| Project name | OP Virtual Reality Learning Platform for Healthcare Training (OP-MedVR) |
| --- | --- |
| Project Type | Software product development – Healthcare Virtual Reality Learning Platform |
| Project Goals | Develop VR platform that simulates real-world healthcare scenarios such as patient diagnosis and emergency response within virtual hospital environment. Implement multi-user capabilities and feedback system to allow lecturers to assess student performance during simulations. Create user training and support for student and lecturers on how to use OP-MedVR. |
| Project Deliverables | Tangible deliverables: -VR homepage and navigation integrated within OP LMS. -Single-sign on using existing student and lecturer accounts. -Multiplayer mode for students and observer mode for lecturers. -Role-playing scenarios for students. -User training manual on how to use OP MedVR. -Feedback feature for lecturers. -User training for students and lecturers. -Maori values and design integration into homepage and VR. -VR Hospital Rooms: -Emergency Room -Intensive Care Unit -Medical Ward -Operating Room -Maternity Care -Behavioural and Mental Room -Family Room -Neonatal Intensive Care Unit -Github repository of source code -Jira artifacts Intangible deliverables: -Good User Experience for students and lecturers. -No bugs and no errors during usage. -The VR is responsive and fast for students and lecturers. -Available 24/7 at 99.95% uptime. -The students’ and lecturer’s data are secure and protected. -The VR has scalability feature which handles increasing number of users without affecting performance. -The code is efficient and well documented. -The code is easy to maintain for future updates. -The code has been tested for errors to ensure standards. -Good logging for monitoring. -Availability of VR for students and lecturers everywhere with Internet. |
| Project Methodology | Agile - Scrum |
| Project Budget | Phase; Estimated Cost, NZD. Sprint 0; $104,347.00. Sprint 1; $37,338.00. Sprint 2; $69,342.00. Sprint 3; $48,006.00. Sprint 4; $70,249.20. Sprint 5; $32,004.00. Sprint 6 Sprint 7 Sprint 8 Sprint 9 Sprint 10; $32,004.00 $32,004.00 $32,004.00 $32,004.00 $75,583.20. Total Cost for Project:; $564,845.40. |
| Project Schedule | Start Date: 12 March 2025 Estimated Completion Date: 23 July 2025 Estimated Duration: 96 Working days |
| Milestones | Date; Milestones. 12 March 2025 14 March 2025 25 March 2025; Project start Completion of Project Vision Preparation for Sprint 1 done.. 14 April 2025; Completion of UI/UX flows.. 14 April 2025; Completion of Emergency Room. 25 April 2025 29 April 2025 29 April 2025 29 April 2025 8 May 2025 12 May 2025 21 May 2025 29 May 2025 6 June 2025 16 June 2025 24 June 2025 2 July 2025 10 July 2025 15 July 2025 18 July 2025 23 July 2025; Completion of Deployment to Test Environment Completion of lecturer dashboard Completion of LMS integration Completion of multi-user capabilities Completion of User Training and lecture to students and lecturers Completion of Intensive Care Unit Deployment to production Completion of Medical Ward Completion of Operating Room Completion of Maternity Care Completion of Behavioral and Mental Health Room Completion of Family Room Completion of Neonatal Intensive Care Unit (NICU) Completion of Manual and User Training to Students and Lecturers Deploy to Production Project Closure. |
| Risks | - Tasks might take more time to complete as the tasks are assigned to interns. - The buffer did not consider sick leaves and absences of employees.. - Students or lecturers may be hesitant and avoid using the new VR. - Malfunctions of hardware and software - VR simulations might not reflect the Maori practices.. |

2. Background and Purpose

Otago Polytechnic is set to launch a Virtual Reality (VR) Learning Platform tailored specifically for its Nursing and Healthcare programs in Dunedin. This innovative tool will allow students to hone essential medical skills, such as diagnosing patients and managing emergencies, within a highly immersive virtual hospital setting. By replicating real-world scenarios, the VR platform will create a secure and supportive environment for students to build and perfect their clinical abilities, free from the stress or potential risks of hands-on practice in actual healthcare settings. This initiative reflects the institution’s dedication to preparing students for the challenges of modern healthcare through forward-thinking solutions.

Key features of this platform will be the eight different hospital rooms (Emergency Room, Intensive Care Unit, Medical Ward, Operating Room, Maternity Care, Behavioural and Mental Room, Family Room, and Neonatal Intensive Care Unit) that will be created in the VR world. Another key feature include the ability for students to interact and collaborate with each other in real time. Multi-user capabilities will enable role-playing exercises that closely mimic real healthcare scenarios, helping students develop teamwork, decision-making, and communication skills. This immersive, hands-on approach will better prepare students for the challenges they will encounter in their future careers. Furthermore, the platform will integrate smoothly with the Polytechnic’s existing Learning Management System (LMS), allowing both students and lecturers to easily track progress and manage coursework

The platform will also be designed to be culturally inclusive, integrating Māori health frameworks and practices into the VR simulations. This ensures that students not only learn the technical aspects of healthcare but also gain an understanding of the cultural sensitivities necessary for delivering holistic care. The system will include realistic 3D environments and provide a built-in feedback system, enabling lecturers to evaluate student performance and offer real-time guidance.

To ensure success, the project will also involve comprehensive training programs for both students and faculty, ensuring they feel confident in using the VR technology. With a budget of NZD 600,000.00 and a planned completion timeline of 5 months, this initiative promises to be a groundbreaking step in modern healthcare education. A detailed risk management plan will tackle potential challenges, such as technology issues and resistance to new methods of learning, ensuring the platform’s long-term success and impact.

3. Project Scope

The project scope is defined as a statement by writing the context, main inputs and outputs and main functions of the system to be developed. Project scope defines all tasks, activities, resources, timelines, decisions, and project boundaries that must be done to meet project goals and deliverables. The project scope statement (PSS) is prepared for the customer to illustrate the purpose of developing the project and plan of all activities needed to accomplish the project. The PSS warrants that all stakeholders are benefited to understand the project (Althiyabi & Qureshi, 2021).

3.1 Objectives

It is explained by Pichler (2021) that the project goal is the outcome based and it is important what outcomes the project delivers to the stakeholders.  Software development projects objectives move from the feature based towards the value based with the shift from the importance of the features to the importance of the value the project can deliver (Pichler, 2021).

Pedroso and Oliveira (2013) add that the software development project objectives relates to the value it creates for the stakeholders and to the customers satisfaction. The main software product development project goal is delivering value to the client and stakeholders focusing on the purpose that the project aims to fulfil (Scrum.org, 2021).

The Otago Polytechnic (OP) online Veterinary nursing course project’s goal can be seen in creating the possibility for the students and tutors to continue the education process in the Covid time and to create the online learning experience that is as close as possible to the real life conditions. This project objective is to develop online Veterinary nursing course for Otago Polytechnic (OP) that should provide the possibility for OP Students to gain knowledge and  the veterinary learning experience through online simulation gaming. With the software product, as a result of this project, OP students should be able to perform online simulations of diagnostic, treatment and administrative activities for domestic and farm animals. The software should allow to have secured individual and group access to online training, class projects and database with training archive. Students and tutors should be able to communicate via real time chat and video conferencing.

3.2 Deliverables

Bryde and & Joby (2007) explain the deliverables as the project’s end product that also can be named as measurable results that can be classified as tangible results and intangible results. Jaber et al. (2018) highlights that accurate definition and description of the project deliverables in terms of stakeholders requirements can help with accurate work identification and planning and create the product vision. The deliverables in terms of outputs could be tangible objects created as the project result (product, report and document) or new state that the project created (Jaber et al., 2018). In case of software product development with Scrum the tangible objects could be the main software functions and features, while the intangibles explain how the operations will be different for the stakeholders’ after software installation and usage (Schwaber, 2004).  The tangible and intangible deliverables for the OP online Veterinary nursing course project are listed below. Online simulation learning modules are based on the OP NZ Diploma in Veterinary, level 6 (OP Vet Nursing, 2021).

Tangible deliverables:

-Homepage with login, navigation and all features information.

-Security package (access security, network security, students’ personal information defence).

-Shared access for group simulation training and project work for multiple students and one lecturer.

-Past learning repository (learning history database and storage).

-Communication Suite that includes real time chat and video conferencing.

-Online simulation games for Veterinary nursing course for domestic and farm animals (for 8 learning courses):

- Course 1-Veterinary Nursing Professional Practice

- Course 2-Nursing Process, Disease Pathology, and Life Support

- Course 3-Nutrition, Therapy, Wound Care and Bandaging

- Course 4-Clinical Skills1

- Course 5-Surgery, Anesthesia, and Pharmacology

- Course 6-Imaging, Diagnostics and Dentistry

- Course 7-Clinical Skills2

- Course 8-Veterinary Nursing Services

-Special page with guide to Maori/Iwi practices.

-Online training for OP employees on using the online veterinary learning course.

-User guide within the software package and user documentation.

Intangible deliverables:

-Possibility for the students and OP to continue the learning process without interruptions during the lockdowns and Covid restrictions.

-Possibility for Offshore students to study Veterinary nursing course.

-Through participation simulations and the real nursing practices the students will gain practical experience requited for real work practice and work placement training.

-Increasing students’ satisfaction and work preparedness level.

3.3 Milestones

A milestone is explained by McAbee (2021) as a significant event within the projects’ life that helps in measuring the project’s progress compared with the final point. Within the software development project the agile milestone defined as a moment that displays the important stage in development (Wrike, 2021). For example, it could be when the major deliverable is completed (McAbee, 2021), or when the design is approved (Wrike, 2021).

In the agile development the milestones could be used to measure the performance and check if the project is on track. Within agile approach and scrum process the development lifecycle is separated on iterations, and as the sprints result in delivering of completed element of functionality the scrum team may to have the milestones connected with the end of the sprints (Wrike, 2021).

The milestones for the OP online Veterinary nursing course project are listed below.

| Phase | Milestones | Date |
| --- | --- | --- |
| Foundation phase | Project start | 7 September 2021 |
|  | Foundation Phase completed | 17 September 2021 |
|  | Homepage with login, navigation, security, and database -Done | 1 October 2021 |
| Development | Approval of game characters and Guide to Maori/Iwi practices page by OP and Maori Board | 13 October 2021 |
|  | Game page, online repository page, Maori/Iwi page, Game characters - Done | 15 October 2021 |
|  | Communication suite done | 22 October 2021 |
|  | Online user guide Done | 28 October 2021 |
|  | Release 1 -of Veterinary nursing simulation game with Couse1 | 29 October 2021 |
|  | Release 2 -of Veterinary nursing simulation game Couses 1-4 | 12 November 2021 |
|  | Release 3 -of Veterinary nursing simulation game Couses 1-6 | 26 November 2021 |
|  | Final Release 4 -of Veterinary nursing simulation game Couses 1-8 | 10 December 2021 |
| Closure | Project completed and closed | 16 December 2021 |

3.4 Technical requirements

For the project success the technical requirements to software product needs to be defined in details and they create a formal agreement between the customer and the developer describing specific characteristics for the product to meet (Altexsoft, 2021).   Technical requirements to the software products are divided into functional and nonfunctional and within Scrum Project the functional and nonfunctional requirements that product needs to meet are specified in the Product Backlog (Schwaber, 2004). It is very complex and difficult task to consider in full both types of requirements, thus it requires high level of technical knowledge from the product owner and project team, and collaborative work with stakeholders (Chen et al., 2013).

Functional requirements describe the functionality and determine what product need to do, what features and functions the product can perform (Chen et al., 2013). Non-functional requirements determine how the product performs, describing the system’s properties and responsible for the system’s quality (Altexsoft, 2021). For example, the non-functional requirements relate to performance, response time, security, reliability and availability, compatibility and maintainability (Singhera & Shah, 2006).

3.4.1 Functional requirements

The examples of some of the OP online Veterinary nursing course project functional requirements are listed below:

- Access on main page with login and password window.

- Main page should have the navigation to Courses pages, game page, learning depository page, Maori/Iwi page

- Storage of students’ personal data should meet general data protection requirements standards.

- The teacher can access and get connected to different group game sessions.

- Students should be able to have individual and group access simultaneously to the simulation game sessions.

- The lecturer and students should be able to communicate within the game session and out of the game session through chat and video conference options.

- Video conferencing and chat should be access through game page and main page.

- The average time a student takes to go through the simulation course should be similar to the time required to go through the course materials in the class.

- Simulation game content meets the NZQA Course content requirement of New Zealand Diploma in Veterinary Nursing ( Level6) provided by OP.

- The simulation game content and Maori/Iwi page content meets the Maori Counsel requirements to ethics and values.

3.4.2 Non-functional requirements

Non-functional requirements examples related to the OP online Veterinary nursing course project explained by Altexsoft (2021) can be seen below:

-Security requirements are focused on protecting the system from malware attacks and unauthorised access to the data and the system.

OP online Vet project requirements: 1) the permissions to access to students data, learning history and game sessions can be changed only by the OP IT administrator. 2) With the attempt to access the system by the user from the different device the system should request user verification through the access code to be sent via email or text message.

-Response time indicates the system’s response on different user activities;

OP project requirements: 1) Main page loading time: 2 seconds max, 2) Simulation gaming reaction recommended - 0.1 second, Max time - 1 second. Reaction time more than 3 seconds – Not accepted. As stated by Altexsoft (2021) this parameter is critical for product quality as the user lose attention completely after 10 seconds.

- Compatibility determines how the product interacts with other systems and what the minimum user equipment requirements are;

OP Online Couse User soft and hardware requirements: Operation system: Windows 8.1+, Mac OSX 10.13+, Processor: 1,8GHZ dual core min, 2GHz dual core recommended, RAM 2 GM min, 4 GB recommended, Disc Space 5GB min., display resolution min 1366x768.

-Availability OP Online Couse: 24/7/365

-Reliability OP online Course: 85%. It means that the course has 85% probability that the course system will not have any failures per month.

-Maintainability OP online course: 75%. It means that the course has 75 percent probability that the failures will be fixed during 24 hours.

-Usability requirements address the problems of difficulty/simplicity of using the product.

OP online course min usability requirements: 1) Support all functions to be performed by Mouse and Keyboard. 2) All visual information can be seen by colour blinded people.

-Scalability OP Online course: 1) should allow scalability up to 500 active users simultaneously. 2) Learning repository storage should allow 5 years learning experience data storage.

3.5 Project Exclusions

Project exclusions are explained by Kohrel (2013) as anything that goes beyond the project boundaries and in terms of the project planning and customer relations it could be any possible stakeholder expectations that are not included in the project scope.  It is also noted by Boogaard (2020) that it is important for the project success to stipulate what is not included to avoid any future misunderstanding between the stakeholders and project managers.

The following exclusions are considered for current project:

- The project does not include developing the mobile application and include only the web version for desktop computers.

- The costs and purchasing of any software licensing required for the online course functioning are not included in the project scope and the budget.

- The project does not include purchasing and costs for online learning depository storage capacity and regular content storage costs.

- The project does not include developing the Veterinary nursing course materials.

3.6 Project Limitations

The project limitations are defined by Boogaard (2020) as any limiting factors or boundaries that can have effect and slow down the project and the project team has to work within; These limits can come from the areas or budget, time and resources, including the human resources and pre defining the limitations can help to have understanding what factors may constrain the project completion.

The following limitations are considered for current project:

-The OP Online course will be based on and integrated with the Moodle learning management services capabilities and the course functionality may be limited by the Moodle software capabilities.

- Based on the fact the Moodle LMS is free open code software and has potential higher risk to be affected by the hackers and viruses/malware developers it can limit the project’s developers team efforts to provide efficient security defence.

- The author of this project plan does not have practical online software development experience result of the project planning is limited with the information obtained from open academic sources.

-There is no information in the case study about the project timeframe and planned project start date and required finish dates, therefore the planning was done without considering the holiday periods, while the holiday periods may have considerable effect on the project completion time and cost.

-The project is limited with the human resources available in New Zealand due to the border restrictions and have constrains to hire required specialists from overseas.

4. Project Assumptions

Project assumptions are considered by Kohrel (2013) as the elements on the planning that are just believed to be true. Boogaard (2020) explains the assumptions as the project factors that are just considered to be real and definite and considered to become true without having real practical confirmation or proof. The assumptions are important element that the adds clarity to the project planning, however the future is unpredictable and in case the assumption proves to be false it turns to become a risk for the project, therefore it is important to define the assumptions and consider them in identifying the risks and minimising possible impacts on the project results (Boogaard, 2020).

The following assumptions are considered for current project:

-The project plan is done on the assumption that OP will contract the professional software development company and the project plan is created from the software development company view.

-It is assumed the OP will provide the Online veterinary simulation course materials with documented requirements prior to the beginning of the project.

-The plan and the budgeting are created on the assumption that the software development company has in their possession all equipment and software required for developing software product and ensuring uninterrupted work by their employees, therefore the budgeting is considering the human resources costs only as main costs of the software project.

-The project planning and budgeting is done assuming the software development company has the teams of required specialists employed permanently and full time, therefore there is no need to hire new IT specialists at the beginning of the project.

-The project budgeting assuming the employees’ pay level to stay constant during the project period and does not consider any employees pay raises.

- The planning assumes that the course will be based and integrated with Moodle LMS and OP has all valid licences and registrations to use Moodle LMS, MS 365 suite and MS Teams suite, MS SQL Server.

- The project planning is done on the assumption that project team representative may represent OP communicating with stakeholders like NZQA and Maori Council proving and presenting information about the simulation course, however obtaining final documented approvals of the course content is the OP responsibility.

-The project scheduling is based on the assumption of the project team and OP representatives are available working during normal 40 hour week from Monday to Friday and do not consider possible holidays and breaks or work overtime.

5. Methodology

The methodology chosen for OP online Veterinary nursing course project is Scrum. It is proven to be efficient agile framework to work with complex problems and combining possibility to create the software products of the highest value and ensuring high level of project team creativity and productivity (Scrum.org, 2021). Scrum supports agile values and provides the process control through the strict following of simple sets of practices and rules with specific Scrum Events, Artifacts and Roles (Zenkit, 2018). The heart of Scum is in iteration called Sprint, which is a fixed time iteration comprising full software development cycle process resulting in the pieces of done product functionality and all the workflow is built around sprints with fixed scum sprint events (planning, review, retrospective) and a daily scrum that allow to adjust the planning according to the changes in the process or requirements (Schwaber, 2004).

All the project requirements prioritised for work are presented in the Product Backlog and the requirements from Product backlog are transferred into the Sprint’s backlog for the sprit planning in the form of tasks for performing (Zenkit, 2018). There is no project manager in Scrum and there are only three roles of Product Owner, Scrum Master, and Team member where all managerial responsibilities are split between them (Schwaber, 2004).  The Product Backlog and all the stakeholders relations are managed by the Product Owner who provides the direction for other project members what needs to be created, while how to develop the software product and what exactly to do the team decide themselves (West, 2018). The Scrum Master is responsible for felicitating the Scrum process to flow and making sure all impediments for team work are removed (West, 2018).

5.1 Justification

There are several reasons why Scrum was chosen for OP Veterinary course online simulations game project. It is noticed from Otago Polytechnic (2021) that delivering high quality educational products is the top priority for OP. Scrum meets that requirement as efficient agile framework for creating the software products of the highest value and ensuring high level of project team creativity and productivity (Scrum.org, 2021). There are multiple stakeholders involved in this OP project like Otago Polytechnic lecturers, administration, Nursing course team leader and head of veterinary department, students, NZQA and Maori stakeholders who create the requirement for the use of methodology suitable for considering multiple stakeholder expectations. Having Product Owner as a special role working as stakeholder representative and making sure all stakeholder requirements are translated to the team with the software product that meets the stakeholder expectations delivered makes Scrum the stakeholder focused methodology (Schwaber, 2004).  Thus, it meets the OP project requirements to consider multiple stakeholder expectations.

It can be seen from the cases study that OP online simulation nursing course can be considered to be a complex software product with multiple functions and complex structure with requirements for simulations of all parts of veterinary nursing process applicable to different types of animals. Moreover, it has the requirements for communication suit and the learning history to be built in the product. In addition, according to OP Vet Nursing (2021) the programme consist of eight different courses and creating the simulations for them requires creative approach and design work. Scrum is focused on developing complex software products were design and creativity are important (Scrum.org, 2021). Thus, it is considered to be the nest to suit the OP project requirements.

It is revealed by West (2018) that very often the customers can not realise what they exactly want from the software product until they see it and try to use it, while Scrum delivering the pieces of working, tested and maintainable product at the end of the sprint helps to solve that problem. This Scrum attribute is considered very valuable to OP project as OP team and students can see working parts of the course and simulation game early. Moreover Scrum allows producing different releases starting from minimum viable product so OP team and students can start using for product form the first course and provide the feedback that can be considered in the next releases and the next Veterinary Nursing programme parts.

6. Project Risks and Risk Management Plan

In project management, project risk is defined as the chance of certain occurrences adversely affecting project objectives. It is the degree of exposure to negative events, and their probable consequences. Project risk is therefore characterized by the following risk factors: risk event, risk probability, and amount at stake. Therefore risk management, is the art and science of identifying, analyzing and responding to risk factors throughout the life of a project and in the best interests of its objectives (Pym, 1987). The steps in risk management process are the following: risk identification, risk assessment, risk treatment, risk response planning, risk monitoring and control and risk communication (Martins, 2024).

In the case of OP-MedVR. The table below shows the risks, probability of risk occurring, impact on the project delivery, risk level, member responsible for risk prevention, and mitigation steps.

| Project Risk | Probability | Impact | Risk Register | Member Responsible | Mitigation |
| --- | --- | --- | --- | --- | --- |

7. Project Organisation

A project organizational structure is used to determine the hierarchy and authority of people involved in a specific project. The structure defines each team member’s function and the reporting lines on a chart for team members to reference during a project. Project managers use project organization to align team members before and during a project. The process minimizes disruption to your workflow and conflict among team members, as well as leads to maximum productivity among team members involved in a project (Martins, 2024).

For the OP-MedVR, The whole development team reports to the Senior Product Owner and the Senior Product Owner and the HR Manager reports to the Engineering Manager. The student and lecturer assigned by OP reports to the OP. The table below shows the project organisation structure, their roles, responsibilities, and who they report to.

| Name | Functional role | Responsibilities | Reporting To |
| --- | --- | --- | --- |
| Suigetsu Hozuki | OP Board Member | Decision making for OP |  |
| Kakashi Hatake | Engineering Manager | Leading the development team | OP Board Member |
| Tsunade Senju | HR Manager | Hiring of members | Engineering Manager |
| Choji Akimichi | Senior Product Owner | In charge of backlogs | Engineering Manager |
| Shikamaru Nara | Senior Platforms Engineer | In charge of deployment related tasks, pipeline creation | Senior Product Owner |
| Minato Namikaze | Risk Management Specialist | In charge of risk management | Senior Product Owner |
| Sakura Haruno | Cultural Consultant | Ensure Maori and other Cultural requirements are met | Senior Product Owner |
| Rock Lee | Senior VR Software Engineer 1 | In charge of development, does full-stack development and design | Senior Product Owner |
| Kiba Inuzuka | Senior VR Software Engineer 2 | In charge of development, does full-stack development and design | Senior Product Owner |
| Shino Aburame | Intermediate Full stack software engineer 1 | Full-stack development and design | Senior Product Owner |
| Kurenai Yuhi | Intermediate Full stack software engineer 2 | Full-stack development and design | Senior Product Owner |
| Kimimaro Kaguya | Associate full stack software Engineer 1 | Full-stack development and design | Senior Product Owner |
| Mei Terumi | Associate full stack software Engineer 2 | Full-stack development and design | Senior Product Owner |
| Zabuza Momochi | Fullstack software engineer Intern 1 | Full-stack development and design | Senior Product Owner |
| Konohamaru Sarutobi | Fullstack software engineer Intern 2 | Full-stack development and design | Senior Product Owner |
| Sasuke Uchiha | Fullstack software engineer Intern 3 | Full-stack development and design | Senior Product Owner |
| Naruto Uzumaki | Fullstack software engineer Intern 4 | Full-stack development and design | Senior Product Owner |
| Hinata Hyuga | Fullstack software engineer Intern 5 | Full-stack development and design | Senior Product Owner |
| Danzo Shimura | Senior QA Engineer | In charge of quality and code testing | Senior Product Owner |
| Kisame Hoshigaki | Senior VR Designer/Content Developer | In charge of VR Design, does software development as well | Senior Product Owner |
| Asuma Sarutobi | Trainer | In charge of training to students and lecturers | Senior Product Owner |
| Jinpachi Munashi | Lecturer | Lecturer assigned from OP to test the VR | OP Board Member |
| Kushimaru Kuriarare | Student | student assigned from OP to test the VR | OP Board Member |

8. Communications with Stakeholders

8.1 Stakeholders identification.

A stakeholder is a person, group or organization with a vested interest, or stake, in the decision-making and activities of a business, organization or project. Stakeholders can be members of the organization they have a stake in, or they can have no official affiliation. Stakeholders can have a direct or indirect influence on the activities or projects of an organization. Their support is often required for business and project success (Barney, 2023). In the case of OP-MedVR, the stakeholders will be the following:

| Stakeholder | Role | Influence Level | Decisional Influence | Internal/External |
| --- | --- | --- | --- | --- |
| OP Head | OP head will be the owner of the project | 5 | 5 | Internal |
| OP board | OP stakeholders that will benefit from the project | 4 | 4 | Internal |
| OP professors | The professors and students will use the VR after deployment | 3 | 3 | Internal |
| Maori consultants | Their Maori knowledge affect decisions | 3 | 3 | External |
| OP Students | They will use the VR after production | 2 | 2 | Internal |
| Operations Team | They will maintain the VR after project closure | 3 | 3 | Internal |
| Manager and Development Team | In charge with development of VR | 3 | 3 | Internal |
| External Auditors | In charge of checking for standards(NZQA, Maori Council, regression testers, and penetration testers) | 3 | 3 | External |

8.2 Communication plan

Agile ceremonies are composed of daily standup, story grooming, sprint planning, sprint review, and sprint retrospective which are used to discuss the project’s next course of action (Laoyan, 2025).

In the case of OP-MedVR, communication with stakeholders will be done during these agile ceremonies. It will be discussed in detail below.

| Stakeholder | Role | Purpose | Mode/Chanel of Communication | Frequency | Time | Participants |
| --- | --- | --- | --- | --- | --- | --- |
| OP Head and board | OP head will be the owner of the project | Get updates from the VR project | Online Meeting | Planning Dates 3/12/25 3/26/25 4/4/25 5/6/25 5/23/25 6/2/25 6/10/25 6/18/25 6/26/25 7/4/25 | 10am | Development Team and Stakeholders |
| OP professors | The professors and students will use the VR after deployment | To know how the VR is used | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders |
| Maori consultants | Their Maori knowledge affect decisions | To know if the VR project follows Maori Principles | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders |
| OP Students | They will use the VR after production | To know how the VR is used | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders |
| Operations Team | They will maintain the VR after project closure | To know how the VR is used | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders |
| Development Team | Development of OP-MedVR | Discuss progress and updates | Daily Standup | Everyday | 3pm | Development Team |

9. Change management plan

Change management ensures that a project achieves its intended results and outcomes by supporting the individual transitions required by that project. When a new technology is used, employees must adopt and use it to deliver value. When you implement a new process, employees must adopt and use it to deliver value. Project-level change management provides the specific strategies, plans, actions and steps that focus on impacted employees and work in alignment with a project deployment (Creasey, 2022).

In scrum, changing requirements is quite common. Agile Manifesto Principle says “Welcome changing requirements, even late in development. “(Beck et al., 2001). Which means, we take decisions on what to do by seeing what results we are seeing. This approach will involve changing requirements as we go along (Kulkarni, 2023). The following below are done in the scenario of a change request (Dworniczak, 2025):

In the case of OP-MedVR, the following is done to assess change request:

- The change request form goes to the Product Owner and the stakeholders. Product owner and the stakeholders checks for cost-benefit effect, risk assessment, resource availability, impact on scope, and priority.

- Once it is approved, the Product Owner discusses with the scrum master and the development team regarding the effect of the change request. For example, the ICU room VR might get delayed in delivery if we apply this change. The development team discusses possible scenarios on how change request will be delivered.

- The Product Owner relays it to the stakeholders the scenarios to see if they will agree to it. The Product Owner then adjusts then backlog based on it.

- The change request then gets implemented based on the priority in the backlog.

10. Project Estimation Technique

A successful project starts with a successful estimate. To properly schedule the work to execute your project, you need to know the timeline, costs, scope, risk and more. All of these considerations are part of project estimation techniques. Estimation techniques help make decisions on the viability of your project. If you decide to move forward, they’re essential to forecasting projects accurately (Hennesy, 2022). The following below are some of the estimation methods:

1. Analogous estimation: A technique for estimating costs for your current projects and future projects based on a similar past project. Analogous estimating is one of the most detailed and accurate ways to estimate the cost data for a given project, so that you can set up an accurate cost baseline, without entering into the world of statistical models (Viter, 2022).

2. Parametric estimation: A statistical and accuracy-based technique for calculating the time, cost, and resources needed for project success. Combining historical and statistical data, parametric estimating uses the relationship between variables to deliver accurate estimations. Often used during a project or in the project planning phase, parametric estimating applies a formula or algorithm for making these calculations, using the specific cost or time needed to implement and finish a project or task (Udoagwu, 2022).

3. PERT diagram: A graphical illustration of a project as a network diagram consisting of numbered nodes linked by labeled vectors. PERT charts help project managers estimate the minimum time needed to complete a project. Managers can also analyze the work breakdown and task connections and assess project risks. The breakdown structure makes it easy to organize a complex project with a variety of moving parts by visualizing the dependencies between each step of the process (Sheldon et al., 2024).

4. Top-down approach: Frequently used for creating rough order of magnitude (ball-park) estimates at an early stage of the project, when the level of detail available is limited (they can also be used for validation purposes). Top-down estimates generally take less time and effort to produce than bottom-up estimates.The main benefit of top-down is the chance to use more holistic data from previous projects or products, including unmitigated and unforeseen risks, and scope creep. This can help reduce the risk of overlooked work activities or costs (Rowland, 2019).

5. Bottom-up approach: It is when you build your estimates from the most granular level of work needed in a specific project and estimate “up” from there to the bigger picture of the project. The superpower of this estimation technique lies in its unparalleled specificity. This creates a work breakdown structure (WBS) to estimate all the details of the lowest level of work needed and then add them up as you work up to the larger activities of a project. You can get to the discrete details by breaking the project into smaller deliverables and then individual tasks (Card, 2024).

In the case of OP-MedVR, Bottom-up approach and parametric estimation was used since most tasks are related, we can allocate the effort and budget for each specific task in relation to previous tasks (Guthrie, 2023). Bottom-up approach is great for this as well as we get to estimate all the activities needed by breaking it down into smaller tasks (Usifo, 2024).

11. Budget

A project budget is the total projected costs needed to complete a project over a defined period of time. It’s used to estimate what the costs of the project will be for every phase of the project. Creating a project budget is a critical part of the project planning process. The project budget will include such things as labor costs, material procurement costs and operating costs. But it’s not a static document. Your project budget will be reviewed and revived throughout the project, hopefully with the help of project budgeting software (Bridges, 2023b).

In relation to OP-MedVR, the expenses used in the preparation(sprint 0) will include all the necessary equipments and software needed for the duration of the project(5 months). The expenses in the sprints(Sprint 1 – Sprint 10) will focus on the labour costs and 5% for miscellaneous cost. This is under the assumption that licenses and equipments were already purchased during preparation, and that since all the employees are working from home, there is minimal cost in other expenses which will be covered by miscellaneous cost.

The rate per hour for each employee were based on the salary sourced from Glassdoor and Seek(2025) as what employers are offering based in current market demand. The annual salary is is divided by 52 weeks and then divided by 40 hours per week to get the salary per hour.

The pay rates for the team employees were estimated based on the information sourced from SEEK (2021) as the source of most recent information what the employers are ready to offer for IT specialists in current market situation. The average annual salary from ten most recent job advertisements with the pay range per occupation was divided by standard 52 working weeks per year and 40 hours per week to calculate the hourly rate.

For the Work Breakdown Structure, the Work breakdown Structure in the MS Project is not utilised under the assumption that all the employees of the team are working full time in the background(communicating with stakeholders, code reviews, testing features, bug fixes, grooming tasks, etc..) even though they are not assigned a project in MS Project, which implies that they are working 8 hours per day, and 5 days per week. This is in exception to the HR Manager and Trainer, which will only work for 5 days and 6 days respectively.

Human resource pay rate per hour table:

| Role | Pay Rate Per Hour | Hours Estimated | Total Cost |
| --- | --- | --- | --- |
| OP Board Member | $0 | 0 | $0 |
| HR Manager | $53.00 | 8 hours x 5 days | $2,120.00 |
| Engineering Manager | $51.00 | 8 hours x 96 days | $39,168.00 |
| Senior Platforms Engineer | $52.00 | 8 hours x 96 days | $39,936.00 |
| Risk Management Specialist | $34.00 | 8 hours x 96 days | $26,112.00 |
| Cultural Consultant | $42.00 | 8 hours x 96 days | $32,256.00 |
| Senior Product Owner | $48.00 | 8 hours x 96 days | $36,864.00 |
| Senior VR Software Engineer | $46.00 | 8 hours x 96 days | $35,328.00 |
| Intermediate Full stack software engineer | $33.00 | 8 hours x 96 days | $25,344.00 |
| Associate full stack software Engineer | $28.00 | 8 hours x 96 days | $21,504.00 |
| Fullstack software engineer Intern | $25.00 | 8 hours x 96 days | $19,200.00 |
| Senior QA Engineer | $34.00 | 8 hours x 96 days | $26,112.00 |
| Senior VR Designer/Content Developer | $35.00 | 8 hours x 96 days | $26,880.00 |
| Trainer | $36.00 | 8 hours x 6 days | $1,728.00 |
| Lecturer | $0 | 0 | $0 |
| Student | $0 | 0 | $0 |
| Total |  |  | $491,528.00 |

For the budget categories, the budget allotted is for the duration of the development of OP-MedVR(5 months) and the needed equipments of the development team. The rent and electricity is $0 under the assumption that the whole team is remote/working from home status. The cost on rent and electricity will be considered under miscellaneous.

| Budget Categories | Description | Cost |
| --- | --- | --- |
| Labour Cost | Manpower Cost | $491,528.00 |
| Accessories | Keyboard and Mouse | $4,000.00 |
| Rent | Monthly Rent | $0.00 |
| Electricity | Montly Electricity | $0.00 |
| Software Licenses | Licenses for Jira, Unreal Engine, Github, and Azure | $3,420.00 |
| Laptops | $1300 x 20 Laptops for the development Team | $26,000.00 |
| VR Hardware | $650 x 20 for the development team | $13,000.00 |
| Miscellaneous | 5% for other expenses | $26,897.40 |
| Total |  | $564,845.40 |

The OP project Budget table:

| Phase | Details | Completion Date | Estimated Cost |
| --- | --- | --- | --- |
| Sprint 0 | Preparation | 25 March 2025 | $104,307.00 |
| Sprint 1 | Design Emergency Room | 3 April 2025 | $37,338.00 |
| Sprint 2 | Develop UI Develop Emergency Room | 22 April 2025 | $69,342.00 |
| Sprint 3 | Develop Dashboard and Multi-user Design ICU | 5 May 2025 | $48,006.00 |
| Sprint 4 | Deployment to Production Develop ICU Design Medical Ward | 22 May 2025 | $70,249.20 |
| Sprint 5 | Develop Medical Ward Design Operating Room | 30 May 2025 | $32,004.00 |
| Sprint 6 | Develop Operating Room Design Maternity Care | 9 June 2025 | $32,004.00 |
| Sprint 7 | Develop Maternity Care Design Behavioural and Mental Health Room | 17 June 2025 | $32,004.00 |
| Sprint 8 | Develop Behavioural and Mental Health Room Design Family Room | 25 June 2025 | $32,004.00 |
| Sprint 9 | Develop Family Room Design NICU | 3 July 2025 | $32,004.00 |
| Sprint 10 | Develop NICU Deployment to Production Project Closing | 23 July 2025 | $75,583.20 |
| Total Cost |  |  | $564,845.40 |

12. Quality Control and Audit

- Quality Control

Quality control (QC) is a process through which a business seeks to ensure that product quality is maintained or improved. QC requires the company to create an environment where management and employees strive for perfection. This is done by training personnel, creating benchmarks for product quality, and testing products to check for statistically significant variations (Hayes, 2024).

- Audit

The audit is designed to determine the status of work performed on a project to ensure it complies with the statement of work, such as the scope, time and budget of the project, along with the maturity of the project management process. During audit the project scope, schedule, quality, cost, resources, and risks are checked to make sure it is still following the project plan (Bridges, 2023a). However in agile teams, the process sometimes deviates to address certain issues, which is expected as stated in the Agile Manifesto, “Individuals and interactions over processes and tools” (Beck et al., 2001). The auditor should communicate with Product Owner and Scrum master to ensure that agile practices were followed (Nair, 2019). In OP-VR LMS, the auditor should check the artifacts created during sprint planning, review and retrospective, as well as product backlogs.

As part of preparation for deployment to production, the table below are asked with setting up the quality control and audit of OP-MedVR.

| Quality Control | Metrics | Implementation in the Project |
| --- | --- | --- |
| New Zealand Qualifications Authority(NZQA) | Compliance with healthcare education standards | Review to ensure OP-MedVR complies with healthcare education standards |
| Maori Council | Compliance with Maori Values and principles | Review to ensure that the project adheres to culturally appropriate Maori practices |
| Regression Testing | Compliance with Industry quality | Testing by third party to ensure industry quality standards |
| Penetration Testing | Compliance with Security standards | Testing by third party to ensure data-leaks of private information such as logging, and unauthorized access are avoided |
| Auditor | Compliance with processes and protocols | Testing by third party to ensure that proper processes and protocols are followed such as code reviews, proper testing, proper deployment from development to testing, proper testing of environment. |

13. Project Closure

Agile project closure is a pivotal phase that ensures the project concludes smoothly while capturing valuable insights for future endeavours. Unlike traditional methodologies, Agile project closure is iterative and aligned with the Agile principles (Sengupta, 2023). To ensure the successful transfer of ownership from the Agile team to the operations team, the following items below are done to make sure we tie up any loose ends (Cosgrove & Hubbard, 2020).

| Closure Task | Description | Artifacts |
| --- | --- | --- |
| The scrum boards(Jira) will be archived, and documentation is organized. | Scrum board(Jira) will be archived. It will be unaccessible but the sprint data can still be viewed. The documentations and links are organized. | Documentations Sprint Data |
| Meetings with the Operations Team | Walkthru the key user stories remaining(if there is any) in the backlog Discuss the sprint artifacts and sprint data. Knowledge sharing regarding end-to-end functionality of OP-MedVR Access controls are given to the Operations Team | Knowledge sharing recordings Sprint artifacts and sprint data Sprint backlog Access controls |
| The project is handed to the Operations Team | Artifacts, source code repositories are given to the Operations Team The user-training manual is also given to the Operations Team | Source code repository User-training manual |
| Final Review of the project | Final sprint review including the stakeholders to review the final scope that was complete, the budget, and the schedule. | Sprint velocity Sprint data |
| Sprint Retrospective | A final retrospective is completed as a team to document on lessons learned, identify process improvements. | Retrospective board |
| Return assets used | The hardware used such as the laptops, VR hardware, other equipments are returned. | Asset tracking document |

13. References:

Althiyabi, T., & Qureshi, R. (2021). Predefined project scope changes and its causes for project success. International Journal of Software Engineering & Applications (IJSEA), 12(2/3).

Barney, N. (2023). Stakeholder. TechTarget. https://www.techtarget.com/searchcio/definition/stakeholder

Beck, K., Cohn, M., Jeffries, R., Anderson, D., Beedle, M., Boehm, B., Combemale, B., Highsmith, J., Hunt, A., Kern, P., Larman, C., Martin, R., Mellor, S., Schwaber, K., Sutherland, J., & Thomas, D. (2001). The Agile Manifesto. Agile Alliance. http://agilemanifesto.org/

Bridges, J. (2023a). How to Do a Project Audit: A Quick Guide. ProjectManager.Com. https://www.projectmanager.com/training/project-management-audit

Bridges, J. (2023b). How to Make a Project Budget: Project Budgeting Basics (Templates Included). ProjectManager.Com. https://www.projectmanager.com/training/create-and-manage-project-budget

Card, K. (2024). Accurate Project Estimations: A Deep Dive Into Bottom-up Estimation. UseMotion.Com. https://www.usemotion.com/blog/bottom-up-estimating

Cosgrove, E., & Hubbard, K. (2020). Agile closing out project. Action Engineering Blog. https://www.action-engineering.com/blog/agile-closing-out-project/

Creasey, T. (2022). Change Management at the Project Level. Prosci. https://www.prosci.com/blog/change-management-at-the-project-level

Dworniczak, M. (2025). Understanding Change Requests in Scrum. LinkedIn. https://www.linkedin.com/pulse/understanding-change-requests-scrum-mariusz-mario-dworniczak-pmp-i26bf

Eby, K. (2021). Essential Guide to Project Organizational Structure. https://www.smartsheet.com/content/project-management-organization?srsltid=AfmBOoo1noRBtZhQ4hZJVw7TRajpVMRSrta9YgIbSvq2FbhXB16auQu4

Guthrie, G. (2023). How to use parametric estimating to improve project performance. Nulab. https://nulab.com/learn/project-management/how-to-use-parametric-estimating-to-improve-project-performance/

Hayes, A. (2024). Quality Control: What It Is, How It Works, and QC Careers. Investopedia. https://www.investopedia.com/terms/q/quality-control.asp

Hennesy, M. (2022). Project Estimation Techniques. ProjectManager.Com. https://www.projectmanager.com/blog/project-estimation-techniques

Kulkarni, S. (2023). Change Management in Scrum. World of Agile. https://worldofagile.com/blog/change-management-in-scrum/

Laoyan, S. (2025). Understanding the 4 Agile ceremonies. Asana. https://asana.com/resources/agile-scrum-ceremonies

Martins, J. (2024). Step-by-step guide to the risk management process. https://asana.com/resources/project-risk-management-process

Nair, B. (2019). Auditing Agile Projects & Agile Auditing- A primer. LinkedIn. https://www.linkedin.com/pulse/auditing-agile-projects-auditing-primer-biju-nair

Pym, D. V. (1987). Risk Management. PM Network, 1(3), 33–36.

Rowland, M. (2019). Three ways to approach cost estimation. APM.Org.Uk. https://www.apm.org.uk/blog/three-ways-to-approach-cost-estimation/

Sengupta, S. (2023). Project closure strategy for agile project. Medium. https://medium.com/@mailme.senguptasudipta/project-closure-strategy-for-agile-project-0744c8440a86

Sheldon, R., Chai, W., & Brush, K. (2024). What is a PERT chart? And how to use it, with examples. TechTarget. https://www.techtarget.com/searchsoftwarequality/definition/PERT-chart

Udoagwu, K. (2022). The Ultimate Guide to Parametric Estimating in Project Management. Wrike.Com. https://www.wrike.com/blog/guide-to-parametric-estimating-in-project-management/

Usifo, D. (2024). How to Use Bottom-Up Estimating in Project Management. DeeProjectManager.Com. https://deeprojectmanager.com/bottom-up-estimating-project-management/

Viter, I. (2022). Understanding the Analogous Estimating Technique. Runn.Io. https://www.runn.io/blog/analogous-estimating

HR Manager - $53 per hour

Althiyabi, T., & Qureshi, R. (2021). Predefined project scope changes and its causes for project success. International Journal of Software Engineering & Applications (IJSEA), 12(2/3).

Barney, N. (2023). Stakeholder. TechTarget. https://www.techtarget.com/searchcio/definition/stakeholder

Beck, K., Cohn, M., Jeffries, R., Anderson, D., Beedle, M., Boehm, B., Combemale, B., Highsmith, J., Hunt, A., Kern, P., Larman, C., Martin, R., Mellor, S., Schwaber, K., Sutherland, J., & Thomas, D. (2001). The Agile Manifesto. Agile Alliance. http://agilemanifesto.org/

Bridges, J. (2023a). How to Do a Project Audit: A Quick Guide. ProjectManager.Com. https://www.projectmanager.com/training/project-management-audit

Bridges, J. (2023b). How to Make a Project Budget: Project Budgeting Basics (Templates Included). ProjectManager.Com. https://www.projectmanager.com/training/create-and-manage-project-budget

Card, K. (2024). Accurate Project Estimations: A Deep Dive Into Bottom-up Estimation. UseMotion.Com. https://www.usemotion.com/blog/bottom-up-estimating

Cosgrove, E., & Hubbard, K. (2020). Agile closing out project. Action Engineering Blog. https://www.action-engineering.com/blog/agile-closing-out-project/

Creasey, T. (2022). Change Management at the Project Level. Prosci. https://www.prosci.com/blog/change-management-at-the-project-level

Dworniczak, M. (2025). Understanding Change Requests in Scrum. LinkedIn. https://www.linkedin.com/pulse/understanding-change-requests-scrum-mariusz-mario-dworniczak-pmp-i26bf

Eby, K. (2021). Essential Guide to Project Organizational Structure. https://www.smartsheet.com/content/project-management-organization?srsltid=AfmBOoo1noRBtZhQ4hZJVw7TRajpVMRSrta9YgIbSvq2FbhXB16auQu4

Guthrie, G. (2023). How to use parametric estimating to improve project performance. Nulab. https://nulab.com/learn/project-management/how-to-use-parametric-estimating-to-improve-project-performance/

Hayes, A. (2024). Quality Control: What It Is, How It Works, and QC Careers. Investopedia. https://www.investopedia.com/terms/q/quality-control.asp

Hennesy, M. (2022). Project Estimation Techniques. ProjectManager.Com. https://www.projectmanager.com/blog/project-estimation-techniques

Kulkarni, S. (2023). Change Management in Scrum. World of Agile. https://worldofagile.com/blog/change-management-in-scrum/

Laoyan, S. (2025). Understanding the 4 Agile ceremonies. Asana. https://asana.com/resources/agile-scrum-ceremonies

Martins, J. (2024). Step-by-step guide to the risk management process. https://asana.com/resources/project-risk-management-process

Nair, B. (2019). Auditing Agile Projects & Agile Auditing- A primer. LinkedIn. https://www.linkedin.com/pulse/auditing-agile-projects-auditing-primer-biju-nair

Pym, D. V. (1987). Risk Management. PM Network, 1(3), 33–36.

Rowland, M. (2019). Three ways to approach cost estimation. APM.Org.Uk. https://www.apm.org.uk/blog/three-ways-to-approach-cost-estimation/

Sengupta, S. (2023). Project closure strategy for agile project. Medium. https://medium.com/@mailme.senguptasudipta/project-closure-strategy-for-agile-project-0744c8440a86

Sheldon, R., Chai, W., & Brush, K. (2024). What is a PERT chart? And how to use it, with examples. TechTarget. https://www.techtarget.com/searchsoftwarequality/definition/PERT-chart

Udoagwu, K. (2022). The Ultimate Guide to Parametric Estimating in Project Management. Wrike.Com. https://www.wrike.com/blog/guide-to-parametric-estimating-in-project-management/

Usifo, D. (2024). How to Use Bottom-Up Estimating in Project Management. DeeProjectManager.Com. https://deeprojectmanager.com/bottom-up-estimating-project-management/

Viter, I. (2022). Understanding the Analogous Estimating Technique. Runn.Io. https://www.runn.io/blog/analogous-estimating

Engineering Manager – 51$ per hour

https://www.glassdoor.co.nz/job-listing/ict-project-manager-techwise-solutions-JV_IC3525162_KO0,19_KE20,38.htm?jl=1009652037968&cs=1_b6da3e24&s=58&t=SR&pos=104&src=GD_JOB_AD&guid=00000195b27ff695b5f85de7264cd50c&jobListingId=1009652037968&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp7vtnigoog804-582d7553ed486054&cb=1742456485931&ctt=1742456494351

Senior Platforms Engineer - $52 per hour

https://www.glassdoor.co.nz/job-listing/senior-devops-engineer-fiserv-JV_IC3525162_KO0,22_KE23,29.htm?jl=1009678594918&cs=1_74fa5c4f&s=58&t=SR&pos=102&src=GD_JOB_AD&guid=00000195b28109a394510563b18d3c45&jobListingId=1009678594918&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp822fq2afp000-bb82b31d9c399180&cb=1742456556303&ctt=1742456627109

Risk Management Specialist – $34 per hour

https://www.glassdoor.co.nz/job-listing/product-development-specialist-hub-services-iag-new-zealand-JV_IC3525162_KO0,43_KE44,59.htm?jl=1009662255445&cs=1_4ef51041&s=58&t=SR&pos=102&src=GD_JOB_AD&guid=00000195b283066fa760d46250f5cb8e&jobListingId=1009662255445&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp861lui0ht800-3a847457d00276f3&cb=1742456686571&ctt=1742456707752

Cultural Consultant - $42 per hour

https://www.glassdoor.co.nz/job-listing/work-winning-consultant-aurecon-group-JV_IC3525162_KO0,23_KE24,37.htm?jl=1009561005629&cs=1_448e59b4&s=58&t=SR&pos=101&src=GD_JOB_AD&guid=00000195b285d69893ad4e1c0af95b38&jobListingId=1009561005629&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp8blnd222o000-75b1809a532fc97c&cb=1742456870868&ctt=1742456884958

Senior Product Owner - $48 per hour

https://www.glassdoor.co.nz/job-listing/product-owner-data-ai-products-asurequality-JV_IC3525162_KO0,30_KE31,43.htm?jl=1009672349495&cs=1_08ef0467&s=58&t=SR&pos=104&src=GD_JOB_AD&guid=00000195b28b54b9befd8a203fdf0cc2&jobListingId=1009672349495&ea=1&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp8ml8ajdr1800-79507115f3c44640&cb=1742457230884&ctt=1742457239278

Senior VR Developer - $46 per hour

https://www.seek.co.nz/job/82471580?type=promoted&ref=search-standalone&origin=cardTitle#sol=077b2a7917309a47ff35c3d0496275e95285e244

Intermediate Full Stack Software Engineer - $33 per hour

https://www.seek.co.nz/job/82758697?type=standard&ref=search-standalone&origin=cardTitle#sol=1f6ec098bbebe4ded5ecba67a912927d61441054

Associate Full Stack Software Engineer – $28 per hour

https://www.glassdoor.co.nz/Salary/Aderant-Associate-Software-Engineer-Salaries-E37370_D_KO8,35.htm

Senior QA Engineer - $34 per hour

https://www.glassdoor.co.nz/job-listing/senior-qa-engineer-payment-product-binance-JV_IC3525162_KO0,34_KE35,42.htm?jl=1009335940342&src=GD_JOB_AD&uido=65FC4472BDEC32AAD12883C19DB458B2&ao=1136043&jrtk=5-pdx1-0-1impacp24gqnl800-2c32325891c848b1&cs=1_12244bb7&s=58&t=SR&pos=102&guid=00000195b2a663e695acf38a3d7b45b8&jobListingId=1009335940342&ea=1&vt=w&cb=1742459004143&ctt=1742459011545

Senior VR Designer/Content Developer - $35 per hour

https://www.glassdoor.co.nz/job-listing/game-director-lead-game-designer-tencent-JV_IC3525162_KO0,32_KE33,40.htm?jl=1009649781596&cs=1_3e9eaa24&s=343&t=SR-JOBS-HR&pos=102&src=GD_JOB_AD&guid=00000195b2a948ee89ebfea76a296686&uido=65FC4472BDEC32AAD12883C19DB458B2&jobListingId=1009649781596&ao=1136043&vt=w&jrtk=5-pdx1-0-1impaij15gqmt800-af997ef44ac85d47&cb=1742459194620&ctt=1742459202771

Trainer - $36 per hour

https://www.seek.co.nz/job/82815772?type=standard&ref=search-standalone&origin=cardTitle#sol=84016d139461aca38e6d722bb3f7f84abd331b3e

Developer Intern - $25 per hour

https://www.sjs.co.nz/job-details/21526/mechatronics-rnd-engineer-intern-casualpartfull-time-cbd/

Laptops - $1300 x 20 = $26000

https://www.dell.com/en-nz/shop/dell-laptops/inspiron-15-laptop/spd/inspiron-15-3520-laptop/oin3520100901mnzh?ref=variantstack

VR hardware - $650 x 12 = $7800

https://www.pbtech.co.nz/product/MVRMTA0024/META-Quest-3s-128GB-Mixed-Reality-Headset-with-2x?qr=GShopping&gad_source=1&gclid=Cj0KCQjw-e6-BhDmARIsAOxxlxVaWUoXJIuyEoiQJ3eRXoX368WtnsJzZHLHL6e3mIZI5g8FZ-UVGZwaAntYEALw_wcB

Azure Subscription - $432 per month

https://azure.microsoft.com/en-us/pricing/calculator/?ef_id=_k_Cj0KCQjw-e6-BhDmARIsAOxxlxX14GT6Xgk_PIpmy9nZve2RbTFsrkhuQPFPnsWSuwNOKvzvVE6FhBAaAhw8EALw_wcB_k_&OCID=AIDcmmp3m06wb2_SEM__k_Cj0KCQjw-e6-BhDmARIsAOxxlxX14GT6Xgk_PIpmy9nZve2RbTFsrkhuQPFPnsWSuwNOKvzvVE6FhBAaAhw8EALw_wcB_k_&gad_source=1&gclid=Cj0KCQjw-e6-BhDmARIsAOxxlxX14GT6Xgk_PIpmy9nZve2RbTFsrkhuQPFPnsWSuwNOKvzvVE6FhBAaAhw8EALw_wcB

VR Software Licenses - $10000 one time

https://clutch.co/developers/virtual-reality/pricing

Github - $4 x 20 = $80 per month

https://github.com/pricing

Jira - $8.6 x 20 = $172 per month