## Sheet1
[10 empty] | Role | Pay Rate Per Hour | days | hours
[10 empty] | HR Manager | 53 | 5 | 8 | 2120 | Budget Categories | Description | Cost
[6 empty] | HR Manager | 60 |  | 10000 | Engineering Manager | 51 | 96 | 8 | 39168 | Labour Cost | Manpower Cost | 491528
[6 empty] | Engineering Manager | 60 |  | 328 | Senior Platforms Engineer | 52 | 96 | 8 | 39936 | Accessories | Laptops and Mouse | 4000
[6 empty] | Senior Platforms Engineer | 56 |  | 7800 | Risk Management Specialist | 34 | 96 | 8 | 26112 | Rent | Monthly Rent | 0
72000 |  |  | 1300 |  | 650 | Risk Management Specialist | 28 | sprint 0 | 26000 | Cultural Consultant | 42 | 96 | 8 | 32256 | Electricity | Montly Electricity | 0
12 |  |  | 20 |  | 12 | Cultural Consultant | 42 |  | 2400 | Senior Product Owner | 48 | 96 | 8 | 36864 | Software Licenses | Licenses for Jira, Unreal Engine, Github, and Azure | 3420
20 |  |  | 26000 |  | 7800 | Senior Product Owner | 52 |  | 5760 | Senior VR Software Engineer 1 | 46 | 96 | 8 | 35328 | Laptops | $1300 x 20 Laptops for the development Team | 26000
8 | [5 empty] | Senior VR Software Engineer 1 | 50 |  | 5376 | Senior VR Software Engineer 2 | 46 | 96 | 8 | 35328 | VR Hardware | $650 x 20 for the development team | 13000
37.5 | [5 empty] | Associate full stack software Engineer 2 | 32 |  | 4032 | Intermediate Full stack software engineer 1 | 33 | 96 | 8 | 25344 | Miscellaneous | 5% for other expenses | 26897.4
[6 empty] | Fullstack software engineer Intern 5 | 25 |  |  | Intermediate Full stack software engineer 2 | 33 | 96 | 8 | 25344 | Total |  | 564845.4
[6 empty] | Senior QA Engineer | 37 |  |  | Associate full stack software Engineer 1 | 28 | 96 | 8 | 21504
[6 empty] | Senior VR Designer/Content Developer | 37 |  |  | Associate full stack software Engineer 2 | 28 | 96 | 8 | 21504
[6 empty] | Trainer | 38 |  |  | Fullstack software engineer Intern 1 | 25 | 96 | 8 | 19200
|  |  |  | 172 |  | Senior VR Software Engineer 2 | 50 |  |  | Fullstack software engineer Intern 2 | 25 | 96 | 8 | 19200
110000 | [5 empty] | Intermediate Full stack software engineer 2 | 42 |  |  | Fullstack software engineer Intern 3 | 25 | 96 | 8 | 19200
12 | 52 |  |  |  |  | Intermediate Full stack software engineer 1 | 42 |  |  | Fullstack software engineer Intern 4 | 25 | 96 | 8 | 19200
20 | 40 | 328 |  |  |  | Associate full stack software Engineer 1 | 32 |  |  | Fullstack software engineer Intern 5 | 25 | 96 | 8 | 19200
8 |  | 5 |  |  |  | Fullstack software engineer Intern 4 | 25 |  |  | Senior QA Engineer | 34 | 96 | 8 | 26112
57.2917 | 52.8846 | 1640 |  | 650 |  | Fullstack software engineer Intern 3 | 25 |  |  | Senior VR Designer/Content Developer | 35 | 96 | 8 | 26880
|  |  |  | 15 |  | Fullstack software engineer Intern 2 | 25 |  |  | Trainer | 36 | 6 | 8 | 1728
|  |  |  | 9750 |  | Fullstack software engineer Intern 1 | 25 |  |  | Electricity | 0 | 0 | 0 | 0
[6 empty] | VR Licenses | 10000 |  |  | Rent | 0 | 0 | 0 | 0
[10 empty] | Keyboard | 45 | 1 | 20 | 900
[6 empty] | Azure Subscription | 328 |  |  | Mouse | 20 | 1 | 20 | 400 | Budget Categories | Cost
|  | 172 |  |  |  | VR Hardware | 7800 |  |  | Jira | 172 | 1 | 5 | 860 | Material | 73317.4
|  | 5 |  |  |  | Laptops | 26000 |  |  | Laptops | 1300 | 1 | 20 | 26000 | Work | 491528
[10 empty] | VR Hardware | 650 | 1 | 20 | 13000 | Miscellaneous
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0 | Total | 564845.4
[10 empty] | Github | 4 | 5 | 20 | 400
[10 empty] | Azure Subscription | 432 | 5 | 1 | 2160
Materials
Item
[14 empty] | 535248 | Electricity
[10 empty] | Misscelaneous |  |  | 5% | 26762.4 | Rent
[14 empty] | 562010.4 | Accessories
Jira
Laptops
VR Hardware
Unreal Engine License
[10 empty] | Sprint 0 |  |  |  |  | Github
[10 empty] | HR Manager | 53 | 5 | 8 | 2120 | Azure Subscription
[10 empty] | Engineering Manager | 51 | 10 | 8 | 4080
[10 empty] | Senior Platforms Engineer | 52 | 10 | 8 | 4160
[10 empty] | Risk Management Specialist | 34 | 10 | 8 | 2720
[10 empty] | Cultural Consultant | 42 | 10 | 8 | 3360 | Expenses | Cost
[10 empty] | Senior Product Owner | 48 | 10 | 8 | 3840 | Material
[10 empty] | Senior VR Software Engineer 1 | 46 | 10 | 8 | 3680
[10 empty] | Senior VR Software Engineer 2 | 46 | 10 | 8 | 3680
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 10 | 8 | 2640 | Role | hours | hourly rate | total cost | source
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 10 | 8 | 2640 | HR Manager | 8 hours x 5 days | 53 | 2120 | HR Manager
[10 empty] | Associate full stack software Engineer 1 | 28 | 10 | 8 | 2240 | Project Manager | 8 hours x 96 days | 51 | 39168 | Project Manager
[10 empty] | Associate full stack software Engineer 2 | 28 | 10 | 8 | 2240 | Senior Platforms Engineer | 8 hours x 96 days | 52 | 39936 | Senior Platforms Engineer
[10 empty] | Fullstack software engineer Intern 1 | 25 | 10 | 8 | 2000 | Risk Management Specialist | 8 hours x 96 days | 34 | 26112 | Risk Management Specialist
[10 empty] | Fullstack software engineer Intern 2 | 25 | 10 | 8 | 2000 | Cultural Consultant | 8 hours x 96 days | 42 | 32256 | Cultural Consultant
[10 empty] | Fullstack software engineer Intern 3 | 25 | 10 | 8 | 2000 | Senior Product Owner | 8 hours x 96 days | 48 | 36864 | Senior Product Owner
[10 empty] | Fullstack software engineer Intern 4 | 25 | 10 | 8 | 2000 | Senior VR Software Engineer 1 | 8 hours x 96 days | 46 | 35328 | Senior VR Software Engineer
[10 empty] | Fullstack software engineer Intern 5 | 25 | 10 | 8 | 2000 | Senior VR Software Engineer 2 | 8 hours x 96 days | 46 | 35328 | Senior VR Software Engineer
[10 empty] | Senior QA Engineer | 34 | 10 | 8 | 2720 | Intermediate Full stack software engineer 1 | 8 hours x 96 days | 33 | 25344 | Intermediate Full stack software engineer
[10 empty] | Senior VR Designer/Content Developer | 35 | 10 | 8 | 2800 | Intermediate Full stack software engineer 2 | 8 hours x 96 days | 33 | 25344 | Intermediate Full stack software engineer
[10 empty] | Trainer | 36 | 0 | 8 | 0 | Associate full stack software Engineer 1 | 8 hours x 96 days | 28 | 21504 | Associate full stack software Engineer
[10 empty] | Electricity | 0 | 0 | 0 | 0 | Associate full stack software Engineer 2 | 8 hours x 96 days | 28 | 21504 | Associate full stack software Engineer
[10 empty] | Rent | 0 | 0 | 0 | 0 | Fullstack software engineer Intern 1 | 8 hours x 96 days | 25 | 19200 | Fullstack software engineer Intern
[10 empty] | Accessories | 200 | 1 | 20 | 1300 | Fullstack software engineer Intern 2 | 8 hours x 96 days | 25 | 19200 | Fullstack software engineer Intern
[10 empty] | Jira | 172 | 1 | 5 | 860 | Fullstack software engineer Intern 3 | 8 hours x 96 days | 25 | 19200 | Fullstack software engineer Intern
[10 empty] | Laptops | 1300 | 1 | 20 | 26000 | Fullstack software engineer Intern 4 | 8 hours x 96 days | 25 | 19200 | Fullstack software engineer Intern
[10 empty] | VR Hardware | 650 | 1 | 20 | 13000 | Fullstack software engineer Intern 5 | 8 hours x 96 days | 25 | 19200 | Fullstack software engineer Intern
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0 | Senior QA Engineer | 8 hours x 96 days | 34 | 26112 | Senior QA Engineer
[10 empty] | Github | 4 | 5 | 20 | 400 | Senior VR Designer/Content Developer | 8 hours x 96 days | 35 | 26880 | Senior VR Designer/Content Developer
[10 empty] | Azure Subscription | 432 | 5 | 1 | 2160 | Trainer | 8 hours x 6 days | 36 | 1728 | Trainer
[15 empty] | Total |  |  | 491528
[13 empty] | Sprint 0 | 96640
[10 empty] | Misscelaneous |  |  | 5% | 4832
[14 empty] | 101472 | material | quantity | cost per unit | total cost | purpose | source
[15 empty] | Keyboard | 20 pcs | 45 | 900 | For the use of employees | PowerPlay Keyboard
[15 empty] | Mouse | 20 pcs | 20 | 400 | For the use of employees | Warehouse Mouse
[15 empty] | Jira | 5 months | 172 | 860 | License for use of Jira | Jira
[10 empty] | Sprint 1 |  |  |  |  | Laptops | 20 pcs | 1300 | 26000 | For the use of employees | Dell Laptop
[10 empty] | HR Manager | 53 | 0 | 8 | 0 | VR Hardware | 20 pcs | 650 | 13000 | For the use of employees | Meta Quest
[10 empty] | Engineering Manager | 51 | 7 | 8 | 2856 | Unreal Engine License | 0 | 0 | 0 | license for VR development | Unreal Engine
[10 empty] | Senior Platforms Engineer | 52 | 7 | 8 | 2912 | Github | 20 pcs x 5 months | 4 | 400 | license for Github repository | Github
[10 empty] | Risk Management Specialist | 34 | 7 | 8 | 1904 | Azure Subscription | 5 months | 432 | 2160 | license for cloud use | Azure Calculator
[10 empty] | Cultural Consultant | 42 | 7 | 8 | 2352 | Electricity | 0 | 0 | 0 | no electricity (remote work)
[10 empty] | Senior Product Owner | 48 | 7 | 8 | 2688 | Rent | 0 | 0 | 0 | no rent (remote work)
[10 empty] | Senior VR Software Engineer 1 | 46 | 7 | 8 | 2576 | Total |  |  | 43720
[10 empty] | Senior VR Software Engineer 2 | 46 | 7 | 8 | 2576
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 7 | 8 | 1848
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 7 | 8 | 1848 | Budget Categories | Cost
[10 empty] | Associate full stack software Engineer 1 | 28 | 7 | 8 | 1568 | Material | 43720
[10 empty] | Associate full stack software Engineer 2 | 28 | 7 | 8 | 1568 | Work | 491528
[10 empty] | Fullstack software engineer Intern 1 | 25 | 7 | 8 | 1400 | Miscellaneous(5%) | 26762.4
[10 empty] | Fullstack software engineer Intern 2 | 25 | 7 | 8 | 1400 | Total | 562010.4
[10 empty] | Fullstack software engineer Intern 3 | 25 | 7 | 8 | 1400
[10 empty] | Fullstack software engineer Intern 4 | 25 | 7 | 8 | 1400
[10 empty] | Fullstack software engineer Intern 5 | 25 | 7 | 8 | 1400
[10 empty] | Senior QA Engineer | 34 | 7 | 8 | 1904
[10 empty] | Senior VR Designer/Content Developer | 35 | 7 | 8 | 1960
[10 empty] | Trainer | 36 | 0 | 8 | 0
[10 empty] | Electricity | 0 | 0 | 0 | 0
[10 empty] | Rent | 0 | 0 | 0 | 0
[10 empty] | Accessories | 200 | 0 | 20 | 0
[10 empty] | Jira | 172 | 0 | 5 | 0
[10 empty] | Laptops | 1300 | 0 | 20 | 0
[10 empty] | VR Hardware | 650 | 0 | 20 | 0
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0
[10 empty] | Github | 4 | 0 | 20 | 0
[10 empty] | Azure Subscription | 432 | 0 | 1 | 0
[13 empty] | Sprint 1 | 35560
[10 empty] | Misscelaneous |  |  | 5% | 1778
37338
Sprint 2
[10 empty] | HR Manager | 53 | 0 | 8 | 0
[10 empty] | Engineering Manager | 51 | 13 | 8 | 5304
[10 empty] | Senior Platforms Engineer | 52 | 13 | 8 | 5408
[10 empty] | Risk Management Specialist | 34 | 13 | 8 | 3536
[10 empty] | Cultural Consultant | 42 | 13 | 8 | 4368
[10 empty] | Senior Product Owner | 48 | 13 | 8 | 4992
[10 empty] | Senior VR Software Engineer 1 | 46 | 13 | 8 | 4784
[10 empty] | Senior VR Software Engineer 2 | 46 | 13 | 8 | 4784
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 13 | 8 | 3432
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 13 | 8 | 3432
[10 empty] | Associate full stack software Engineer 1 | 28 | 13 | 8 | 2912
[10 empty] | Associate full stack software Engineer 2 | 28 | 13 | 8 | 2912
[10 empty] | Fullstack software engineer Intern 1 | 25 | 13 | 8 | 2600
[10 empty] | Fullstack software engineer Intern 2 | 25 | 13 | 8 | 2600
[10 empty] | Fullstack software engineer Intern 3 | 25 | 13 | 8 | 2600
[10 empty] | Fullstack software engineer Intern 4 | 25 | 13 | 8 | 2600
[10 empty] | Fullstack software engineer Intern 5 | 25 | 13 | 8 | 2600
[10 empty] | Senior QA Engineer | 34 | 13 | 8 | 3536
[10 empty] | Senior VR Designer/Content Developer | 35 | 13 | 8 | 3640
[10 empty] | Trainer | 36 | 0 | 8 | 0
[10 empty] | Electricity | 0 | 0 | 0 | 0
[10 empty] | Rent | 0 | 0 | 0 | 0
[10 empty] | Accessories | 200 | 0 | 20 | 0
[10 empty] | Jira | 172 | 0 | 5 | 0
[10 empty] | Laptops | 1300 | 0 | 20 | 0
[10 empty] | VR Hardware | 650 | 0 | 20 | 0
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0
[10 empty] | Github | 4 | 0 | 20 | 0
[10 empty] | Azure Subscription | 432 | 0 | 1 | 0
[13 empty] | Sprint 2 | 66040
[10 empty] | Misscelaneous |  |  | 5% | 3302
69342
Sprint 3
[10 empty] | HR Manager | 53 | 0 | 8 | 0
[10 empty] | Engineering Manager | 51 | 9 | 8 | 3672
[10 empty] | Senior Platforms Engineer | 52 | 9 | 8 | 3744
[10 empty] | Risk Management Specialist | 34 | 9 | 8 | 2448
[10 empty] | Cultural Consultant | 42 | 9 | 8 | 3024
[10 empty] | Senior Product Owner | 48 | 9 | 8 | 3456
[10 empty] | Senior VR Software Engineer 1 | 46 | 9 | 8 | 3312
[10 empty] | Senior VR Software Engineer 2 | 46 | 9 | 8 | 3312
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 9 | 8 | 2376
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 9 | 8 | 2376
[10 empty] | Associate full stack software Engineer 1 | 28 | 9 | 8 | 2016
[10 empty] | Associate full stack software Engineer 2 | 28 | 9 | 8 | 2016
[10 empty] | Fullstack software engineer Intern 1 | 25 | 9 | 8 | 1800
[10 empty] | Fullstack software engineer Intern 2 | 25 | 9 | 8 | 1800
[10 empty] | Fullstack software engineer Intern 3 | 25 | 9 | 8 | 1800
[10 empty] | Fullstack software engineer Intern 4 | 25 | 9 | 8 | 1800
[10 empty] | Fullstack software engineer Intern 5 | 25 | 9 | 8 | 1800
[10 empty] | Senior QA Engineer | 34 | 9 | 8 | 2448
[10 empty] | Senior VR Designer/Content Developer | 35 | 9 | 8 | 2520
[10 empty] | Trainer | 36 | 0 | 8 | 0
[10 empty] | Electricity | 0 | 0 | 0 | 0
[10 empty] | Rent | 0 | 0 | 0 | 0
[10 empty] | Accessories | 200 | 0 | 20 | 0
[10 empty] | Jira | 172 | 0 | 5 | 0
[10 empty] | Laptops | 1300 | 0 | 20 | 0
[10 empty] | VR Hardware | 650 | 0 | 20 | 0
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0
[10 empty] | Github | 4 | 0 | 20 | 0
[10 empty] | Azure Subscription | 432 | 0 | 1 | 0
[13 empty] | Sprint 3 | 45720
[10 empty] | Misscelaneous |  |  | 5% | 2286
48006
Sprint 4
[10 empty] | HR Manager | 53 | 0 | 8 | 0
[10 empty] | Engineering Manager | 51 | 13 | 8 | 5304
[10 empty] | Senior Platforms Engineer | 52 | 13 | 8 | 5408
[10 empty] | Risk Management Specialist | 34 | 13 | 8 | 3536
[10 empty] | Cultural Consultant | 42 | 13 | 8 | 4368
[10 empty] | Senior Product Owner | 48 | 13 | 8 | 4992
[10 empty] | Senior VR Software Engineer 1 | 46 | 13 | 8 | 4784
[10 empty] | Senior VR Software Engineer 2 | 46 | 13 | 8 | 4784
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 13 | 8 | 3432
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 13 | 8 | 3432
[10 empty] | Associate full stack software Engineer 1 | 28 | 13 | 8 | 2912
[10 empty] | Associate full stack software Engineer 2 | 28 | 13 | 8 | 2912
[10 empty] | Fullstack software engineer Intern 1 | 25 | 13 | 8 | 2600
[10 empty] | Fullstack software engineer Intern 2 | 25 | 13 | 8 | 2600
[10 empty] | Fullstack software engineer Intern 3 | 25 | 13 | 8 | 2600
[10 empty] | Fullstack software engineer Intern 4 | 25 | 13 | 8 | 2600
[10 empty] | Fullstack software engineer Intern 5 | 25 | 13 | 8 | 2600
[10 empty] | Senior QA Engineer | 34 | 13 | 8 | 3536
[10 empty] | Senior VR Designer/Content Developer | 35 | 13 | 8 | 3640
[10 empty] | Trainer | 36 | 3 | 8 | 864
[10 empty] | Electricity | 0 | 0 | 0 | 0
[10 empty] | Rent | 0 | 0 | 0 | 0
[10 empty] | Accessories | 200 | 0 | 20 | 0
[10 empty] | Jira | 172 | 0 | 5 | 0
[10 empty] | Laptops | 1300 | 0 | 20 | 0
[10 empty] | VR Hardware | 650 | 0 | 20 | 0
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0
[10 empty] | Github | 4 | 0 | 20 | 0
[10 empty] | Azure Subscription | 432 | 0 | 1 | 0
[13 empty] | Sprint 4 | 66904
[10 empty] | Misscelaneous |  |  | 5% | 3345.2
70249.2
Sprint 5
[10 empty] | HR Manager | 53 | 0 | 8 | 0
[10 empty] | Engineering Manager | 51 | 6 | 8 | 2448
[10 empty] | Senior Platforms Engineer | 52 | 6 | 8 | 2496
[10 empty] | Risk Management Specialist | 34 | 6 | 8 | 1632
[10 empty] | Cultural Consultant | 42 | 6 | 8 | 2016
[10 empty] | Senior Product Owner | 48 | 6 | 8 | 2304
[10 empty] | Senior VR Software Engineer 1 | 46 | 6 | 8 | 2208
[10 empty] | Senior VR Software Engineer 2 | 46 | 6 | 8 | 2208
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 6 | 8 | 1584
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 6 | 8 | 1584
[10 empty] | Associate full stack software Engineer 1 | 28 | 6 | 8 | 1344
[10 empty] | Associate full stack software Engineer 2 | 28 | 6 | 8 | 1344
[10 empty] | Fullstack software engineer Intern 1 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 2 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 3 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 4 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 5 | 25 | 6 | 8 | 1200
[10 empty] | Senior QA Engineer | 34 | 6 | 8 | 1632
[10 empty] | Senior VR Designer/Content Developer | 35 | 6 | 8 | 1680
[10 empty] | Trainer | 36 | 0 | 8 | 0
[10 empty] | Electricity | 0 | 0 | 0 | 0
[10 empty] | Rent | 0 | 0 | 0 | 0
[10 empty] | Accessories | 200 | 0 | 20 | 0
[10 empty] | Jira | 172 | 0 | 5 | 0
[10 empty] | Laptops | 1300 | 0 | 20 | 0
[10 empty] | VR Hardware | 650 | 0 | 20 | 0
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0
[10 empty] | Github | 4 | 0 | 20 | 0
[10 empty] | Azure Subscription | 432 | 0 | 1 | 0
[13 empty] | Sprint 5 | 30480
[10 empty] | Misscelaneous |  |  | 5% | 1524
32004
Sprint 6
[10 empty] | HR Manager | 53 | 0 | 8 | 0
[10 empty] | Engineering Manager | 51 | 6 | 8 | 2448
[10 empty] | Senior Platforms Engineer | 52 | 6 | 8 | 2496
[10 empty] | Risk Management Specialist | 34 | 6 | 8 | 1632
[10 empty] | Cultural Consultant | 42 | 6 | 8 | 2016
[10 empty] | Senior Product Owner | 48 | 6 | 8 | 2304
[10 empty] | Senior VR Software Engineer 1 | 46 | 6 | 8 | 2208
[10 empty] | Senior VR Software Engineer 2 | 46 | 6 | 8 | 2208
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 6 | 8 | 1584
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 6 | 8 | 1584
[10 empty] | Associate full stack software Engineer 1 | 28 | 6 | 8 | 1344
[10 empty] | Associate full stack software Engineer 2 | 28 | 6 | 8 | 1344
[10 empty] | Fullstack software engineer Intern 1 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 2 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 3 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 4 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 5 | 25 | 6 | 8 | 1200
[10 empty] | Senior QA Engineer | 34 | 6 | 8 | 1632
[10 empty] | Senior VR Designer/Content Developer | 35 | 6 | 8 | 1680
[10 empty] | Trainer | 36 | 0 | 8 | 0
[10 empty] | Electricity | 0 | 0 | 0 | 0
[10 empty] | Rent | 0 | 0 | 0 | 0
[10 empty] | Accessories | 200 | 0 | 20 | 0
[10 empty] | Jira | 172 | 0 | 5 | 0
[10 empty] | Laptops | 1300 | 0 | 20 | 0
[10 empty] | VR Hardware | 650 | 0 | 20 | 0
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0
[10 empty] | Github | 4 | 0 | 20 | 0
[10 empty] | Azure Subscription | 432 | 0 | 1 | 0
[13 empty] | Sprint 6 | 30480
[10 empty] | Misscelaneous |  |  | 5% | 1524
32004
Sprint 7
[10 empty] | HR Manager | 53 | 0 | 8 | 0
[10 empty] | Engineering Manager | 51 | 6 | 8 | 2448
[10 empty] | Senior Platforms Engineer | 52 | 6 | 8 | 2496
[10 empty] | Risk Management Specialist | 34 | 6 | 8 | 1632
[10 empty] | Cultural Consultant | 42 | 6 | 8 | 2016
[10 empty] | Senior Product Owner | 48 | 6 | 8 | 2304
[10 empty] | Senior VR Software Engineer 1 | 46 | 6 | 8 | 2208
[10 empty] | Senior VR Software Engineer 2 | 46 | 6 | 8 | 2208
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 6 | 8 | 1584
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 6 | 8 | 1584
[10 empty] | Associate full stack software Engineer 1 | 28 | 6 | 8 | 1344
[10 empty] | Associate full stack software Engineer 2 | 28 | 6 | 8 | 1344
[10 empty] | Fullstack software engineer Intern 1 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 2 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 3 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 4 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 5 | 25 | 6 | 8 | 1200
[10 empty] | Senior QA Engineer | 34 | 6 | 8 | 1632
[10 empty] | Senior VR Designer/Content Developer | 35 | 6 | 8 | 1680
[10 empty] | Trainer | 36 | 0 | 8 | 0
[10 empty] | Electricity | 0 | 0 | 0 | 0
[10 empty] | Rent | 0 | 0 | 0 | 0
[10 empty] | Accessories | 200 | 0 | 20 | 0
[10 empty] | Jira | 172 | 0 | 5 | 0
[10 empty] | Laptops | 1300 | 0 | 20 | 0
[10 empty] | VR Hardware | 650 | 0 | 20 | 0
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0
[10 empty] | Github | 4 | 0 | 20 | 0
[10 empty] | Azure Subscription | 432 | 0 | 1 | 0
[13 empty] | Sprint 7 | 30480
[10 empty] | Misscelaneous |  |  | 5% | 1524
32004
Sprint 8
[10 empty] | HR Manager | 53 | 0 | 8 | 0
[10 empty] | Engineering Manager | 51 | 6 | 8 | 2448
[10 empty] | Senior Platforms Engineer | 52 | 6 | 8 | 2496
[10 empty] | Risk Management Specialist | 34 | 6 | 8 | 1632
[10 empty] | Cultural Consultant | 42 | 6 | 8 | 2016
[10 empty] | Senior Product Owner | 48 | 6 | 8 | 2304
[10 empty] | Senior VR Software Engineer 1 | 46 | 6 | 8 | 2208
[10 empty] | Senior VR Software Engineer 2 | 46 | 6 | 8 | 2208
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 6 | 8 | 1584
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 6 | 8 | 1584
[10 empty] | Associate full stack software Engineer 1 | 28 | 6 | 8 | 1344
[10 empty] | Associate full stack software Engineer 2 | 28 | 6 | 8 | 1344
[10 empty] | Fullstack software engineer Intern 1 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 2 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 3 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 4 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 5 | 25 | 6 | 8 | 1200
[10 empty] | Senior QA Engineer | 34 | 6 | 8 | 1632
[10 empty] | Senior VR Designer/Content Developer | 35 | 6 | 8 | 1680
[10 empty] | Trainer | 36 | 0 | 8 | 0
[10 empty] | Electricity | 0 | 0 | 0 | 0
[10 empty] | Rent | 0 | 0 | 0 | 0
[10 empty] | Accessories | 200 | 0 | 20 | 0
[10 empty] | Jira | 172 | 0 | 5 | 0
[10 empty] | Laptops | 1300 | 0 | 20 | 0
[10 empty] | VR Hardware | 650 | 0 | 20 | 0
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0
[10 empty] | Github | 4 | 0 | 20 | 0
[10 empty] | Azure Subscription | 432 | 0 | 1 | 0
[13 empty] | Sprint 8 | 30480
[10 empty] | Misscelaneous |  |  | 5% | 1524
32004
Sprint 9
[10 empty] | HR Manager | 53 | 0 | 8 | 0
[10 empty] | Engineering Manager | 51 | 6 | 8 | 2448
[10 empty] | Senior Platforms Engineer | 52 | 6 | 8 | 2496
[10 empty] | Risk Management Specialist | 34 | 6 | 8 | 1632
[10 empty] | Cultural Consultant | 42 | 6 | 8 | 2016
[10 empty] | Senior Product Owner | 48 | 6 | 8 | 2304
[10 empty] | Senior VR Software Engineer 1 | 46 | 6 | 8 | 2208
[10 empty] | Senior VR Software Engineer 2 | 46 | 6 | 8 | 2208
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 6 | 8 | 1584
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 6 | 8 | 1584
[10 empty] | Associate full stack software Engineer 1 | 28 | 6 | 8 | 1344
[10 empty] | Associate full stack software Engineer 2 | 28 | 6 | 8 | 1344
[10 empty] | Fullstack software engineer Intern 1 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 2 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 3 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 4 | 25 | 6 | 8 | 1200
[10 empty] | Fullstack software engineer Intern 5 | 25 | 6 | 8 | 1200
[10 empty] | Senior QA Engineer | 34 | 6 | 8 | 1632
[10 empty] | Senior VR Designer/Content Developer | 35 | 6 | 8 | 1680
[10 empty] | Trainer | 36 | 0 | 8 | 0
[10 empty] | Electricity | 0 | 0 | 0 | 0
[10 empty] | Rent | 0 | 0 | 0 | 0
[10 empty] | Accessories | 200 | 0 | 20 | 0
[10 empty] | Jira | 172 | 0 | 5 | 0
[10 empty] | Laptops | 1300 | 0 | 20 | 0
[10 empty] | VR Hardware | 650 | 0 | 20 | 0
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0
[10 empty] | Github | 4 | 0 | 20 | 0
[10 empty] | Azure Subscription | 432 | 0 | 1 | 0
[13 empty] | Sprint 9 | 30480
[10 empty] | Misscelaneous |  |  | 5% | 1524
32004
Sprint 10
[10 empty] | HR Manager | 53 | 0 | 8 | 0
[10 empty] | Engineering Manager | 51 | 14 | 8 | 5712
[10 empty] | Senior Platforms Engineer | 52 | 14 | 8 | 5824
[10 empty] | Risk Management Specialist | 34 | 14 | 8 | 3808
[10 empty] | Cultural Consultant | 42 | 14 | 8 | 4704
[10 empty] | Senior Product Owner | 48 | 14 | 8 | 5376
[10 empty] | Senior VR Software Engineer 1 | 46 | 14 | 8 | 5152
[10 empty] | Senior VR Software Engineer 2 | 46 | 14 | 8 | 5152
[10 empty] | Intermediate Full stack software engineer 1 | 33 | 14 | 8 | 3696
[10 empty] | Intermediate Full stack software engineer 2 | 33 | 14 | 8 | 3696
[10 empty] | Associate full stack software Engineer 1 | 28 | 14 | 8 | 3136
[10 empty] | Associate full stack software Engineer 2 | 28 | 14 | 8 | 3136
[10 empty] | Fullstack software engineer Intern 1 | 25 | 14 | 8 | 2800
[10 empty] | Fullstack software engineer Intern 2 | 25 | 14 | 8 | 2800
[10 empty] | Fullstack software engineer Intern 3 | 25 | 14 | 8 | 2800
[10 empty] | Fullstack software engineer Intern 4 | 25 | 14 | 8 | 2800
[10 empty] | Fullstack software engineer Intern 5 | 25 | 14 | 8 | 2800
[10 empty] | Senior QA Engineer | 34 | 14 | 8 | 3808
[10 empty] | Senior VR Designer/Content Developer | 35 | 14 | 8 | 3920
[10 empty] | Trainer | 36 | 3 | 8 | 864
[10 empty] | Electricity | 0 | 0 | 0 | 0
[10 empty] | Rent | 0 | 0 | 0 | 0
[10 empty] | Accessories | 200 | 0 | 20 | 0
[10 empty] | Jira | 172 | 0 | 5 | 0
[10 empty] | Laptops | 1300 | 0 | 20 | 0
[10 empty] | VR Hardware | 650 | 0 | 20 | 0
[10 empty] | Unreal Engine License | 0 | 0 | 0 | 0
[10 empty] | Github | 4 | 0 | 20 | 0
[10 empty] | Azure Subscription | 432 | 0 | 1 | 0
[13 empty] | Sprint 10 | 71984
[10 empty] | Misscelaneous |  |  | 5% | 3599.2
75583.2
535248
562010.4
[10 empty] | 10 |  |  |  | 101472
[10 empty] | 7 |  |  |  | 37338
[10 empty] | 13 |  |  |  | 69342
[10 empty] | 9 |  |  |  | 48006
[10 empty] | 13 |  |  |  | 70249.2
[10 empty] | 6 |  |  |  | 32004
[10 empty] | 6 |  |  |  | 32004
[10 empty] | 6 |  |  |  | 32004
[10 empty] | 6 |  |  |  | 32004
[10 empty] | 6 |  |  |  | 32004
[10 empty] | 13 |  |  |  | 75583.2
562010.4
95

## Sheet12
Tangible Deliverables | Description | Importance
VR Homepage and navigation | VR homepage and navigation integrated within OP LMS. | High importance as it is the requirement
Single Sign on | Single-sign on using existing student and lecturer accounts. | High importance for seamless authentication and security
Multiple user feature | Multiplayer mode for students and observer mode for lecturers. | High importance for collaborative learning and real-time interactions
Role-playing | Role-playing scenarios for students. | High importance to enhance immersive learning
User Training Manual | User training manual on how to use OP-MedVR. | Medium importance as it supports onboarding but does not affect functionality
Feedback feature | Feedback feature for lecturers. | High importance for performance tracking and student improvement
Maori Values | Maori values and design integration into homepage and VR. | High importance for cultural responsiveness and Treaty of Waitangi compliance
Eight VR Hospital Rooms: | Rooms consists of -Emergency Room -Intensive Care Unit -Medical Ward -Operating Room -Maternity Care -Behavioural and Mental Room -Family Room -Neonatal Intensive Care Unit | High importance for covering a range of healthcare training scenarios
Source Code | Github repository of source code | High importance for system maintenance and future development
Jira | Jira artifacts | Medium importance for tracking development progress
Multiple instances | Deployed instances in three different environments: development, testing, and production | High importance for ensuring a stable and tested deployment process
Intangible Deliverables | Description | Importance
User Experience | Good User Experience for Students and Lecturers | High importance as this affects satisfaction
Error Free | No bugs and no errors during usage. | High importance as this affects satisfaction
Fast | The VR is responsive and fast for students and lecturers. | High importance as this affects satisfaction
Reliability | Available 24/7 at 99.95% uptime. | High importance as this affects satisfaction
Secured | The students’ and lecturer’s data are secure and protected. | High importance as this affects satisfaction
Scalability | Handles increasing number of users without affecting performance. | High importance as this affects satisfaction
Efficient | The code is efficient and well documented. | High importance as it affects performance and maintainability
Readability | The code is easy to maintain for future updates. | High importance for long-term development and bug fixes
Code Quality | The code has been tested for errors to ensure standards. | High importance to prevent system failures
Logging | Good logging for monitoring. | High importance for debugging and security tracking
Availability | Availability of VR for students and lecturers everywhere with Internet. | High importance to ensure accessibility
User Training | Training for the students regarding the use of OP-MedVR | Medium importance as it supports onboarding but does not affect functionality

## Sheet18
Sr. No. | Milestone | Date Became Milestone
1 | Project start | 12 March 2025 | Project start
2 | Completion of Project Vision | 14 March 2025 | Completion of Project Vision
3 | Preparation for Sprint 1 done | 25 March 2025 | Preparation for Sprint 1 done
4 | Completion of UI/UX flows | 14 April 2025 | Completion of UI/UX flows
5 | Completion of Emergency Room | 14 April 2025 | Completion of Emergency Room
6 | Completion of Deployment to Test Environment | 25 April 2025 | Completion of Deployment to Test Environment
7 | Completion of lecturer dashboard | 29 April 2025 | Completion of lecturer dashboard
8 | Completion of LMS integration | 29 April 2025 | Completion of LMS integration
9 | Completion of multi-user capabilities | 29 April 2025 | Completion of multi-user capabilities
10 | Completion of User Training and lecture to students and lecturers | 8 May 2025 | Completion of User Training and lecture to students and lecturers
11 | Completion of Intensive Care Unit | 12 May 2025 | Completion of Intensive Care Unit
12 | Deployment to production | 21 May 2025 | Deployment to production
13 | Completion of Medical Ward | 29 May 2025 | Completion of Medical Ward
14 | Completion of Operating Room | 6 June 2025 | Completion of Operating Room
15 | Completion of Maternity Care | 16 June 2025 | Completion of Maternity Care
16 | Completion of Behavioral and Mental Health Room | 24 June 2025 | Completion of Behavioral and Mental Health Room
17 | Completion of Family Room | 2 July 2025 | Completion of Family Room
18 | Completion of Neonatal Intensive Care Unit (NICU) | 10 July 2025 | Completion of Neonatal Intensive Care Unit (NICU)
19 | Completion of Manual and User Training to Students and Lecturers | 15 July 2025 | Completion of Manual and User Training to Students and Lecturers
20 | Deploy to Production | 18 July 2025 | Deploy to Production
21 | Project Closure | 23 July 2025 | Project Closure

## Sheet17
Tangible Deliverables | Description | Intangible Deliverables | Description
VR Homepage and navigation | VR homepage and navigation integrated within OP LMS. | VR Homepage and navigation | VR homepage and navigation integrated within OP LMS.
Single Sign on | Single-sign on using existing student and lecturer accounts. | Single Sign on | Single-sign on using existing student and lecturer accounts.
Multiple user feature | Multiplayer mode for students and observer mode for lecturers. | Multiple user feature | Multiplayer mode for students and observer mode for lecturers.
Role-playing | Role-playing scenarios for students. | Role-playing | Role-playing scenarios for students.
User Training Manual | User training manual on how to use OP-MedVR. | User Training Manual | User training manual on how to use OP-MedVR.
Feedback feature | Feedback feature for lecturers. | Feedback feature | Feedback feature for lecturers.
Maori Values | Maori values and design integration into homepage and VR. | Maori Values | Maori values and design integration into homepage and VR.
Eight VR Hospital Rooms: | Rooms consists of -Emergency Room -Intensive Care Unit -Medical Ward -Operating Room -Maternity Care -Behavioural and Mental Room -Family Room -Neonatal Intensive Care Unit | Eight VR Hospital Rooms: | Rooms consists of -Emergency Room -Intensive Care Unit -Medical Ward -Operating Room -Maternity Care -Behavioural and Mental Room -Family Room -Neonatal Intensive Care Unit
Source Code | Github repository of source code | Source Code | Github repository of source code
Jira | Jira artifacts | Jira | Jira artifacts
Multiple instances | Deployed instances in three different environments: development, testing, and production | Multiple instances | Deployed instances in three different environments: development, testing, and production

## Sheet11
Quality Control | Metrics | Implementation in the Project
Unit testing and test coverage | Compliance to local testing and unit test coverage | Provide unit tests and sufficient unit test coverage during the development of each VR rooms.
Code Review | Compliance to Acceptance Criteria | As part of development, the code is sent to other engineers to review the code done for each task.
Quality assurance check | Compliance with testing | After developing each task, it is sent to the Quality Assurance Engineer to test the new features.
Design feedback | Compliance with customer design | After designing each room, it is checked with the lecturers and students of OP before proceeding with development
Sprint Review | Compliance with Integration | After approval from Quality Assurance, each feature done during each sprint is demonstrated to the stakeholders for approval.
Audit Control | Metrics | Implementation in the Project
New Zealand Qualifications Authority (NZQA) | Compliance with healthcare education standards | Review to ensure OP-MedVR complies with healthcare education standards during preparation of pre-prod requirements
Maori Council | Compliance to Treaty of Waitangi | Before each deployment to production, audit check with Maori Council is done to ensure that the content is culturally appropriate
Closure Task | Description | Artifacts
The scrum boards (Jira) will be archived, and documentation is organized. | Scrum board (Jira) will be archived. It will be inaccessible, but the sprint data can still be viewed. The documentations and links are organized. | Documentations Sprint Data
Meetings with the Operations Team | Walkthrough the key user stories remaining (if there is any) in the backlog Discuss the sprint artifacts and sprint data. Knowledge sharing regarding end-to-end functionality of OP-MedVR Access controls are given to the Operations Team | Knowledge sharing recordings Sprint artifacts and sprint data Sprint backlog Access controls
The project is handed to the Operations Team | Artifacts, source code repositories are given to the Operations Team The user-training manual is also given to the Operations Team | Source code repository User-training manual
Final Review of the project | Final sprint review including the stakeholders to review the final scope that was complete, the budget, and the schedule. | Sprint velocity Sprint data
Sprint Retrospective | A final retrospective is completed as a team to document on lessons learned, identify process improvements. | Retrospective board

## Sheet16
Maori Value | Description
Whanaungatanga | Enable inclusion of full translations to Te Reo Māori language in VR settings, and adding Māori phrases in dialogues in other languages (Hudson et al., 2023).
Enable inclusion of Māori greetings in startup of VR (Andrade et al., 2021).
Enable inclusion of Māori Visual art in background of hospital rooms (eg. Paintings in Family room) (Brown, 2008).
Enable inclusion of Māori history in dialogues (Shedlock (Ngāpuhi & Hudson (Te Whakatōhea), 2022).
Enable inclusion of Māori celebrations in the VR background, like Matariki(New Year) (Hudson et al., 2023)
Whanaungatanga | Enable inclusion of rendering rubbish bins in VR to educate students on proper waste segregation (Castronovo et al., 2018).
Enable inclusion of dialogues and scenarios in VR regarding handling wastes (Castronovo et al., 2018).
Enable inclusion of scenarios and dialogues in VR for the students and teachers to pledge to care for their environment (Sterman et al., 2015).
Final sprint review including the stakeholders to review the final scope that was complete, the budget, and the schedule.
A final retrospective is completed as a team to document on lessons learned, identify process improvements.

## Sheet14
8.1
Stakeholder | Role | Influence Level | Decisional Influence | Internal/External
OP Sponsor | OP Sponsor will be the owner of the project | 5 | 5 | Internal
OP Professors / Lecturers | The professors will use the VR after deployment | 4 | 4 | Internal
Māori consultants | Their Māori knowledge will affect the usability | 4 | 4 | External
OP Students | They will use the VR after production | 3 | 3 | Internal
Operations Team | They will maintain the VR after project closure | 2 | 2 | Internal
Manager and Development Team | In charge with development of VR | 4 | 4 | Internal
External Auditors | In charge of checking for standards(NZQA, Maori Council, regression testers, and penetration testers) | 3 | 3 | External
8.2
Stakeholder | Role | Purpose | Mode / Channel | Frequency | Time | Participants
OP Sponsor | Project Oversight | Ensure funding and project alignment | Sprint Meetings, emails | Weekly | Wednesday 3-5pm | OP Sponsor, Project Manager, Development Team
Project Manager | Project Coordination and Employee development | Project and employee guidance | Sprint Meetings, emails | Daily | Daily 10am-10:15am | Project Manager, Development Team
OP Professors / Lecturers | Project assessment | Provide feedback about design and use | Sprint review meetings, emails | Twice a week | Every Tuesday and Thursday 1pm-2pm | Project Manager, Development Team, OP Students
Maori Consultants | Cultural content assessment | Provide feedback about Maori values | Meetings, emails, interviews | Monthly | Every first Monday of the Month 1pm-2pm | Project Manager, Development Team, OP Sponsor
OP Students | Project Assessment | Provide feedback about design and use | Sprint review meetings, emails | Twice a week | Every Tuesday and Thursday 1pm-2pm | Project Manager, Development Team, OP Lecturers
Development Team | Infrastructure, software development and software testing | Creation and integration of OP-MedVR | Sprint Meetings, emails | Daily | Daily 10am-10:15am | Project Manager
HR Manager | Employee hiring | Hiring of Development Team | Sprint Meetings, emails | Daily | Daily 10am-10:15am | Project Manager, Development Team
Trainers | Training | Provide Training to students | Training meetings, emails | Monthly | Every first Monday of the Month 3pm-4pm | Project Manager, Development Team
New Zealand Qualifications Authority (NZQA) | New Zealand Quality Assessment | Provide feedback about NZ Quality | Audit Meetings, emails | Monthly | Every first Monday of the Month 2pm-3pm | Project Manager, Development Team, OP Sponsor

## Sheet0
Project name | OP Virtual Reality Learning Platform for Healthcare Training (OP-MedVR)
Project Type | Software product development – Healthcare Virtual Reality Learning Platform
Project Manager | Gielo Joseph Fernandez
Project Goals | Develop VR platform that simulates real-world healthcare scenarios such as patient diagnosis and emergency response within virtual hospital environment. Implement multi-user capabilities and feedback system to allow lecturers to assess student performance during simulations. Create user training and support for student and lecturers on how to use OP-MedVR.
Project Deliverables | Tangible deliverables: -VR homepage and navigation integrated within OP LMS. -Single-sign on using existing student and lecturer accounts. -Multiplayer mode for students and observer mode for lecturers. -Role-playing scenarios for students. -User training manual on how to use OP-MedVR. -Feedback feature for lecturers. -Maori values and design integration into homepage and VR. - Eight VR Hospital Rooms: -Emergency Room -Intensive Care Unit -Medical Ward -Operating Room -Maternity Care -Behavioural and Mental Room -Family Room -Neonatal Intensive Care Unit -Github repository of source code -Jira artifacts -Deployed instances in three different environments: development, testing, and production
Manager and Development Team | In charge with development of VR
Intangible deliverables: -Good User Experience for students and lecturers. -No bugs and no errors during usage. -The VR is responsive and fast for students and lecturers. -Available 24/7 at 99.95% uptime. -The students’ and lecturer’s data are secure and protected. -The VR has scalability feature which handles increasing number of users without affecting performance. -The code is efficient and well documented. -The code is easy to maintain for future updates. -The code has been tested for errors to ensure standards. -Good logging for monitoring. -Availability of VR for students and lecturers everywhere with Internet. -Server logging mechanism to check for hardware/software issues. -User training for students and lecturers.
Project Methodology | Agile - Scrum
Project Budget | Phase Estimated Cost Sprint 0 $101,472.00 Sprint 1 $37,338.00 Sprint 2 $69,342.00 Sprint 3 $48,006.00 Sprint 4 $70,249.20 Sprint 5 $32,004.00 Sprint 6 $32,004.00 Sprint 7 $32,004.00 Sprint 8 $32,004.00 Sprint 9 $32,004.00 Sprint 10 $75,583.20 Total Cost $562,010.40
Project Schedule | Start Date: 12 March 2025 Estimated Completion Date: 23 July 2025 Estimated Duration: 96 days
Milestones | Date Milestones | Date | Milestones
| 12 March 2025 Project start | 12 March 2025 | Project start
| 14 March 2025 Completion of Project Vision | 14 March 2025 | Completion of Project Vision
| 25 March 2025 Preparation for Sprint 1 done | 25 March 2025 | Preparation for Sprint 1 done
| 14 April 2025 Completion of UI/UX flows | 14 April 2025 | Completion of UI/UX flows
| 14 April 2025 Completion of Emergency Room | 14 April 2025 | Completion of Emergency Room
| 25 April 2025 Completion of Deployment to Test Environment | 25 April 2025 | Completion of Deployment to Test Environment
| 29 April 2025 Completion of lecturer dashboard | 29 April 2025 | Completion of lecturer dashboard
| 29 April 2025 Completion of LMS integration | 29 April 2025 | Completion of LMS integration
| 29 April 2025 Completion of multi-user capabilities | 29 April 2025 | Completion of multi-user capabilities
| 8 May 2025 Completion of User Training and lecture to students and lecturers | 8 May 2025 | Completion of User Training and lecture to students and lecturers
| 12 May 2025 Completion of Intensive Care Unit | 12 May 2025 | Completion of Intensive Care Unit
| 21 May 2025 Deployment to production | 21 May 2025 | Deployment to production
| 29 May 2025 Completion of Medical Ward | 29 May 2025 | Completion of Medical Ward
| 6 June 2025 Completion of Operating Room | 6 June 2025 | Completion of Operating Room
| 16 June 2025 Completion of Maternity Care | 16 June 2025 | Completion of Maternity Care
| 24 June 2025 Completion of Behavioral and Mental Health Room | 24 June 2025 | Completion of Behavioral and Mental Health Room
| 2 July 2025 Completion of Family Room | 2 July 2025 | Completion of Family Room
| 10 July 2025 Completion of Neonatal Intensive Care Unit (NICU) | 10 July 2025 | Completion of Neonatal Intensive Care Unit (NICU)
| 15 July 2025 Completion of Manual and User Training to Students and Lecturers | 15 July 2025 | Completion of Manual and User Training to Students and Lecturers
| 18 July 2025 Deploy to Production | 18 July 2025 | Deploy to Production
| 23 July 2025 Project Closure | 23 July 2025 | Project Closure
Risks | • Tasks might take more time to complete as the tasks are assigned to interns. • The buffer did not consider sick leaves and absences of employees. • Students or lecturers may be hesitant and avoid using the new VR. • Malfunctions of hardware and software • VR simulations might not reflect the Maori practices.

## Sheet7
|  | Assumptions | Explanation
|  | All the employees in the development team are working full time | Due to the nature of the work needed to finish, the engineers not assigned a task during the period are still contributing to the sprint goals. This is because there are other aspects to it, like communicating with stakeholders, grooming backlog, testing features, bug fixes, code reviews, testing, making unit tests, communicating with students and lecturers, etc..
|  | All the employees in the development team are working remotely | To reduce costs in rent, electricity, etc., we assume that all are remotely, and from home.
|  | All the employees in the development team can start working immediately | To reduce intricacies during planning and development, we assumed that the employees are all ready to start working during preparation(sprint)
|  | The experiences of the Senior Engineers is sufficient in delivering this product | To mitigate the unknowns, we assume that the Senior Engineers have delivered similar projects in the past.
|  | Additional cost after project closure is not accounted into planning | Future costs such as licenses, electricity, etc are not accounted during planning
|  | Learning VR Platform | We assume that the students will use the OP MedVr as alternative learning methods and it will enhance their healthcare skills
|  | Budget | We assume that the allocated budget will cover from start of project to project closure
|  | Timeframe | We assume that there are no unknown delays that significantly affect delivery
Assumptions | Explanation | Assumptions | Explanation
|  | Learning VR Platform | We assume that the students will use the OP MedVr as alternative learning methods and it will enhance their healthcare skills
|  | Budget | We assume that the allocated budget will cover from start of project to project closure
|  | Timeframe | We assume that there are no unknown delays that significantly affect delivery

## Sheet8
Limitations | Explanation | Limitations | Explanation
|  | Cost | The budget approved for OP MedVR is only $564,845.40. Additional cost will be limited to the 5% miscellaneous budget
|  | Time | The project development will start at 12 March 2025 and must end at 23 July 2025.
|  | Technology | The software licenses used for the development will consider cost and features as factors The hardware used during the development will also be limited by budget allocated
|  | Experience | The skills and experience of the development team will be limited with the available skills in the market.
564845.4

## Sheet10
Exclusion | Description | Exclusion | Description
|  | Servers and other Hardware | Since we are deploying serverless, we are not deploying physical servers and would only utilize deploying in the cloud
|  | Classroom deployment | Since we are only developing the OP-MedVR, Setting up a physical VR computer room in OP is not part of the project.
|  | Software update and upgrade | Since we are only developing OP-MedVR in 5 months, any changes after it would require a new budget and planning.
|  | hardware development | We are utilizing existing VR hardware and we will not develop custom VR hardware
|  | non healthcare training | The development of VR will only cover healthcare students and will not cover other disciplines
|  | NonVR platform | The development of OP MedVR only cover the VR aspect, it will not cover other technologies (mobile, desktop, etc.)
|  | Other procurement | Procuring materials outside the proposed resources and materials and would need additional budget added

## Annual Salary
| Annual | # of weeks | per week | per hour | Rounded
HR Manager | 110000 | 52 | 40 | 52.8846 | 53
Engineering Manager | 105000 | 52 | 40 | 50.4808 | 51
Senior Platforms Engineer | 107000 | 52 | 40 | 51.4423 | 52
Risk Management Specialist | 70000 | 52 | 40 | 33.6538 | 34
Cultural Consultant | 86000 | 52 | 40 | 41.3462 | 42
Senior Product Owner | 98000 | 52 | 40 | 47.1154 | 48
Senior VR Software Engineer 1 | 95000 | 52 | 40 | 45.6731 | 46
Senior VR Software Engineer 2 | 95000 | 52 | 40 | 45.6731 | 46
Intermediate Full stack software engineer 1 | 68000 | 52 | 40 | 32.6923 | 33
Intermediate Full stack software engineer 2 | 68000 | 52 | 40 | 32.6923 | 33
Associate full stack software Engineer 1 | 58000 | 52 | 40 | 27.8846 | 28
Associate full stack software Engineer 2 | 58000 | 52 | 40 | 27.8846 | 28
Fullstack software engineer Intern 1 |  | 52 | 40 | 25 | 25
Fullstack software engineer Intern 2 |  | 52 | 40 | 25 | 25
Fullstack software engineer Intern 3 |  | 52 | 40 | 25 | 25
Fullstack software engineer Intern 4 |  | 52 | 40 | 25 | 25
Fullstack software engineer Intern 5 |  | 52 | 40 | 25 | 25
Senior QA Engineer | 70000 | 52 | 40 | 33.6538 | 34
Senior VR Designer/Content Developer | 71000 | 52 | 40 | 34.1346 | 35
Trainer | 73000 | 52 | 40 | 35.0962 | 36
42
12
20
8

## Sheet3
Phase | Details | Completion Date | Estimated Cost | Phase | Estimated Cost
Sprint 0 | Preparation | 25 March 2025 | 101472 | Sprint 0 | 104307
Sprint 1 | Design Emergency Room | 3 April 2025 | 37338 | Sprint 1 | 37338
Sprint 2 | Develop UI Develop Emergency Room | 22 April 2025 | 69342 | Sprint 2 | 69342
Sprint 3 | Develop Dashboard and Multi-user Design ICU | 5 May 2025 | 48006 | Sprint 3 | 48006
Sprint 4 | Deployment to Production Develop ICU Design Medical Ward | 22 May 2025 | 70249.2 | Sprint 4 | 70249.2
Sprint 5 | Develop Medical Ward Design Operating Room | 30 May 2025 | 32004 | Sprint 5 | 32004
Sprint 6 | Develop Operating Room Design Maternity Care | 9 June 2025 | 32004 | Sprint 6 | 32004
Sprint 7 | Develop Maternity Care Design Behavioural and Mental Health Room | 17 June 2025 | 32004 | Sprint 7 | 32004
Sprint 8 | Develop Behavioural and Mental Health Room Design Family Room | 25 June 2025 | 32004 | Sprint 8 | 32004
Sprint 9 | Develop Family Room Design NICU | 3 July 2025 | 32004 | Sprint 9 | 32004
Sprint 10 | Develop NICU Deployment to Production Project Closing | 23 July 2025 | 75583.2 | Sprint 10 | 75583.2
Total Cost |  |  | 562010.4 | Total Cost | 564845.4
Budget Categories | Cost
Material | 73317.4
Work | 491528
Total | 564845.4

## Sheet4
Stakeholder | Role | Influence Level | Decisional Influence | Internal/External
OP Head | OP head will be the owner of the project | 5 | 5 | Internal |  |  | Stakeholder | Role | Influence Level | Decisional Influence | Internal/External
OP board | OP stakeholders that will benefit from the project | 4 | 4 | Internal |  |  | OP Head | OP head will be the owner of the project | 5 | 5 | Internal
OP professors | The professors and students will use the VR after deployment | 3 | 3 | Internal |  |  | OP board | OP stakeholders that will benefit from the project | 4 | 4 | Internal
Maori consultants | Their Maori knowledge affect decisions | 3 | 3 | External |  |  | OP professors | The professors and students will use the VR after deployment | 3 | 3 | Internal
OP Students | They will use the VR after production | 2 | 2 | Internal |  |  | Maori consultants | Their Maori knowledge affect decisions | 3 | 3 | External
Operations Team | They will maintain the VR after project closure | 3 | 3 | Internal |  |  | OP Students | They will use the VR after production | 2 | 2 | Internal
[7 empty] | Operations Team | They will maintain the VR after project closure | 3 | 3 | Internal
Stakeholder | Role | Purpose | Mode/Chanel of Communication | Frequency | Time | Participants
OP Head and board | OP head will be the owner of the project | Get updates from the VR project | Sprint Planning, Sprint review, and sprint retrospective | Every start and end of sprint | 10am every Start and End of Sprint | Development Team and Stakeholders
OP professors | The professors and students will use the VR after deployment | To know how the VR is used | Sprint review | End of Sprint | 10am Every end of sprint | Development Team and Stakeholders
Maori consultants | Their Maori knowledge affect decisions | To know if the VR project follows Maori Principles | Sprint review | End of sprint | 10am Every end of sprint | Development Team and Stakeholders
OP Students | They will use the VR after production | To know how the VR is used | Sprint review | End of Sprint | 10am Every end of sprint | Development Team and Stakeholders
Operations Team | They will maintain the VR after project closure | To know how the VR is used | Sprint review | End of Sprint | 10am Every end of sprint | Development Team and Stakeholders
Stakeholder | Role | Purpose | Mode/Chanel of Communication | Frequency | Time | Participants
OP Head and board | OP head will be the owner of the project | Get updates from the VR project | Online Meeting | Planning Dates 3/12/25 3/26/25 4/4/25 5/6/25 5/23/25 6/2/25 6/10/25 6/18/25 6/26/25 7/4/25 | 10am | Development Team and Stakeholders
OP professors | The professors and students will use the VR after deployment | To know how the VR is used | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders
Maori consultants | Their Maori knowledge affect decisions | To know if the VR project follows Maori Principles | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders
OP Students | They will use the VR after production | To know how the VR is used | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders
Operations Team | They will maintain the VR after project closure | To know how the VR is used | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders

## Sheet5
Milestones | Date | Milestones | Date | Milestones
12 March 2025 |  |  | 12 March 2025 | Project start
14 March 2025 |  |  | 14 March 2025 | Completion of Project Vision
25 March 2025 | Project start |  | 25 March 2025 | Preparation for Sprint 1 done.
Completion of Project Vision
Preparation for Sprint 1 done. |  |  | 14 April 2025 | Completion of UI/UX flows.
|  |  | 14 April 2025 | Completion of Emergency Room
14 April 2025 | Completion of UI/UX flows.
14 April 2025 | Completion of Emergency Room |  | 25 April 2025 | Completion of Deployment to Test Environment
|  |  | 29 April 2025 | Completion of lecturer dashboard
25 April 2025 |  |  | 29 April 2025 | Completion of LMS integration
29 April 2025 |  |  | 29 April 2025 | Completion of multi-user capabilities
29 April 2025
29 April 2025 |  |  | 8 May 2025 | Completion of User Training and lecture to students and lecturers
8 May 2025 |  |  | 12 May 2025 | Completion of Intensive Care Unit
|  |  | 21 May 2025 | Deployment to production
12 May 2025
21 May 2025 |  |  | 29 May 2025 | Completion of Medical Ward
29 May 2025 |  |  | 6 June 2025 | Completion of Operating Room
6 June 2025 |  |  | 16 June 2025 | Completion of Maternity Care
16 June 2025 |  |  | 24 June 2025 | Completion of Behavioral and Mental Health Room
24 June 2025 |  |  | 2 July 2025 | Completion of Family Room
2 July 2025 |  |  | 10 July 2025 | Completion of Neonatal Intensive Care Unit (NICU)
|  |  | 15 July 2025 | Completion of Manual and User Training to Students and Lecturers
10 July 2025
15 July 2025 |  |  | 18 July 2025 | Deploy to Production
|  |  | 23 July 2025 | Project Closure
18 July 2025
23 July 2025 | Completion of Deployment to Test Environment
Completion of lecturer dashboard
Completion of LMS integration
Completion of multi-user capabilities
Completion of User Training and lecture to students and lecturers
Completion of Intensive Care Unit
Deployment to production
Completion of Medical Ward
Completion of Operating Room
Completion of Maternity Care
Completion of Behavioral and Mental Health Room
Completion of Family Room
Completion of Neonatal Intensive Care Unit (NICU)
Completion of Manual and User Training to Students and Lecturers
Deploy to Production
Project Closure

## Sheet2
Name | Status | Functional role | Responsibilities | Reporting To | Name | Functional role | Responsibilities | Reporting To
[5 empty] | Kakashi Hatake | OP Sponsor | Decision making for OP
[5 empty] | Gielo Joseph Fernandez | Project Manager | Leading the development team | OP Sponsor
[5 empty] | Choji Akimichi | Senior Product Owner | In charge of backlogs | Engineering Manager
[5 empty] | Tsunade Senju | HR Manager | Hiring of members | Engineering Manager
[5 empty] | Shikamaru Nara | Senior Platforms Engineer | In charge of deployment related tasks, pipeline creation | Engineering Manager
[5 empty] | Minato Namikaze | Risk Management Specialist | In charge of risk management | Engineering Manager
[5 empty] | Sakura Haruno | Cultural Consultant | Ensure Maori and other Cultural requirements are met | Engineering Manager
[5 empty] | Rock Lee | Senior VR Software Engineer 1 | In charge of development, does full-stack development and design | Engineering Manager
[5 empty] | Kiba Inuzuka | Senior VR Software Engineer 2 | In charge of development, does full-stack development and design | Engineering Manager
[5 empty] | Shino Aburame | Intermediate Full stack software engineer 1 | Full-stack development and design | Engineering Manager
[5 empty] | Kurenai Yuhi | Intermediate Full stack software engineer 2 | Full-stack development and design | Engineering Manager
[5 empty] | Kimimaro Kaguya | Associate full stack software Engineer 1 | Full-stack development and design | Engineering Manager
[5 empty] | Mei Terumi | Associate full stack software Engineer 2 | Full-stack development and design | Engineering Manager
[5 empty] | Zabuza Momochi | Fullstack software engineer Intern 1 | Full-stack development and design | Engineering Manager
[5 empty] | Konohamaru Sarutobi | Fullstack software engineer Intern 2 | Full-stack development and design | Engineering Manager
[5 empty] | Sasuke Uchiha | Fullstack software engineer Intern 3 | Full-stack development and design | Engineering Manager
[5 empty] | Naruto Uzumaki | Fullstack software engineer Intern 4 | Full-stack development and design | Engineering Manager
[5 empty] | Hinata Hyuga | Fullstack software engineer Intern 5 | Full-stack development and design | Engineering Manager
[5 empty] | Danzo Shimura | Senior QA Engineer | In charge of quality and code testing | Engineering Manager
[5 empty] | Kisame Hoshigaki | Senior VR Designer/Content Developer | In charge of VR Design, does software development as well | Engineering Manager
[5 empty] | Asuma Sarutobi | Trainer | In charge of training to students and lecturers | Engineering Manager
[5 empty] | Jinpachi Munashi | Lecturer | Lecturer assigned from OP to test the VR | OP Sponsor
[5 empty] | Kushimaru Kuriarare | Student | student assigned from OP to test the VR | OP Sponsor

## Sheet6
Tasks might take more time to complete as the tasks are assigned to interns.
The buffer did not consider sick leaves and absences of employees. | Project Risk | Probability | Impact | Risk Register | Member Responsible | Mitigation
Students or lecturers may be hesitant and avoid using the new VR. | Tasks might take more time to complete as the tasks are assigned to interns. | 4 | 4 | 4 | Senior VR Developer | Co-pair with Intermediate and Senior Developers Buffer for the tasks are assigned
Malfunctions of hardware and software | The buffer did not consider sick leaves and absences of employees. | 4 | 4 | 4 | Scrum Master | Daily standup to monitor if team needs more manpower
VR simulations might not reflect the Maori practices. | Scope Creep | 4 | 4 | 4 | Scrum Master | Define Acceptance criteria during planning Utilize Change Management request for Scope Creep
| Students or lecturers may be hesitant and avoid using the new VR. | 9 | 9 | 9 | Risk Management Specialist | Every developed VR Room is consulted with lecturers and students to fine tune it and address issues
| Bugs detected after deployment to production | 9 | 9 | 9 | Scrum Master | Delegate schedules of engineers to morning, afternoon, and evening shifts to monitoring post deployment
| Malfunctions of hardware and software | 6 | 6 | 6 | Senior Platform Developer | Added logs as feature to address technology malfunction For hardware issues, it is a limitation that is an accepted risk
| VR simulations might not reflect the Maori practices. | 6 | 6 | 6 | Cultural Consultant | Every developed VR Room is consulted with lecturers and students Maori Council and NZQA is also involved in checking the quality

## Sheet9
functional requirement | Description | Importance