AM804001: Project Management

Assessment 2: Case Study – Project Management Plan

| Study block 1 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Date issued |  |  |  |  |  |  |  |  |
| Due date |  |  |  |  | Time |  |  |  |
| Delivery: |  | Submit to Turnitin via Moodle before deadline |  |  |  |  |  |  |
| Weighting |  | 70% |  |  |  |  |  |  |
| Marks out of |  | 100 |  |  |  |  |  |  |
| Instructions |  | Complete this cover sheet and attach to you your assignment. - This assignment must be your own work. - Collusion, copying or plagiarism may result in disciplinary action. - We advise that you keep a copy of this assignment. - Word limit is 3000-3500 words Refer to following website for reference related resources: http://www.cite.auckland.ac.nz/index.php?p=quickcite |  |  |  |  |  |  |
|  |  | We confirm that: This is an original assessment and is entirely my own work. Where ideas, tables, diagrams etc. of other writers have been used, we have acknowledged the source in every case. This assignment has not been, nor will be, submitted as assessed work for any other academic course. |  |  |  |  |  |  |
| Student’s Name |  |  | ID No |  |  | Signature |  |  |
| Gielo Joseph Fernandez |  |  | 737214696 |  |  | Gielo |  |  |
| Date | March 22, 2025 |  |  | Cohort Number |  |  |  | 1 |

Table of Contents

Executive Summary	2

2. Background and Purpose	6

3. Project Scope	7

3.1. Objectives	8

3.2. Deliverables	8

3.3. Milestones	8

3.4. Technical requirements	9

3.4.1 Functional requirements	9

3.4.2 Non-functional requirement	9

3.5. Project Exclusions	10

3.6. Project Limitations	10

4. Project Assumptions	11

5. Methodology	12

5.1 Justification	12

5.2 Maori Value: how you can apply Maori values	13

6. Project Risks and Risk Management Plan	14

7. Project Organisation	17

8. Communications with Stakeholders	20

8.1 Stakeholders identification.`	20

8.2 Communication plan	21

9. Change management plan	24

10. Project Estimation Technique	25

12. Quality Control and Audit	29

13. Project Closure	30

14. Appendices	32

15. References:	37

# Executive Summary

| Project name | OP Virtual Reality Learning Platform for Healthcare Training (OP-MedVR) |
| --- | --- |
| Project Type | Software product development – Healthcare Virtual Reality Learning Platform |
| Project Manager | Gielo Joseph Fernandez |
| Project Goals | Develop VR platform that simulates real-world healthcare scenarios such as patient diagnosis and emergency response within virtual hospital environment. Implement multi-user capabilities and feedback system to allow lecturers to assess student performance during simulations. Create user training and support for student and lecturers on how to use OP-MedVR. |
| Project Deliverables | Tangible deliverables: -VR homepage and navigation integrated within OP LMS. -Single-sign on using existing student and lecturer accounts. -Multiplayer mode for students and observer mode for lecturers. -Role-playing scenarios for students. -User training manual on how to use OP-MedVR. -Feedback feature for lecturers. -User training for students and lecturers. -Maori values and design integration into homepage and VR. - Eight VR Hospital Rooms: -Emergency Room -Intensive Care Unit -Medical Ward -Operating Room -Maternity Care -Behavioural and Mental Room -Family Room -Neonatal Intensive Care Unit -Github repository of source code -Jira artifacts -Deployed instances in three different environments: development, testing, and production Intangible deliverables: -Good User Experience for students and lecturers. -No bugs and no errors during usage. -The VR is responsive and fast for students and lecturers. -Available 24/7 at 99.95% uptime. -The students’ and lecturer’s data are secure and protected. -The VR has scalability feature which handles increasing number of users without affecting performance. -The code is efficient and well documented. -The code is easy to maintain for future updates. -The code has been tested for errors to ensure standards. -Good logging for monitoring. -Availability of VR for students and lecturers everywhere with Internet. -Server logging mechanism to check for hardware/software issues. |
| Project Methodology | Agile - Scrum |
| Project Budget | Phase; Estimated Cost. Sprint 0; $104,307.00. Sprint 1; $37,338.00. Sprint 2; $69,342.00. Sprint 3; $48,006.00. Sprint 4; $70,249.20. Sprint 5; $32,004.00. Sprint 6; $32,004.00. Sprint 7; $32,004.00. Sprint 8; $32,004.00. Sprint 9; $32,004.00. Sprint 10; $75,583.20. Total Cost; $564,845.40. |
| Project Schedule | Start Date: 12 March 2025 Estimated Completion Date: 23 July 2025 Estimated Duration: 96 Working days |
| Milestones | Date; Milestones. 12 March 2025; Project start. 14 March 2025; Completion of Project Vision. 25 March 2025; Preparation for Sprint 1 done.. 14 April 2025; Completion of UI/UX flows.. 14 April 2025; Completion of Emergency Room. 25 April 2025; Completion of Deployment to Test Environment. 29 April 2025; Completion of lecturer dashboard. 29 April 2025; Completion of LMS integration. 29 April 2025; Completion of multi-user capabilities. 8 May 2025; Completion of User Training and lecture to students and lecturers. 12 May 2025; Completion of Intensive Care Unit. 21 May 2025; Deployment to production. 29 May 2025; Completion of Medical Ward. 6 June 2025; Completion of Operating Room. 16 June 2025; Completion of Maternity Care. 24 June 2025; Completion of Behavioral and Mental Health Room. 2 July 2025; Completion of Family Room. 10 July 2025; Completion of Neonatal Intensive Care Unit (NICU). 15 July 2025; Completion of Manual and User Training to Students and Lecturers. 18 July 2025; Deploy to Production. 23 July 2025; Project Closure. |
| Risks | - Tasks might take more time to complete as the tasks are assigned to interns. - The buffer did not consider sick leaves and absences of employees.. - Students or lecturers may be hesitant and avoid using the new VR. - Malfunctions of hardware and software - VR simulations might not reflect the Maori practices.. |

# 2. Background and Purpose

Otago Polytechnic is set to launch a Virtual Reality (VR) Learning Platform tailored specifically for its Nursing and Healthcare programs in Dunedin. This innovative tool will allow students to hone essential medical skills, such as diagnosing patients and managing emergencies, within a highly immersive virtual hospital setting. By replicating real-world scenarios, the VR platform will create a secure and supportive environment for students to build and perfect their clinical abilities, free from the stress or potential risks of hands-on practice in actual healthcare settings. This initiative reflects the institution’s dedication to preparing students for the challenges of modern healthcare through forward-thinking solutions.

Key features of this platform will be the eight different hospital rooms (Emergency Room, Intensive Care Unit, Medical Ward, Operating Room, Maternity Care, Behavioural and Mental Room, Family Room, and Neonatal Intensive Care Unit) that will be created in the VR world. Another key feature includes the ability for students to interact and collaborate with each other in real time. Multi-user capabilities will enable role-playing exercises that closely mimic real healthcare scenarios, helping students develop teamwork, decision-making, and communication skills. This immersive, hands-on approach will better prepare students for the challenges they will encounter in their future careers. Furthermore, the platform will integrate smoothly with the Polytechnic’s existing Learning Management System (LMS), allowing both students and lecturers to easily track progress and manage coursework

The platform will also be designed to be culturally inclusive, integrating Māori health frameworks and practices into the VR simulations. This ensures that students not only learn the technical aspects of healthcare but also gain an understanding of the cultural sensitivities necessary for delivering holistic care. The system will include realistic 3D environments and provide a built-in feedback system, enabling lecturers to evaluate student performance and offer real-time guidance.

To ensure success, the project will also involve comprehensive training programs for both students and faculty, ensuring they feel confident in using the VR technology. With a budget of NZD 564,845.40 and a planned completion timeline of 5 months, this initiative promises to be a groundbreaking step in modern healthcare education. A detailed risk management plan will tackle potential challenges, such as technology issues and resistance to new methods of learning, ensuring the platform’s long-term success and impact.

# 3. Project Scope

The project scope is defined as a statement by writing the context, main inputs and outputs and main functions of the system to be developed. Project scope defines all tasks, activities, resources, timelines, decisions, and project boundaries that must be done to meet project goals and deliverables. The project scope statement (PSS) is prepared for the customer to illustrate the purpose of developing the project and plan of all activities needed to accomplish the project. The PSS warrants that all stakeholders are benefited to understand the project (Althiyabi & Qureshi, 2021).

## 3.1. Objectives

Project objectives define the critical steps that must be taken to successfully execute a project plan. Project objectives can be tangible deliverables or intangible milestones, but they should always be SMART (specific, measurable, achievable, realistic and timebound) and related to your broader project goals. Project objectives allow you to communicate with your team and outline what individuals are responsible for what objectives to better meet stakeholder quality expectations. Your objectives should contain metrics such as budget, quality and how long it takes to finish the project (Bridges, 2024).

## 3.2. Deliverables

Project deliverables are essential to ensure the success of data integration projects by providing a way to measure progress and manage expectations. Well-defined deliverables help maintain sanity by setting clear expectations and preventing stakeholders from constantly asking for more than what can be realistically delivered within the allotted time. Project deliverables act as a roadmap and a control mechanism for the integration project. They help to solidify base requirements and mappings, which in turn provides the team with more flexibility to handle last-minute requests. They also communicate what features and outcomes to expect from the project from its initiation to completion (Goldfedder, 2020).

## 3.3. Milestones

In project management, milestones are defined as significant points or events within a project's timeline. Milestones serve as crucial reference points for tracking progress and assessing achievements against the project plan. Milestones can signify the completion of specific phases or the delivery of key deliverables. Milestones are used as benchmarks to measure how the project is advancing. By identifying when milestones are reached (or not reached), project managers can gauge whether the project is on track (Lock, 2017).

The table below discuss the project milestones of OP-MedVR in more detail.

## 3.4. Technical requirements

In project management, are the factors required to deliver a desired function or behaviour from a system to satisfy a user’s standards and needs. Usually written in a technical requirement document, technical requirement document empowers the team to come to a mutual understanding of what is required, technically, to make your project or product a success. Technical requirements also provide information that will help you determine the needed budget, leverage work breakdown schedule, help create a realistic Gantt chart, and risk management aspects (Espinheira, 2021).

Technical requirements is broken down into two parts, functional and non-functional requirements. Functional and non-functional requirements will be discussed in detail below.

### 3.4.1 Functional requirements

In software development, functional requirements refer to the features and functions a solution must have to ensure it behaves as expected. In other words, proper functional requirements describe how the product enables users to complete their tasks (Rebrova, 2024). Functional requirements are simply a way to understand what to build so that you don't waste time and money building the wrong thing. It also gives you the necessary up front information to devise an elegant design that implements these requirements (Fowler, 2010).

In the case of OP-MedVR, the table below shows the functional requirements in more detail. These are in the form of the following: authentication,

### 3.4.2 Non-functional requirement

In project planning, although aspects such as performance, security, usability, reliability, and scalability are not part of the functional requirements in developing a software project, it is still important as 	not including it may not meet user or stakeholder expectations, or the needs of the business.

In the case of OP-MedVR, the table below contains the non-functional requirements in more detail.

## 3.5. Project Exclusions

In project planning, it is necessary to include things that are not included in the project as this can lead to scope creep during the development of OP-MedVR. Similar to project limitations but project exclusion specifies any work or activities explicitly not included in the project scope. This helps manage expectations and avoid misunderstandings about project deliverables (Wootton, 2024).

In the case of OP-MedVR, the table below discusses the project exclusions in more detail.

| Exclusion | Description |
| --- | --- |
| Servers and other Hardware | Since we are deploying serverless, we will not be deploying physical servers and will only utilize deploying in the cloud. |
| Classroom deployment | Since we are only developing the OP-MedVR, we will not be setting up a physical VR computer room in OP is not part of the project. |
| Software update and upgrade | Since we are only developing OP-MedVR in 5 months, any changes after it would require a new budget and planning. |
| hardware development | We are utilizing existing VR hardware, and we will not develop custom VR hardware. |
| non healthcare training | The development of VR will only cover healthcare students and will not cover other disciplines. |
| NonVR platform | The development of OP-MedVR only cover the VR aspect, it will not cover other technologies (mobile, desktop, etc.). |
| Other procurement | Procuring materials outside the proposed resources and materials and would need additional budget added. |

## 3.6. Project Limitations

In project planning, it is always important to take into account the limitations of the resources that you have. These limitations can be budget, time, technology, material choice and so on. These things are the limit of what can be done with the project. Often times these limitations guide the project, like how time can affect the quality of the delivery (Erro, 2016).

In the case of OP-MedVR, the table below discusses the project limitations in more detail.

| Limitations | Explanation |
| --- | --- |
| Cost | The budget approved for OP-MedVR is only $564,845.40. Additional cost will be limited to the 5% miscellaneous budget |
| Time | The project development will start at 12 March 2025 and must end at 23 July 2025. |
| Technology | The software licenses used for the development will consider cost and features as factors and choose the best affordable option The hardware used during the development will also be limited by budget allocated. Internet used for remote work will be limited to the internet plan that the employee can afford. |
| Experience | The skills and experience of the development team will be limited to the available skills in the market. |

# 4. Project Assumptions

In project management, assumptions are factors believed to be true or real, even without any real evidence. These assumptions vary from each phase of the project lifecycle. A project manager has to make certain assumptions related to the market, resources, technology, scope, or some other project factors. If they do not, it is hard to proceed ahead because there is simply no way to give proof or certainty for everything in a project plan (Sharma, 2024).

| Assumptions | Explanation |
| --- | --- |
| All the employees in the development team are working full time | Due to the nature of the work needed to finish, the engineers that are not assigned a task during the period are still contributing to the sprint goals. This is because there are other aspects to it, like communicating with stakeholders, grooming backlog, testing features, bug fixes, code reviews, testing, making unit tests, communicating with students and lecturers, etc.. |
| All the employees in the development team are working remotely | To reduce costs in rent, electricity, etc., we assume that all are remotely, and from home. |
| All the employees in the development team can start working immediately | To reduce intricacies during planning and development, we assumed that the employees are all ready to start working during preparation(sprint) and are working full time for the duration of the development. |
| The experiences of the Senior Engineers are sufficient in delivering this product | To mitigate the unknowns, we assume that the Senior Engineers have delivered similar projects in the past. |
| Additional cost after project closure is not accounted into planning | Future costs such as licenses, electricity, etc are not accounted during planning |
| Learning VR Platform | We assume that the students will use the OP-MedVr as alternative learning methods and it will enhance their healthcare skills |
| Budget | We assume that the allocated budget will cover from start of project-to-project closure |
| Timeframe | We assume that there are no unknown delays that can significantly affect delivery |

# 5. Methodology

Scrum is an agile approach to software development that focuses on working in small, manageable chunks. It's a way of developing products that’s flexible and collaborative, allowing teams to adapt quickly as they go. Scrum challenges the traditional, step-by-step methods of product development by emphasizing self-organizing teams. The idea is that when team members collaborate closely, both online and face-to-face, it leads to better outcomes. Instead of working in isolation, everyone on the team contributes and communicates, helping the project move forward more smoothly and flexibly. (Sachdeva, 2016). In regard to OP-MedVR, Scrum is a good methodology because it can handle changing requirements such as lecturer/students feedback, new curriculum. Since Scrum also encourages iterative deployment, lecturer and students can quickly review OP-MedVR and provide feedback and changes earlier in the development phase. Since many hospital rooms are being developed in this project, feedback from the first room(emergency room), can be implemented in the other hospital rooms.

## 5.1 Justification

Below are the justifications for why Scrum is the best fit for this initiative.

Firstly, Scrum’s iterative development process allows for continuous improvement and adaptation. The OPAIC VR platform project involves cutting-edge technology and requires frequent testing and refinement to ensure it meets the needs of students and lecturers, only scrum ideal to use in this type of project scenario. By breaking the project into smaller, manageable sprints, the development team can deliver incremental updates, gather feedback, and make necessary adjustments. This is particularly important for ensuring the platform’s immersive 3D environments, multi-user capabilities, and integrated feedback system function seamlessly (Schwaber & Sutherland, 2020).

Second, Scrum emphasizes collaboration and communication, which is critical for a project involving multiple stakeholders such as OPAIC VR platform project, stakeholders in this project will include among other students, lecturers, software developers, and healthcare professionals. The daily stand-ups, sprint reviews, and retrospectives will foster transparency and ensure that everyone is aligned with the project’s goals. This collaborative approach is essential for integrating culturally responsive healthcare practices rooted in Iwi/Māori health frameworks, as it requires ongoing dialogue and input from diverse stakeholders (Rubin, 2012).

Thirdly, scrum is adopted because of Scrum’s flexibility that makes it ideal for addressing the uncertainties and challenges inherent in developing a VR platform. For instance, the risk management plan for technology malfunctions and user resistance can be continuously updated based on real-time feedback and testing. This adaptability ensures that potential issues are identified and resolved early, minimizing disruptions to the project (Sutherland & Sutherland, 2014).

Lastly, Scrum’s focus on delivering value incrementally ensures that the platform’s key features, such as role-playing for multiple participants and integration with the existing LMS, are prioritized and developed efficiently. This approach also allows for early user training, ensuring that students and lecturers become confident with the VR technology as it evolves (Mike, 2010).

In conclusion, Scrum’s iterative, collaborative, and flexible framework makes it the most suitable methodology for the VR Learning Platform project. It enables continuous improvement, fosters stakeholder collaboration, and ensures the timely delivery of high-quality, culturally inclusive healthcare training solutions.

## 5.2 Māori Value: how you can apply Māori values

Implementing Māori values such as Whanaungatanga and Kaitiakitanga is necessary as it is needed to comply with NZQA and Māori Council standards. The team also hired a Cultural Consultant to help with implementing Māori Values. To implement Whanaungatanga, it is done in the following ways below:

- Enable inclusion of full translations to Te Reo Māori language in VR settings, and adding Māori phrases in dialogues in other languages (Hudson et al., 2023).

- Enable inclusion of Māori greetings in startup of VR (Andrade et al., 2021).

- Enable inclusion of Māori Visual art in background of hospital rooms (eg. Paintings in Family room) (Brown, 2008).

- Enable inclusion of Māori history in dialogues (Shedlock (Ngāpuhi & Hudson (Te Whakatōhea), 2022).

- Enable inclusion of Māori celebrations in the VR background, like Matariki(New Year) (Hudson et al., 2023)

For the Kaitiakitanga, it is done in the following ways below:

- Enable inclusion of rendering rubbish bins in VR to educate students on proper waste segregation (Castronovo et al., 2018).

- Enable inclusion of dialogues and scenarios in VR regarding handling wastes (Castronovo et al., 2018).

- Enable inclusion of scenarios and dialogues in VR for the students and teachers to pledge to care for their environment (Sterman et al., 2015).

Adopting Māori ideals like Manaakitanga, Auahatanga, and Whanaungatanga should be implemented in the OPAIC IT project in several ways. For Manaakitanga, by actively encouraging open communication, empathy, and inclusivity, the project team can ensure that every member feels valued and accepted. This may include planning frequent team-building exercises and encouraging a spirit of belonging among team members. Auahatanga can also be embraced by fostering an innovative and creative culture that allows team members to experiment with novel tools and methods. This could include setting aside time for innovation workshops, hackathons, or brainstorming sessions to create fresh concepts and answers.

# 6. Project Risks and Risk Management Plan

In project management, project risk is defined as the chance of certain occurrences adversely affecting project objectives. It is the degree of exposure to negative events, and their probable consequences. Project risk is therefore characterized by the following risk factors: risk event, risk probability, and amount at stake. Therefore risk management, is the art and science of identifying, analyzing and responding to risk factors throughout the life of a project and in the best interests of its objectives (Pym, 1987). The steps in risk management process are the following: risk identification, risk assessment, risk treatment, risk response planning, risk monitoring and control and risk communication (Martins, 2024).

In the case of OP-MedVR. The table below shows the risks, probability of risk occurring, impact on the project delivery, risk level, member responsible for risk prevention, and mitigation steps.

| Project Risk | Probability | Impact | Risk Register | Member Responsible | Mitigation |
| --- | --- | --- | --- | --- | --- |
| Tasks might take more time to complete as the tasks are assigned to interns. | 4 | 4 | 4 | Senior VR Developer | Co-pair with Intermediate and Senior Developers Buffer for the tasks are assigned |
| The buffer did not consider sick leaves and absences of employees. | 4 | 4 | 4 | Scrum Master | Daily standup to monitor if team needs more manpower |
| Students or lecturers may be hesitant and avoid using the new VR. | 9 | 9 | 9 | Risk Management Specialist | Every developed VR Room is consulted with lecturers and students to fine tune it and address issues Hired Trainer to ensure training with the students runs smoothly. |
| Malfunctions of hardware and software | 6 | 6 | 6 | Senior Platform Developer | Added logs as feature to easily monitor and address technology malfunction For hardware issues, it is a limitation that is an accepted risk |
| VR simulations might not reflect the Maori practices. | 6 | 6 | 6 | Cultural Consultant | Every developed VR Room is consulted with lecturers and students Maori Council and NZQA is also involved in checking the quality |
| Scope Creep | 4 | 4 | 4 | Scrum Master | Define Acceptance criteria/Definition of Done during planning Re-estimate tasks if scope creep needs to be accepted Utilize Change Management request for Scope Creep |
| Bugs detected after deployment to production | 9 | 9 | 9 | Scrum Master | Delegate schedules of engineers to morning, afternoon, and evening shifts to monitoring post deployment |

Figure 1: Risk Assessment Matrix (Hatton, 2024)

# 7. Project Organisation

A project organizational structure is used to determine the hierarchy and authority of people involved in a specific project. The structure defines each team member’s function and the reporting lines on a chart for team members to reference during a project. Project managers use project organization to align team members before and during a project. The process minimizes disruption to your workflow and conflict among team members, as well as leads to maximum productivity among team members involved in a project (Martins, 2024).

For the OP-MedVR, There is no Scrum Master role since the plan is to have the whole development team rotate on the Scrum Master role except the Engineering Manager and the Product Owner (Shuiqing Yu, 2019). The whole development team reports to the Senior Product Owner and the Senior Product Owner and the HR Manager reports to the Engineering Manager. The student and lecturer assigned by OP reports to the OP. The table below shows the project organisation structure, their roles, responsibilities, and who they report to.

| Name | Functional role | Responsibilities | Reporting To |
| --- | --- | --- | --- |
| Suigetsu Hozuki | OP Board Member | Decision making for OP |  |
| Kakashi Hatake | Engineering Manager | Leading the development team | OP Board Member |
| Tsunade Senju | HR Manager | Hiring of members | Engineering Manager |
| Choji Akimichi | Senior Product Owner | In charge of backlogs | Engineering Manager |
| Shikamaru Nara | Senior Platforms Engineer | In charge of deployment related tasks, pipeline creation | Senior Product Owner |
| Minato Namikaze | Risk Management Specialist | In charge of risk management | Senior Product Owner |
| Sakura Haruno | Cultural Consultant | Ensure Maori and other Cultural requirements are met | Senior Product Owner |
| Rock Lee | Senior VR Software Engineer 1 | In charge of development, does full-stack development and design | Senior Product Owner |
| Kiba Inuzuka | Senior VR Software Engineer 2 | In charge of development, does full-stack development and design | Senior Product Owner |
| Shino Aburame | Intermediate Full stack software engineer 1 | Full-stack development and design | Senior Product Owner |
| Kurenai Yuhi | Intermediate Full stack software engineer 2 | Full-stack development and design | Senior Product Owner |
| Kimimaro Kaguya | Associate full stack software Engineer 1 | Full-stack development and design | Senior Product Owner |
| Mei Terumi | Associate full stack software Engineer 2 | Full-stack development and design | Senior Product Owner |
| Zabuza Momochi | Fullstack software engineer Intern 1 | Full-stack development and design | Senior Product Owner |
| Konohamaru Sarutobi | Fullstack software engineer Intern 2 | Full-stack development and design | Senior Product Owner |
| Sasuke Uchiha | Fullstack software engineer Intern 3 | Full-stack development and design | Senior Product Owner |
| Naruto Uzumaki | Fullstack software engineer Intern 4 | Full-stack development and design | Senior Product Owner |
| Hinata Hyuga | Fullstack software engineer Intern 5 | Full-stack development and design | Senior Product Owner |
| Danzo Shimura | Senior QA Engineer | In charge of quality and code testing | Senior Product Owner |
| Kisame Hoshigaki | Senior VR Designer/Content Developer | In charge of VR Design, does software development as well | Senior Product Owner |
| Asuma Sarutobi | Trainer | In charge of training to students and lecturers | Senior Product Owner |
| Jinpachi Munashi | Lecturer | Lecturer assigned from OP to test the VR | OP Board Member |
| Kushimaru Kuriarare | Student | student assigned from OP to test the VR | OP Board Member |

# 8. Communications with Stakeholders

## 8.1 Stakeholders identification.

A stakeholder is a person, group or organization with a vested interest, or stake, in the decision-making and activities of a business, organization or project. Stakeholders can be members of the organization they have a stake in, or they can have no official affiliation. Stakeholders can have a direct or indirect influence on the activities or projects of an organization. Their support is often required for business and project success (Barney, 2023). In the case of OP-MedVR, the stakeholders will be the following:

| Stakeholder | Role | Influence Level | Decisional Influence | Internal/External |
| --- | --- | --- | --- | --- |
| OP Head | OP head will be the owner of the project | 5 | 5 | Internal |
| OP board | OP stakeholders that will benefit from the project | 4 | 4 | Internal |
| OP professors | The professors and students will use the VR after deployment | 3 | 3 | Internal |
| Māori consultants | Their Māori knowledge affect decisions | 3 | 3 | External |
| OP Students | They will use the VR after production | 2 | 2 | Internal |
| Operations Team | They will maintain the VR after project closure | 3 | 3 | Internal |
| Manager and Development Team | In charge with development of VR | 3 | 3 | Internal |
| External Auditors | In charge of checking for standards(NZQA, Maori Council, regression testers, and penetration testers) | 3 | 3 | External |

## 8.2 Communication plan

Agile ceremonies are composed of daily standup, story grooming, sprint planning, sprint review, and sprint retrospective which are used to discuss the project’s next course of action (Laoyan, 2025).

In the case of OP-MedVR, communication with stakeholders will be done during these agile ceremonies. It will be discussed in detail below.

| Stakeholder | Role | Purpose | Mode/Chanel of Communication | Frequency | Time | Participants |
| --- | --- | --- | --- | --- | --- | --- |
| OP Head and board | OP head will be the owner of the project | Get updates from the VR project | Online Meeting | Planning Dates 3/12/25 3/26/25 4/4/25 5/6/25 5/23/25 6/2/25 6/10/25 6/18/25 6/26/25 7/4/25 | 10am | Development Team and Stakeholders |
| OP professors | The professors and students will use the VR after deployment | To know how the VR is used | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders |
| Māori consultants | Their Māori knowledge affect decisions | To know if the VR project follows Māori Principles | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders |
| OP Students | They will use the VR after production | To know how the VR is used | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders |
| Operations Team | They will maintain the VR after project closure | To know how the VR is used | Online Meeting | Review Dates 3/25/25 4/3/25 4/22/25 5/5/25 5/22/25 5/30/25 6/9/25 6/17/25 6/25/26 7/3/25 7/23/25 | 10am | Development Team and Stakeholders |
| Development Team | Development of OP-MedVR | Discuss progress and updates | Daily Standup | Everyday | 3pm | Development Team |

# 9. Change management plan

Change management ensures that a project achieves its intended results and outcomes by supporting the individual transitions required by that project. When a new technology is used, employees must adopt and use it to deliver value. When you implement a new process, employees must adopt and use it to deliver value. Project-level change management provides the specific strategies, plans, actions and steps that focus on impacted employees and work in alignment with a project deployment (Creasey, 2022).

In scrum, changing requirements is quite common. Agile Manifesto Principle says “Welcome changing requirements, even late in development. “(Beck et al., 2001). Which means, we take decisions on what to do by seeing what results we are seeing. This approach will involve changing requirements as we go along (Kulkarni, 2023). The following below are done in the scenario of a change request (Dworniczak, 2025):

In the case of OP-MedVR, the following is done to assess change request:

- The change request form goes to the Product Owner and the stakeholders. Product owner and the stakeholders checks for cost-benefit effect, risk assessment, resource availability, impact on scope, and priority.

- Once it is approved, the Product Owner discusses with the scrum master and the development team regarding the effect of the change request. For example, the ICU room VR might get delayed in delivery if we apply this change. The development team discusses possible scenarios on how change request will be delivered.

- The Product Owner relays it to the stakeholders the scenarios to see if they will agree to it. The Product Owner then adjusts then backlog based on it.

- The change request then gets implemented based on the priority in the backlog.

# 10. Project Estimation Technique

A successful project starts with a successful estimate. To properly schedule the work to execute your project, you need to know the timeline, costs, scope, risk and more. All of these considerations are part of project estimation techniques. Estimation techniques help make decisions on the viability of your project. If you decide to move forward, they’re essential to forecasting projects accurately (Hennesy, 2022). The following below are some of the estimation methods:

1. Analogous estimation: A technique for estimating costs for your current projects and future projects based on a similar past project. Analogous estimating is one of the most detailed and accurate ways to estimate the cost data for a given project, so that you can set up an accurate cost baseline, without entering into the world of statistical models (Viter, 2022).

2. Parametric estimation: A statistical and accuracy-based technique for calculating the time, cost, and resources needed for project success. Combining historical and statistical data, parametric estimating uses the relationship between variables to deliver accurate estimations. Often used during a project or in the project planning phase, parametric estimating applies a formula or algorithm for making these calculations, using the specific cost or time needed to implement and finish a project or task (Udoagwu, 2022).

3. PERT diagram: A graphical illustration of a project as a network diagram consisting of numbered nodes linked by labelled vectors. PERT charts help project managers estimate the minimum time needed to complete a project. Managers can also analyse the work breakdown and task connections and assess project risks. The breakdown structure makes it easy to organize a complex project with a variety of moving parts by visualizing the dependencies between each step of the process (Sheldon et al., 2024).

4. Top-down approach: Frequently used for creating rough order of magnitude (ballpark) estimates at an early stage of the project, when the level of detail available is limited (they can also be used for validation purposes). Top-down estimates generally take less time and effort to produce than bottom-up estimates. The main benefit of top-down is the chance to use more holistic data from previous projects or products, including unmitigated and unforeseen risks, and scope creep. This can help reduce the risk of overlooked work activities or costs (Rowland, 2019).

5. Bottom-up approach: It is when you build your estimates from the most granular level of work needed in a specific project and estimate “up” from there to the bigger picture of the project. The superpower of this estimation technique lies in its unparalleled specificity. This creates a work breakdown structure (WBS) to estimate all the details of the lowest level of work needed and then add them up as you work up to the larger activities of a project. You can get to the discrete details by breaking the project into smaller deliverables and then individual tasks (Card, 2024).

In the case of OP-MedVR, Bottom-up approach and parametric estimation was used since most tasks are related, we can allocate the effort and budget for each specific task in relation to previous tasks (Guthrie, 2023). Bottom-up approach is great for this as well as we get to estimate all the activities needed by breaking it down into smaller tasks (Usifo, 2024).

11. Budget

A project budget is the total projected costs needed to complete a project over a defined period of time. It’s used to estimate what the costs of the project will be for every phase of the project. Creating a project budget is a critical part of the project planning process. The project budget will include such things as labour costs, material procurement costs and operating costs. But it’s not a static document. Your project budget will be reviewed and revived throughout the project, hopefully with the help of project budgeting software (Bridges, 2023b).

In relation to OP-MedVR, the expenses used in the preparation (sprint 0) will include all the necessary equipment and software needed for the duration of the project (5 months). The expenses in the sprints (Sprint 1 – Sprint 10) will focus on the labour costs and 5% for miscellaneous cost. This is under the assumption that licenses and equipment were already purchased during preparation, and that since all the employees are working from home, there is minimal cost in other expenses which will be covered by miscellaneous cost.

The rate per hour for each employee were based on the salary sourced from Glassdoor and Seek (2025) as what employers are offering based in current market demand. The annual salary is divided by 52 weeks and then divided by 40 hours per week to get the salary per hour.

The pay rates for the team employees were estimated based on the information sourced from SEEK (2021) as the source of most recent information what the employers are ready to offer for IT specialists in current market situation. The average annual salary from ten most recent job advertisements with the pay range per occupation was divided by standard 52 working weeks per year and 40 hours per week to calculate the hourly rate.

For the Work Breakdown Structure, the Work breakdown Structure in the MS Project is not utilised under the assumption that all the employees of the team are working full time in the background(communicating with stakeholders, code reviews, testing features, bug fixes, grooming tasks, etc..) even though they are not assigned a project in MS Project, which implies that they are working 8 hours per day, and 5 days per week. This is in exception to the HR Manager and Trainer, which will only work for 5 days and 6 days respectively.

The following tables contains the budget allocated:

| material | quantity | cost per unit | total cost | purpose | source |
| --- | --- | --- | --- | --- | --- |
| Keyboard | 20 pcs | $45.00 | $900.00 | For the use of employees | PowerPlay Keyboard |
| Mouse | 20 pcs | $20.00 | $400.00 | For the use of employees | Warehouse Mouse |
| Jira | 5 months | $172.00 | $860.00 | License for use of Jira | Jira |
| Laptops | 20 pcs | $1,300.00 | $26,000.00 | For the use of employees | Dell Laptop |
| VR Hardware | 20 pcs | $650.00 | $13,000.00 | For the use of employees | Meta Quest |
| Unreal Engine License | 0 | $0.00 | $0.00 | license for VR development | Unreal Engine |
| Github | 20 pcs x 5 months | $4.00 | $400.00 | license for Github repository | Github |
| Azure Subscription | 5 months | $432.00 | $2,160.00 | license for cloud use | Azure Calculator |
| Electricity | 0 | $0.00 | $0.00 | no electricity (remote work) |  |
| Rent | 0 | $0.00 | $0.00 | no rent (remote work) |  |
| Total |  |  | $43,720.00 |  |  |

| Role | hours | hourly rate | total cost | source |
| --- | --- | --- | --- | --- |
| HR Manager | 8 hours x 5 days | $53.00 | $2,120.00 | HR Manager |
| Project Manager | 8 hours x 96 days | $51.00 | $39,168.00 | Project Manager |
| Senior Platforms Engineer | 8 hours x 96 days | $52.00 | $39,936.00 | Senior Platforms Engineer |
| Risk Management Specialist | 8 hours x 96 days | $34.00 | $26,112.00 | Risk Management Specialist |
| Cultural Consultant | 8 hours x 96 days | $42.00 | $32,256.00 | Cultural Consultant |
| Senior Product Owner | 8 hours x 96 days | $48.00 | $36,864.00 | Senior Product Owner |
| Senior VR Software Engineer 1 | 8 hours x 96 days | $46.00 | $35,328.00 | Senior VR Software Engineer |
| Senior VR Software Engineer 2 | 8 hours x 96 days | $46.00 | $35,328.00 | Senior VR Software Engineer |
| Intermediate Full stack software engineer 1 | 8 hours x 96 days | $33.00 | $25,344.00 | Intermediate Full stack software engineer |
| Intermediate Full stack software engineer 2 | 8 hours x 96 days | $33.00 | $25,344.00 | Intermediate Full stack software engineer |
| Associate full stack software Engineer 1 | 8 hours x 96 days | $28.00 | $21,504.00 | Associate full stack software Engineer |
| Associate full stack software Engineer 2 | 8 hours x 96 days | $28.00 | $21,504.00 | Associate full stack software Engineer |
| Fullstack software engineer Intern 1 | 8 hours x 96 days | $25.00 | $19,200.00 | Fullstack software engineer Intern |
| Fullstack software engineer Intern 2 | 8 hours x 96 days | $25.00 | $19,200.00 | Fullstack software engineer Intern |
| Fullstack software engineer Intern 3 | 8 hours x 96 days | $25.00 | $19,200.00 | Fullstack software engineer Intern |
| Fullstack software engineer Intern 4 | 8 hours x 96 days | $25.00 | $19,200.00 | Fullstack software engineer Intern |
| Fullstack software engineer Intern 5 | 8 hours x 96 days | $25.00 | $19,200.00 | Fullstack software engineer Intern |
| Senior QA Engineer | 8 hours x 96 days | $34.00 | $26,112.00 | Senior QA Engineer |
| Senior VR Designer/Content Developer | 8 hours x 96 days | $35.00 | $26,880.00 | Senior VR Designer/Content Developer |
| Trainer | 8 hours x 6 days | $36.00 | $1,728.00 | Trainer |
| Total |  |  | $491,528.00 |  |

For the budget categories, the budget allotted is for the duration of the development of OP-MedVR(5 months) and the needed equipment of the development team. The rent and electricity is $0 under the assumption that the whole team is remote/working from home status. The cost on rent and electricity will be considered under miscellaneous.

The OP project Budget table:

# 12. Quality Control and Audit

- Quality Control

Quality control (QC) is a process through which a business seeks to ensure that product quality is maintained or improved. QC requires the company to create an environment where management and employees strive for perfection. This is done by training personnel, creating benchmarks for product quality, and testing products to check for statistically significant variations (Hayes, 2024).

- Audit

The audit is designed to determine the status of work performed on a project to ensure it complies with the statement of work, such as the scope, time and budget of the project, along with the maturity of the project management process. During audit the project scope, schedule, quality, cost, resources, and risks are checked to make sure it is still following the project plan (Bridges, 2023a). However in agile teams, the process sometimes deviates to address certain issues, which is expected as stated in the Agile Manifesto, “Individuals and interactions over processes and tools” (Beck et al., 2001). The auditor should communicate with Product Owner and Scrum master to ensure that agile practices were followed (Nair, 2019). In OP-VR LMS, the auditor should check the artifacts created during sprint planning, review and retrospective, as well as product backlogs.

As part of preparation for deployment to production, the table below are asked with setting up the quality control and audit of OP-MedVR.

| Quality Control | Metrics | Implementation in the Project |
| --- | --- | --- |
| New Zealand Qualifications Authority (NZQA) | Compliance with healthcare education standards | Review to ensure OP-MedVR complies with healthcare education standards during preparation of pre-prod requirements |
| Code Testing | Compliance with acceptance criteria of tasks | After developing each VR hospital room |
| Design feedback |  |  |

# 13. Project Closure

Agile project closure is a pivotal phase that ensures the project concludes smoothly while capturing valuable insights for future endeavours. Unlike traditional methodologies, Agile project closure is iterative and aligned with the Agile principles (Sengupta, 2023). To ensure the successful transfer of ownership from the Agile team to the operations team, the following items below are done to make sure we tie up any loose ends (Cosgrove & Hubbard, 2020).

| Closure Task | Description | Artifacts |
| --- | --- | --- |
| The scrum boards (Jira) will be archived, and documentation is organized. | Scrum board (Jira) will be archived. It will be inaccessible, but the sprint data can still be viewed. The documentations and links are organized. | Documentations Sprint Data |
| Meetings with the Operations Team | Walkthrough the key user stories remaining (if there is any) in the backlog Discuss the sprint artifacts and sprint data. Knowledge sharing regarding end-to-end functionality of OP-MedVR Access controls are given to the Operations Team | Knowledge sharing recordings Sprint artifacts and sprint data Sprint backlog Access controls |
| The project is handed to the Operations Team | Artifacts, source code repositories are given to the Operations Team The user-training manual is also given to the Operations Team | Source code repository User-training manual |
| Final Review of the project | Final sprint review including the stakeholders to review the final scope that was complete, the budget, and the schedule. | Sprint velocity Sprint data |
| Sprint Retrospective | A final retrospective is completed as a team to document on lessons learned, identify process improvements. | Retrospective board |
| Return assets used | The hardware used such as the laptops, VR hardware, other equipment are returned. | Asset tracking document |

# 14. Appendices

HR Manager - $53 per hour

https://www.glassdoor.co.nz/job-listing/hr-manager-foster-moore-JV_IC3525162_KO0,10_KE11,23.htm?jl=1009673518619&cs=1_ec9b4ff3&s=58&t=SR&pos=102&src=GD_JOB_AD&guid=00000195b27bb2459b30eef8ec034985&jobListingId=1009673518619&ea=1&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp7nckhgqnl800-1d963c8dbd503581&cb=1742456206940&ctt=1742456254121

Engineering Manager – 51$ per hour

https://www.glassdoor.co.nz/job-listing/ict-project-manager-techwise-solutions-JV_IC3525162_KO0,19_KE20,38.htm?jl=1009652037968&cs=1_b6da3e24&s=58&t=SR&pos=104&src=GD_JOB_AD&guid=00000195b27ff695b5f85de7264cd50c&jobListingId=1009652037968&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp7vtnigoog804-582d7553ed486054&cb=1742456485931&ctt=1742456494351

Senior Platforms Engineer - $52 per hour

https://www.glassdoor.co.nz/job-listing/senior-devops-engineer-fiserv-JV_IC3525162_KO0,22_KE23,29.htm?jl=1009678594918&cs=1_74fa5c4f&s=58&t=SR&pos=102&src=GD_JOB_AD&guid=00000195b28109a394510563b18d3c45&jobListingId=1009678594918&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp822fq2afp000-bb82b31d9c399180&cb=1742456556303&ctt=1742456627109

Risk Management Specialist – $34 per hour

https://www.glassdoor.co.nz/job-listing/product-development-specialist-hub-services-iag-new-zealand-JV_IC3525162_KO0,43_KE44,59.htm?jl=1009662255445&cs=1_4ef51041&s=58&t=SR&pos=102&src=GD_JOB_AD&guid=00000195b283066fa760d46250f5cb8e&jobListingId=1009662255445&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp861lui0ht800-3a847457d00276f3&cb=1742456686571&ctt=1742456707752

Cultural Consultant - $42 per hour

https://www.glassdoor.co.nz/job-listing/work-winning-consultant-aurecon-group-JV_IC3525162_KO0,23_KE24,37.htm?jl=1009561005629&cs=1_448e59b4&s=58&t=SR&pos=101&src=GD_JOB_AD&guid=00000195b285d69893ad4e1c0af95b38&jobListingId=1009561005629&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp8blnd222o000-75b1809a532fc97c&cb=1742456870868&ctt=1742456884958

Senior Product Owner - $48 per hour

https://www.glassdoor.co.nz/job-listing/product-owner-data-ai-products-asurequality-JV_IC3525162_KO0,30_KE31,43.htm?jl=1009672349495&cs=1_08ef0467&s=58&t=SR&pos=104&src=GD_JOB_AD&guid=00000195b28b54b9befd8a203fdf0cc2&jobListingId=1009672349495&ea=1&ao=1136043&vt=w&jrtk=5-pdx1-0-1imp8ml8ajdr1800-79507115f3c44640&cb=1742457230884&ctt=1742457239278

Senior VR Developer - $46 per hour

https://www.seek.co.nz/job/82471580?type=promoted&ref=search-standalone&origin=cardTitle#sol=077b2a7917309a47ff35c3d0496275e95285e244

Intermediate Full Stack Software Engineer - $33 per hour

https://www.seek.co.nz/job/82758697?type=standard&ref=search-standalone&origin=cardTitle#sol=1f6ec098bbebe4ded5ecba67a912927d61441054

Associate Full Stack Software Engineer – $28 per hour

https://www.glassdoor.co.nz/Salary/Aderant-Associate-Software-Engineer-Salaries-E37370_D_KO8,35.htm

Senior QA Engineer - $34 per hour

https://www.glassdoor.co.nz/job-listing/senior-qa-engineer-payment-product-binance-JV_IC3525162_KO0,34_KE35,42.htm?jl=1009335940342&src=GD_JOB_AD&uido=65FC4472BDEC32AAD12883C19DB458B2&ao=1136043&jrtk=5-pdx1-0-1impacp24gqnl800-2c32325891c848b1&cs=1_12244bb7&s=58&t=SR&pos=102&guid=00000195b2a663e695acf38a3d7b45b8&jobListingId=1009335940342&ea=1&vt=w&cb=1742459004143&ctt=1742459011545

Senior VR Designer/Content Developer - $35 per hour

https://www.glassdoor.co.nz/job-listing/game-director-lead-game-designer-tencent-JV_IC3525162_KO0,32_KE33,40.htm?jl=1009649781596&cs=1_3e9eaa24&s=343&t=SR-JOBS-HR&pos=102&src=GD_JOB_AD&guid=00000195b2a948ee89ebfea76a296686&uido=65FC4472BDEC32AAD12883C19DB458B2&jobListingId=1009649781596&ao=1136043&vt=w&jrtk=5-pdx1-0-1impaij15gqmt800-af997ef44ac85d47&cb=1742459194620&ctt=1742459202771

Trainer - $36 per hour

https://www.seek.co.nz/job/82815772?type=standard&ref=search-standalone&origin=cardTitle#sol=84016d139461aca38e6d722bb3f7f84abd331b3e

Developer Intern - $25 per hour

https://www.sjs.co.nz/job-details/21526/mechatronics-rnd-engineer-intern-casualpartfull-time-cbd/

Laptops - $1300 x 20 = $26000

https://www.dell.com/en-nz/shop/dell-laptops/inspiron-15-laptop/spd/inspiron-15-3520-laptop/oin3520100901mnzh?ref=variantstack

Keyboard - $45

https://www.pbtech.co.nz/product/KEYEBL1026/PowerPlay-E-Blue-Mechanical-Sense-RGB-Gaming-Keybo?srsltid=AfmBOooLZOmmTw6reVHHwSRwjH_6l9iixH98waNnHECwnCvt0Ds56fdIxjI&gStoreCode=PBAucklandCBD

Mouse - $20

https://www.thewarehouse.co.nz/p/logitech-m190-full-size-wireless-mouse---blue-910-005914/M18529702.html?srsltid=AfmBOortW7da92oV1ogJUmJ3HhpLUx3YZDpAapauHqF3Qt9arrRaK8aDHzI

VR hardware - $650 x 12 = $7800

https://www.pbtech.co.nz/product/MVRMTA0024/META-Quest-3s-128GB-Mixed-Reality-Headset-with-2x?qr=GShopping&gad_source=1&gclid=Cj0KCQjw-e6-BhDmARIsAOxxlxVaWUoXJIuyEoiQJ3eRXoX368WtnsJzZHLHL6e3mIZI5g8FZ-UVGZwaAntYEALw_wcB

Azure Subscription - $432 per month

https://azure.microsoft.com/en-us/pricing/calculator/?ef_id=_k_Cj0KCQjw-e6-BhDmARIsAOxxlxX14GT6Xgk_PIpmy9nZve2RbTFsrkhuQPFPnsWSuwNOKvzvVE6FhBAaAhw8EALw_wcB_k_&OCID=AIDcmmp3m06wb2_SEM__k_Cj0KCQjw-e6-BhDmARIsAOxxlxX14GT6Xgk_PIpmy9nZve2RbTFsrkhuQPFPnsWSuwNOKvzvVE6FhBAaAhw8EALw_wcB_k_&gad_source=1&gclid=Cj0KCQjw-e6-BhDmARIsAOxxlxX14GT6Xgk_PIpmy9nZve2RbTFsrkhuQPFPnsWSuwNOKvzvVE6FhBAaAhw8EALw_wcB

VR Software Licenses - free

https://www.unrealengine.com/en-US/license

Github - $4 x 20 = $80 per month

https://github.com/pricing

Jira - $8.6 x 20 = $172 per month

https://www.atlassian.com/software/jira/pricing

# 15. References:

Althiyabi, T., & Qureshi, R. (2021). Predefined project scope changes and its causes for project success. International Journal of Software Engineering & Applications (IJSEA), 12(2/3).

Andrade, A. D., Techatassanasoontorn, A. A., Singh, H., & Staniland, N. (2021). Indigenous cultural re-presentation and re-affirmation: The case of M_aori IT professionals. Information Systems Journal. https://doi.org/doi:10.1111/isj.12331

Barney, N. (2023). Stakeholder. TechTarget. https://www.techtarget.com/searchcio/definition/stakeholder

Beck, K., Cohn, M., Jeffries, R., Anderson, D., Beedle, M., Boehm, B., Combemale, B., Highsmith, J., Hunt, A., Kern, P., Larman, C., Martin, R., Mellor, S., Schwaber, K., Sutherland, J., & Thomas, D. (2001). The Agile Manifesto. Agile Alliance. http://agilemanifesto.org/

Bridges, J. (2023a). How to Do a Project Audit: A Quick Guide. ProjectManager.Com. https://www.projectmanager.com/training/project-management-audit

Bridges, J. (2023b). How to Make a Project Budget: Project Budgeting Basics (Templates Included). ProjectManager.Com. https://www.projectmanager.com/training/create-and-manage-project-budget

Bridges, J. (2024). How to Write Effective Project Objectives & Goals Every Time. https://www.projectmanager.com/training/how-to-write-effective-project-objectives-every-time

Brown, D. (2008). “Ko to ringa ki nga rakau a te Pakeha”—Virtual Taonga Maori and Museums. Visual Resources, 24(1), 59–75. https://doi.org/10.1080/01973760801892266

Card, K. (2024). Accurate Project Estimations: A Deep Dive Into Bottom-up Estimation. UseMotion.Com. https://www.usemotion.com/blog/bottom-up-estimating

Castronovo, F., Yilmaz, S., Rao, A., Condori, W., & Monga, K. (2018). Development of a Virtual Reality Educational Game for Waste Management: Attack of the Recyclops. 24–27.

Cosgrove, E., & Hubbard, K. (2020). Agile closing out project. Action Engineering Blog. https://www.action-engineering.com/blog/agile-closing-out-project/

Creasey, T. (2022). Change Management at the Project Level. Prosci. https://www.prosci.com/blog/change-management-at-the-project-level

Dworniczak, M. (2025). Understanding Change Requests in Scrum. LinkedIn. https://www.linkedin.com/pulse/understanding-change-requests-scrum-mariusz-mario-dworniczak-pmp-i26bf

Eby, K. (2021). Essential Guide to Project Organizational Structure. https://www.smartsheet.com/content/project-management-organization?srsltid=AfmBOoo1noRBtZhQ4hZJVw7TRajpVMRSrta9YgIbSvq2FbhXB16auQu4

Erro, S. (2016). Limitations vs. Constraints. https://medium.com/@SteveErro/limitations-vs-constraints-575d9334ed2f

Espinheira, E. (2021). Management Fix. ILLUMINATION. https://medium.com/illumination/management-fix-9a4ce364ced2

Fowler, K. (2010). Chapter 1—Best Practices in Mission-Assured, Mission-Critical, and Safety-Critical Systems. In K. Fowler (Ed.), Mission-Critical and Safety-Critical Systems Handbook (pp. 1–82). Newnes. https://doi.org/10.1016/B978-0-7506-8567-2.00001-9

Goldfedder, J. (2020). Finding Your Purpose: Project Deliverables. In J. Goldfedder (Ed.), Building a Data Integration Team: Skills, Requirements, and Solutions for Designing Integrations (pp. 49–73). Apress. https://doi.org/10.1007/978-1-4842-5653-4_4

Guthrie, G. (2023). How to use parametric estimating to improve project performance. Nulab. https://nulab.com/learn/project-management/how-to-use-parametric-estimating-to-improve-project-performance/

Hatton, M. (2024). How to conduct a risk assessment. https://heightsafety.net/news/how-to-conduct-a-risk-assessment/

Hayes, A. (2024). Quality Control: What It Is, How It Works, and QC Careers. Investopedia. https://www.investopedia.com/terms/q/quality-control.asp

Hennesy, M. (2022). Project Estimation Techniques. ProjectManager.Com. https://www.projectmanager.com/blog/project-estimation-techniques

Hudson, P., Whaanga, H., & Keegan, T. T. (2023). Computing Technologies for Resilience, Sustainability, and Resistance. IEEE Ann. Hist. Comput., 45(4), 27–38. https://doi.org/10.1109/MAHC.2023.3325249

Kulkarni, S. (2023). Change Management in Scrum. World of Agile. https://worldofagile.com/blog/change-management-in-scrum/

Laoyan, S. (2025). Understanding the 4 Agile ceremonies. Asana. https://asana.com/resources/agile-scrum-ceremonies

Lock, D. (2017). The Essentials of Project Management (4th, Ed.). Routledge.

Martins, J. (2024). Step-by-step guide to the risk management process. https://asana.com/resources/project-risk-management-process

Nair, B. (2019). Auditing Agile Projects & Agile Auditing- A primer. LinkedIn. https://www.linkedin.com/pulse/auditing-agile-projects-auditing-primer-biju-nair

Pym, D. V. (1987). Risk Management. PM Network, 1(3), 33–36.

Rebrova, A. (2024). Functional vs Non-Functional Requirements in Software Development. Mad Devs Blog. https://maddevs.io/blog/functional-vs-non-functional-requirements/

Rowland, M. (2019). Three ways to approach cost estimation. APM.Org.Uk. https://www.apm.org.uk/blog/three-ways-to-approach-cost-estimation/

Sengupta, S. (2023). Project closure strategy for agile project. Medium. https://medium.com/@mailme.senguptasudipta/project-closure-strategy-for-agile-project-0744c8440a86

Sharma, N. (2024). Project assumptions: Guide to identify, evaluate & manage risks. ProofHub. https://www.proofhub.com/articles/project-assumptions

Shedlock (Ngāpuhi, N. P., Te Whakatōhea) ,Kevin, & Hudson (Te Whakatōhea), P. (2022). Kaupapa Māori concept modelling for the creation of Māori IT Artefacts. Journal of the Royal Society of New Zealand, 52(sup1), 18–32. https://doi.org/10.1080/03036758.2022.2070223

Sheldon, R., Chai, W., & Brush, K. (2024). What is a PERT chart? And how to use it, with examples. TechTarget. https://www.techtarget.com/searchsoftwarequality/definition/PERT-chart

Shuiqing Yu, J. (2019). Five Benefits of a Rotating Scrum Master. https://www.linkedin.com/pulse/five-benefits-rotating-scrum-master-shuiqing-yu-joseph/

Sterman, J., Franck, T., Fiddaman, T., Jones, A., McCauley, S., Rice, P., Sawin, E., Siegel, L., & Rooney-Varga, J. N. (2015). WORLD CLIMATE: A Role-Play Simulation of Climate Negotiations. Simulation & Gaming, 46(3–4), 348–382. https://doi.org/10.1177/1046878113514935

Udoagwu, K. (2022). The Ultimate Guide to Parametric Estimating in Project Management. Wrike.Com. https://www.wrike.com/blog/guide-to-parametric-estimating-in-project-management/

Usifo, D. (2024). How to Use Bottom-Up Estimating in Project Management. DeeProjectManager.Com. https://deeprojectmanager.com/bottom-up-estimating-project-management/

Viter, I. (2022). Understanding the Analogous Estimating Technique. Runn.Io. https://www.runn.io/blog/analogous-estimating

Wootton, P. (2024). Project Scope Statement. https://www.projectmanagement.com/wikis/961606/project-scope-statement#_=_