## Sheet1
activities for VR scrum
|  | Sprint 0 | Project Setup & Planning
Epic 1 Project Setup & Planning |  |  | Define project Scope, goals, and success criteria
-Define project scope, goals, and success criteria |  |  | Hiring employees
Configure version control system (GIT) |  |  | Configure Version Control System
Configure Cloud storage |  |  | Cloud Storage
Setup development and testing environments for VR |  |  | Setup development and testing environments for VR
Identify required VR hardware and software (headsets, controllers) |  |  | Identify required VR hardware and software (headsets, controllers)
Identify project Management tools (Jira) |  |  | Identify project Management tools (Jira)
Develop a risk management strategy (tech malfunctions, user adoption challenges). |  |  | Conduct Research on culturally responsive healthcare training(Iwi/Maori frameworks)
Epic 2 Research & Design
Conduct research on culturally responsive healthcare training (Iwi/Maori frameworks). |  | Sprint 1 | Design Emergency rooms and models
Design immersive 3D hospital environment and patient simulations. |  |  | Design wireframes and UI/UX flow for the platform.
Plan multi-user interaction & role-playing mechanics. |  |  | Design immersive 3d hospital (Emergency room)
Map out LMS integration requirements. |  |  | Design VR doctor and patient models (Emergency room)
Develop wireframes and UI/UX flow for the platform. |  |  | Design interactive medical tools (Emergency room)
Gather feedback from lecturers and students. |  |  | Design role-playing mechanics (medical scenarios) (Emergency room)
Design culturally inclusive assets
Epic 3 VR Environment & Asset Development |  |  | Gather feedback from lecturers and students.
Build 3D hospital environments (wards, ER, consultation rooms). |  |  | Design risk management strategy (tech malfunctions, user adoption challenges).
Create culturally inclusive assets and medical scenarios.
Implement VR patient models with realistic conditions.
Develop interactive medical tools (stethoscope, IVs, monitors).
Integrate real-world healthcare workflows into the VR environment. |  | Sprint 2 | Emergency room integration
Develop immersive 3d hospital (Emergency room)
Epic 4 Multi-User & Role-Playing System |  |  | Develop UI/UX flows
Implement real-time collaboration (multiple users in the same VR space). |  |  | Develop interactive medical tools
Develop role-based functionality (students as doctors/nurses, lecturers as observers). |  |  | Develop role-playing mechanics.
Enable voice communication and in-VR annotations. |  |  | Develop VR doctor and patient models (Emergency Room)
Test multi-user interactions and refine networking stability. |  | Milestone | Testing of UI/UX flows
|  | Milestone | Testing of emergency room
Gather feedback from lecturers and students.
Epic 5 Feedback & Assessment System |  |  | Design lecturer dashboard to review student performance
Design a lecturer dashboard to review student performance. |  |  | Design LMS integration requirements.
Implement automated feedback & scoring for medical procedures. |  |  | Design multi-user capabilities
Allow students to receive real-time feedback on their actions. |  |  | Gather feedback from lecturers and students.
Ensure feedback aligns with healthcare best practices and cultural guidelines. |  | Sprint 3
Deploy to Testing Environment
Epic 6 LMS Integration |  |  | Design risk management strategy (tech malfunctions, user adoption challenges). | load testing
Develop API connections between the VR platform and the existing LMS. |  |  | Develop multi-user capabilities/collaboration (multiple users in the same VR space)
Enable automatic reporting of student performance into LMS. |  |  | Develop LMS integration
Allow lecturers to assign, track, and grade VR training sessions. |  | Milestone | Testing of Multi-user capabilities
Ensure compliance with Otago Polytechnic’s learning management requirements. |  | Milestone | Testing of LMS
Preparation for preproduction requirements
Epic 7. User Training & Documentation |  |  | Design risk management strategy (tech malfunctions, user adoption challenges).
Create a user-friendly guide for students and lecturers. |  |  | Design Immersive 3d hospital (Intensive Care Unit)
Develop onboarding tutorials within the VR experience. |  |  | Design VR doctor and patient models (Intensive Care Unit)
Conduct training sessions to Ensure adoption. |  |  | Design interactive medical tools (Intensive Care Unit)
Gather user feedback to improve ease of use. |  |  | Design role-playing mechanics (medical scenarios) (Intensive Care Unit)
Gather feedback from lecturers and students.
Epic 8. Optimization & Performance Testing |  |  | Performance testing of Test Environment
Optimize VR rendering for smooth performance (reduce latency, enhance graphics).
Ensure platform runs effectively on required VR hardware.
Test for bugs, usability issues, and accessibility concerns. |  | Sprint 4
Conduct stress tests for multi-user scalability. |  |  | Deploy to higher Environment
Integration Testing
Epic 9 Deployment & Launch |  | MileStones | Deploy to production
Finalize software packaging for distribution. |  |  | Develop Immersive 3d hospital (Intensive Care Unit)
Implement security and data protection measures. |  |  | Develop VR doctor and patient models (Intensive Care Unit)
Conduct a pilot rollout with a Test group. |  |  | Develop interactive medical tools (Intensive Care Unit)
Gather last-minute feedback before the full release. |  |  | Develop role-playing mechanics (medical scenarios) (Intensive Care Unit)
Testing Intensive Care Unit
Epic 10. Post-Launch Support & Future Enhancements |  |  | Design Immersive 3d hospital (Medical Ward)
Monitor user adoption and collect feedback. |  |  | Design VR doctor and patient models (Medical Ward)
Provide technical support & bug fixes. |  |  | Design interactive medical tools (Medical Ward)
Update training materials based on feedback. |  |  | Design role-playing mechanics (medical scenarios) (Medical Ward)
Expand scenarios and add new medical case studies over time. |  |  | Gather feedback from lecturers and students.
Develop Performance improvements
Sprint 5
Deploy to higher Environment
Develop Immersive 3d hospital (Medical Ward)
Develop VR doctor and patient models (Medical Ward)
Develop interactive medical tools (Medical Ward)
Develop role-playing mechanics (medical scenarios) (Medical Ward)
Testing Medical Ward
Design Immersive 3d hospital (Operating Room)
Design VR doctor and patient models (Operating Room)
Design interactive medical tools (Operating Room)
Design role-playing mechanics (medical scenarios) (Operating Room)
Gather feedback from lecturers and students.
Sprint 6
Deploy to higher Environment
Develop Immersive 3d hospital (Operating Room)
Develop VR doctor and patient models (Operating Room)
Develop interactive medical tools (Operating Room)
Develop role-playing mechanics (medical scenarios) (Operating Room)
Testing Medical Rooms
Design Immersive 3d hospital (Maternity Care)
Design VR doctor and patient models (Maternity Care)
Design interactive medical tools (Maternity Care)
Design role-playing mechanics (medical scenarios) (Maternity Care)
Gather feedback from lecturers and students.
Maternity Care
Behavioral and Mental Health Rooms
Family Room
Neonatal Intensive Care Unit (NICU)
Sprint 7
Deploy To Higher Environment
Develop Immersive 3d hospital (Maternity Care)
Develop VR doctor and patient models (Maternity Care)
Develop interactive medical tools (Maternity Care)
Develop role-playing mechanics (medical scenarios) (Maternity Care)
Testing Maternity Care
Design Immersive 3d hospital (Behavioral and Mental Health Rooms)
Design VR doctor and patient models (Behavioral and Mental Health Rooms)
Design interactive medical tools (Behavioral and Mental Health Rooms)
Design role-playing mechanics (medical scenarios) (Behavioral and Mental Health Rooms)
Gather feedback from lecturers and students.
Sprint 8
Deploy To Higher Environment
Develop Immersive 3d hospital (Behavioral and Mental Health Rooms)
Develop VR doctor and patient models (Behavioral and Mental Health Rooms)
Develop interactive medical tools (Behavioral and Mental Health Rooms)
Develop role-playing mechanics (medical scenarios) (Behavioral and Mental Health Rooms)
Testing Behavioral and Mental Health Rooms
Design Immersive 3d hospital (Family Room)
Design VR doctor and patient models (Family Room)
Design interactive medical tools (Family Room)
Design role-playing mechanics (medical scenarios) (Family Room)
Gather feedback from lecturers and students.
Sprint 9
Deploy To Higher Environment
Develop Immersive 3d hospital (Family Room)
Develop VR doctor and patient models (Family Room)
Develop interactive medical tools (Family Room)
Develop role-playing mechanics (medical scenarios) (Family Room)
Testing Family Room
Design Immersive 3d hospital (Neonatal Intensive Care Unit (NICU))
Design VR doctor and patient models (Neonatal Intensive Care Unit (NICU))
Design interactive medical tools (Neonatal Intensive Care Unit (NICU))
Design role-playing mechanics (medical scenarios) (Neonatal Intensive Care Unit (NICU))
Gather feedback from lecturers and students.
Sprint 10
Deploy To Higher Environment
Develop Immersive 3d hospital (Neonatal Intensive Care Unit (NICU))
Develop VR doctor and patient models (Neonatal Intensive Care Unit (NICU))
Develop interactive medical tools (Neonatal Intensive Care Unit (NICU))
Develop role-playing mechanics (medical scenarios) (Neonatal Intensive Care Unit (NICU))
Testing Neonatal Intensive Care Unit (NICU)
Sprint 11
Deploy To Higher Environment
Pre-prod testing
Deploy to Production
Deploy to production
Creation of User Training Manual
User Training for Students and Lecturers
Completion of User Training to Students and Lecturers

## Sheet2
For your case study of the VR Learning Platform for Healthcare Training using Scrum, I’ve broken down the project into 150 activities to include in Microsoft Project. These activities span across multiple phases of the project, including planning, development, testing, and deployment. They also cover key tasks like resource management, training, and risk management. Below is a suggested list of activities:
1. Project Initiation & Planning
1. Define project scope and objectives
2. Identify stakeholders
3. Assign project team roles
4. Develop initial project timeline
5. Set up project communication plan
6. Create project charter
7. Develop initial risk management plan
8. Define budget and resources
9. Conduct project kickoff meeting
10. Create high-level requirements
11. Establish project governance structure
12. Develop project roadmap
13. Set up project management tools
14. Review and approve project charter
15. Establish team work schedules
16. Assign project manager
17. Conduct stakeholder analysis
18. Define quality standards
19. Conduct initial feasibility study
20. Develop Scrum framework adoption plan
2. Requirements Gathering
21. Collect user requirements from healthcare faculty
22. Conduct focus groups with students and lecturers
23. Define VR technology requirements (hardware/software)
24. Gather cultural inclusivity requirements from Iwi/Māori representatives
25. Develop functional requirements for VR platform
26. Define system integration requirements (LMS)
27. Gather feedback from medical professionals for realistic simulation
28. Determine multi-user interaction requirements
29. Establish learner feedback system requirements
30. Prioritize features for the VR system
31. Finalize requirements documentation
32. Create use cases for VR learning scenarios
33. Define data privacy and security requirements
34. Create list of required medical procedures to simulate
35. Finalize cultural health practices to incorporate
36. Establish performance measurement criteria
37. Organize requirements review meeting
38. Sign off on final requirements
3. Design and Architecture
39. Develop system architecture design
40. Design 3D immersive environments (VR simulation spaces)
41. Define platform integration with existing LMS
42. Design multi-user interface for collaborative learning
43. Create UX/UI design for the VR platform
44. Develop VR content design (e.g., patient scenarios, emergency response)
45. Develop database structure for feedback system
46. Design VR hardware integration (headsets, controllers, etc.)
47. Develop culturally inclusive healthcare curriculum outline
48. Develop wireframes for system interfaces
49. Design feedback and performance review system
50. Create design approval plan
51. Review and approve design specifications
52. Create development environment and tools setup
53. Develop storyboards for learning scenarios
54. Develop technical documentation for VR system architecture
55. Design safety protocols for VR use
4. Development Phase (Sprints)
56. Set up project repository for source code
57. Sprint 1 planning (defining backlog tasks)
58. Develop core VR simulation engine
59. Integrate multi-user collaboration features
60. Develop VR medical procedure simulations
61. Code feedback system for students’ performance
62. Integrate existing LMS with VR platform
63. Develop user authentication system
64. Implement hardware integration with VR headsets
65. Develop cultural inclusivity features in simulation
66. Create tutorial and guide for lecturers in VR platform
67. Develop health scenario templates (diagnosis, response, etc.)
68. Implement UI for VR interaction (student/lecturer roles)
69. Conduct unit tests for individual features
70. Implement real-time feedback mechanism for students
71. Code VR interface for emergency scenarios
72. Sprint 1 review (retrospective meeting)
73. Sprint 2 planning (defining backlog tasks)
74. Develop patient avatars for simulation
75. Implement facial expressions and body language for avatars
76. Implement voice recognition and speech for scenario interaction
77. Integrate cultural symbols and health practices in the simulation
78. Develop interactive elements for emergency response scenarios
79. Enhance UX/UI based on feedback from sprint 1
80. Develop session recording feature for feedback
81. Implement scenario branching for different medical conditions
82. Implement real-time collaboration features (multi-user)
83. Develop integration with feedback system for performance tracking
84. Conduct system performance testing
85. Sprint 2 review (retrospective meeting)
86. Sprint 3 planning (defining backlog tasks)
87. Optimize VR performance (load times, frame rates)
88. Conduct cross-platform testing for VR hardware
89. Develop integration with learning materials (lecturer guides)
90. Test simulation scenarios for accuracy and realism
91. Finalize multi-user scenario testing
92. Implement student progress tracking feature
93. Develop system alerts and notifications for students
94. Review feedback from previous sprint
95. Sprint 3 review (retrospective meeting)
5. Testing Phase
96. Develop comprehensive test cases
97. Test VR simulations for usability and realism
98. Perform load testing for multi-user scenarios
99. Conduct performance benchmarking of VR platform
100. Test integration with existing LMS
101. Conduct cultural inclusivity testing (Iwi/Māori focus)
102. Perform security testing (data privacy)
103. Conduct compatibility testing with different VR hardware
104. Perform cross-browser testing (for web-based LMS)
105. Conduct user acceptance testing (UAT) with students
106. Perform accessibility testing for diverse user groups
107. Review feedback from UAT sessions
108. Conduct hardware stress testing (VR headsets)
109. Document testing results and issues
110. Resolve testing issues and bugs
111. Perform regression testing after bug fixes
112. Test instructor feedback and review system
113. Conduct real-time collaboration testing
114. Perform end-to-end testing of all integrated systems
115. Review testing progress with stakeholders
116. Sign-off on testing completion
6. Deployment & Implementation
117. Create deployment plan
118. Prepare VR hardware (set up headsets, controllers)
119. Integrate VR system with the Polytech’s infrastructure
120. Prepare for initial user training (lecturers and students)
121. Deploy VR platform in a staging environment
122. Configure LMS integration in production environment
123. Set up monitoring and logging for system health
124. Conduct deployment smoke test
125. Deploy VR platform for pilot users
126. Monitor deployment for issues
127. Provide first-line user support for pilot users
128. Finalize user training content (manuals, videos, FAQs)
129. Conduct first round of user training sessions
130. Conduct second round of user training sessions
131. Provide continuous user support during pilot
132. Collect user feedback during pilot
133. Analyze pilot data and resolve issues
134. Refine VR platform based on pilot feedback
135. Final deployment to all users
136. Provide final user training for all students and lecturers
137. Set up support desk for ongoing technical support
138. Perform final review meeting with stakeholders
139. Conduct project closeout meeting
140. Finalize all documentation
141. Sign-off on project completion
142. Deliver final project report
7. Maintenance & Continuous Improvement
143. Monitor system performance regularly
144. Analyze usage data for potential improvements
145. Conduct periodic updates to VR content
146. Review feedback for ongoing improvements
147. Release software updates and patches as needed
148. Conduct periodic user training refresher courses
149. Conduct annual review of the system with stakeholders
150. Collect and analyze new requirements for future improvements
This breakdown can be imported into Microsoft Project, where you can further assign durations, dependencies, and resources based on your team's capacity and project timeline. You can also adjust these activities to fit within your sprint cycles if you’re using Scrum as your framework.

## Sheet3
1 | HR Manager
1 | Engineering Manager
2 | Senior Platforms Engineer
1 | Risk Management Specialist
1 | Cultural Consultant
1 | Senior Product Owner
2 | Senior VR Software Engineer
2 | full stack software engineer
3 | Associate full stack software Engineer
5 | Fullstack software engineer Intern
1 | QA Engineer
1 | Senior VR UI Designer
1 | Senior Designer/Content Developer
1 | Trainer